A Site-Selection and Investment Framework for Procon 24/7's Self-Funded Five-Year Expansion in the UK Ready-Mixed Concrete Sector, Applied to the 2027 Location Decision

| Item | Detail |
| --- | --- |
| Module | BEMM117DA Strategic Business Proposal — Assessment 2 |
| End-point assessment | CMI Assessment Method 1 — L7 Senior Leader (ST0480 v1.2) |
| Apprentice | [NAME] |
| Organisation | Procon 24/7 Ltd |
| Role | Business Manager (P&L accountability) |
| Submission | 9 November 2026 |
| Word count | [WORD_COUNT] (excluding tables, figures, references and appendices) |
| KSB mapping | Appendix 16 (all fifteen KSBs, by section) |
| Employer verification | Appendix 17 |

Contents

1. Executive Summary	3

2. Introduction and Statement of the Problem	4

3. Discussion of the Proposal and Problem	6

3.1 External drivers	6

3.2 The internal cause	7

3.3 Symptoms and quantified consequences	7

3.4 Brand and reputation: a critical evaluation	7

3.5 Resistance and conflicting views	8

4. Methodology, Results and Options Analysis	9

4.1 Research design and its justification	9

4.2 Positionality, ethics and limitations	10

4.3 Findings	11

4.4 Options analysis	12

5. Recommendations and Implementation Plan	16

5.1 Recommendation	16

5.2 Funding strategy: a critical evaluation	16

5.3 Governance, procurement and legal requirements	18

5.4 Budget and resources	18

5.5 Stakeholder engagement and communication	19

5.6 Negotiation and influence	19

5.7 Implementation, change and risk	20

5.8 Progress to date	21

6. Conclusion	22

References	23

Appendices	28

Appendix 1. Stakeholder map and communication plan	29

Appendix 4. Competitor coverage map, PESTEL and SWOT	30

Appendix 5. Depot cost model extract	33

Appendix 8. Break-even model	35

Appendix 9. Scenario and sensitivity pack	36

Appendix 10. Site long-list and feasibility notes	38

Appendix 12. Board presentation and depot model	39

Appendix 14. Implementation Gantt chart and RACI matrix	40

Appendix 15. RAID log	41

Appendix 16. KSB mapping	44

Appendix 19. Declined-work analysis, Leeds and Warrington (April to July 2026)	47

# 1. Executive Summary

This proposal recommends that Procon 24/7 open its 2027 depot in South Yorkshire (Option A) at a capital cost of £278,520. On the board's depot model it breaks even at 596 cubic metres a month, against 842 planned for its first year, and recovers its capital in 23 months, so existing depots must fund about £274,000 of the 2028 depot. The board approved the recommendation and the framework behind it on [APPROVAL_DATE] (Appendix 13).

The decision matters because Procon's five-year plan opens one self-funded depot a year, yet the business had no repeatable way to choose sites. Gross margin per cubic metre varies [MARGIN_MULTIPLE]-fold across its three depots, ready-mixed concrete volumes are the lowest since 1963, and from 2028 volumetric mixers lose the weight derogation on which their payload depends.

A weighted site-selection framework was built from industrial location theory, tested through [N] semi-structured interviews and applied to four options, including deferral, with service capacity weighted to protect the delivery reliability on which Procon's reputation rests. Success is measured by six indicators (Table 1), led by adoption of the framework as standard investment governance and a minimum margin of £[TARGET_MARGIN_M3] per cubic metre.

# 2. Introduction and Statement of the Problem

Procon 24/7 Ltd, an owner-managed supplier of ready-mixed concrete, operates volumetric and static plant from depots in Pontefract, Leeds and Warrington. In [YEAR] the board adopted a five-year growth strategy built on sequential self-funding: a new depot each year from 2027, each capitalised by its predecessor's retained profit. The strategy is defensible in principle and fragile in execution, because it rests on a capability Procon does not hold: a repeatable way of deciding where to expand, and whether a site will return enough, fast enough, to fund its successor.

Desk research and Procon's own records confirmed three conditions that make this a material and time-bound problem, each resting on a different kind of evidence.

First, site economics dominate commercial effort. Gross margin per cubic metre varies [MARGIN_MULTIPLE]-fold between Procon's strongest and weakest depots ([INTERNAL SOURCE: management accounts, FY20XX]). Ready-mixed concrete is perishable and usually supplied within eight miles of the point of use (Mineral Products Association [MPA], 2025a), so profitability is fixed largely by catchment geometry at selection and little can be recovered afterwards.

Second, the sector is contracting sharply, which raises the cost of a wrong choice. Great Britain volumes for the four quarters to Q2 2025 were 11.9 million cubic metres, the lowest since 1963, and fell for a fourth consecutive year in 2025 (MPA, 2025b, 2026). The contraction is uneven: the Construction Products Association (CPA, 2026) forecasts total output down 3.3% in 2026 and private housing down 10.0%, while infrastructure grows 3.2% in both 2026 and 2027. Demand is moving between sectors, and therefore between places.

Third, a regulatory change falls inside the funding chain itself. From 2028 volumetric mixers lose the derogation allowing them to run at 38.4 tonnes (four-axle) and 44 tonnes (five-axle), reverting to the standard 32-tonne limit with no further extensions (Department for Transport [DfT], 2025b). Payload per journey falls by around [PAYLOAD_LOSS_PCT]%, delivered cost rises by an estimated £[COST_PER_M3_DELTA] per cubic metre and the viable haul radius shrinks, all in the year the 2027 depot is meant to fund its successor.

Against these conditions, site decisions have rested on directors' judgement, and no profitability threshold has ever been modelled.

The aim is to develop and apply a weighted site-selection and investment framework enabling Procon 24/7 to appraise expansion locations on modelled evidence, and to recommend the 2027 location to the board by 5 November 2026. Five objectives support it: establish the demand and competitive baseline for candidate catchments; build a validated cost and break-even model incorporating the 2028 payload reduction; design and weight selection criteria with operational input; appraise the options against a do-nothing baseline; and secure board approval. The scope is the 2027 location decision and the reusable framework; site-level design, pricing policy and the 2028–2031 site choices are excluded. Table 1's indicators meet Doran's (1981) SMART criteria, but SMART rewards results over decision quality, so KPI 6 audits the forecast itself.

Table 1. Key performance indicators and intended impact

| KPI | Baseline | Target | Measurement | Owner | Review |
| --- | --- | --- | --- | --- | --- |
| Framework adopted as standard investment governance | No process exists | Adopted and mandated for all site decisions by [DATE] | Board minute | Managing Director | [DATE] |
| Minimum gross margin per m³ for approval | Undefined | £[TARGET_MARGIN_M3]/m³, set by [DATE] | Management accounts | Business Manager | Quarterly |
| Months to capital payback, 2027 depot | n/a | 23 months or fewer (board model: 23.1) | Depot P&L | Business Manager | Monthly |
| 2028 depot funded from retained trading profit | n/a | No external finance; base-business share £274,303 or less | Cash flow forecast | Managing Director | [DATE] |
| Capacity-related declined enquiries, existing depots (reputation) | 22 of 27 declines, Apr–Jul 2026 | [TARGET, e.g. halved by month 12] | Declined-work logs | Operations Manager | Monthly |
| Forecast accuracy of the appraisal (decision quality) | No forecast has been audited | Month-12 volume and contribution within [X]% of forecast | Post-completion audit (§6) | Business Manager | Month 12 |

# 3. Discussion of the Proposal and Problem

## 3.1 External drivers

A PESTEL analysis (Whittington et al., 2023) covers six domains, but they do not bear equally on this decision; Appendix 4 carries them into an external-first SWOT (Minsky & Aron, 2021). Political, social and technological factors shape the sector yet barely discriminate between catchments. The legal domain is decisive: the 2028 weight reversion (DfT, 2025b) is a dated, confirmed change to the unit economics of Procon's delivery model, and the National Highways bridge-loading evidence behind it makes reversal implausible (DfT, 2025a).

The economic domain is the second determinant. CPA's (2026) forecast divergence between private housing and infrastructure matters most for site selection: housing-led and infrastructure-led catchments face opposite trajectories across the depot's payback period. Here the economic and environmental domains interact. National Highways requires its large and medium Tier 1 suppliers to hold verified PAS 2080 carbon management systems (National Highways, 2024), and the standard expects material suppliers to share product carbon data (British Standards Institution [BSI], 2023), so the requirement reaches Procon indirectly, through contractors' requests for Environmental Product Declarations (MPA, 2025a). Low-carbon capability is becoming a condition of entry to the growth segment. Volumetric batching has an advantage here, since concrete mixed on site when needed reduces waste (DfT, 2023), but the advantage is marketable only once quantified from Procon's returned-load records: environmental claims must be substantiated (Competition and Markets Authority [CMA], 2021), and an unsupported claim would damage the reputation it was meant to build.

Under Porter's (2008) five forces, rivalry is structurally intense: MPA members alone operate 740 ready-mixed concrete plants (MPA, 2025a), the product is close to commodified and price is set largely outside the firm. Warrington's largest declined enquiry, 200 cubic metres, was lost to a competitor, Chorley Concrete (Appendix 19). Supplier power is rising: cement imports rose from 11% of the UK market in 2004 to 32% in 2023 (MPA, 2025a), and from January 2027 the UK carbon border adjustment mechanism (CBAM) taxes the embodied emissions of imported cement (HM Revenue & Customs [HMRC], 2025), so input costs are likely to rise in the new depot's first year. In Kraljic's (1983) terms cement is a strategic purchase, requiring supply-relationship management rather than transactional buying.

The binding constraint in the target catchment is therefore not rivalry in the abstract but [BINDING_FORCE — see register], because [REASON, citing Appendix 4]. The selection criteria encode that conclusion.

## 3.2 The internal cause

The external environment explains why the decision is difficult, not why Procon is badly equipped to make it. Under Barney's (1995) VRIO test, an evidence-based site-selection capability is valuable, since the [MARGIN_MULTIPLE]-fold margin variation shows selection quality turning directly into returns; rare among owner-managed operators who decide by judgement; and hard to imitate, because its value comes from combining the method with Procon's own data. What Procon lacks is the fourth condition, organisation: no process, no threshold, no repeatable appraisal. Experience can entrench the gap: familiar methods blind people to better ones, the Einstellung effect (Luchins, 1942).

The framework draws on industrial location theory because the underlying problem is spatial. Weber's (1909/1929) least-cost model, in which the best site minimises the combined cost of assembling inputs and distributing output, fits ready-mixed concrete directly: aggregate and cement in, a perishable product out against the clock. Hotelling (1929) shows that competitors cluster rather than disperse, so the measure that matters is demand per unit of competing capacity, not absolute demand. Church and ReVelle's (1974) maximal covering location problem formalises the eight-mile radius: cover as much demand as possible within a fixed service distance.

## 3.3 Symptoms and quantified consequences

A 5 Whys analysis (Ohno, 1988) runs back from symptom to cause. Because funding is sequential, one weak site stalls the plan, stranding roughly £[CAPITAL_AT_RISK] in plant, fleet and yard and delaying every later opening by at least twelve months. Weak sites get through because no margin threshold exists, which is why margins vary [MARGIN_MULTIPLE]-fold; no threshold exists because judgement is unmodelled; and judgement is unmodelled because Procon has no repeatable method. Flyvbjerg (2008) shows that cost underestimation and benefit overestimation are strongest where appraisal relies on judgement and ignores reference data, which describes Procon's current approach.

## 3.4 Brand and reputation: a critical evaluation

Fombrun and Shanley (1990) treat reputation as an intangible asset built through repeated signals of reliability. Keller's (1993) brand equity model, by contrast, was developed for consumer markets, and its transfer to business buyers is contested: Leek and Christodoulides (2012), interviewing ten supplier managers, find that business brand value rests on functional qualities such as reliability and capacity, and on the risk reduction and trust they create. A contractor booking a pour is buying confidence that the wagon will arrive, so where price is set externally, reliability is the main source of differentiation and pricing power. In resource-based terms (Barney, 1991), Procon's delivery reputation is a strategic asset, costly to imitate because it is earned through performance.

Procon's records show that asset already at risk. Between April and July 2026 the Leeds and Warrington depots declined 27 enquiries, 22 of them for want of drivers, vehicles or slots (coded by the author, Appendix 19). By volume the picture reverses: those 22 came to 75 cubic metres, under a third of the 250 or more lost on price, which is why such refusals are easy to ignore. Count is the better measure of reputational risk, since each refusal reaches a buyer: the 22 reached 16 customers, one of them five times. The logs also record what buyers did, which Leek and Christodoulides's interviews cannot: two Leeds customers offered an afternoon slot did not book; one 'moved on'. The 2028 payload reduction will tighten the same constraint, because smaller loads mean more journeys, drivers and vehicle hours per cubic metre. Reputation is also plural: Harvey et al. (2017), studying one consulting firm, find competing reputations across stakeholders and places, each sustained through the stakeholder's own relationship with the firm. If that transfers, a failure in a new catchment, or a success, travels mainly through customers buying from more than one depot: [CROSS_DEPOT_SHARE]% of 2025/26 volume (sales ledger).

That leaves a tension the proposal must resolve. Rapid sequential expansion is the strategy most likely to over-extend service capacity and damage the asset its economics rely on, and the same evidence strengthens the case for consolidating first (Option C), which Section 5.2 tests. This is the limits-to-growth archetype (Clancy, 2018; Senge, 2006): self-funding drives growth, service capacity constrains it, and the leverage lies in easing the constraint. Location science shows how: backup coverage models value a second unit able to serve demand when the first is unavailable (Hogan & ReVelle, 1986). The framework applies that logic by weighting service capacity headroom (Table 4) and tracking capacity-related declines as a KPI (Table 1), so a catchment demanding more than demonstrated capability ranks down whatever its demand.

## 3.5 Resistance and conflicting views

[RESISTANCE_NARRATIVE — ~80 words in your own voice: role; stated position; the interest beneath it; how it was resolved; what changed in the proposal. Optional lens from Masterclass 1: Lewin's force-field analysis, driving versus restraining forces, and whether you pushed or reduced the obstacle (Hayes, 2022); one clause at most. The reading list's Essential item on disagreement, Julia Dhar's TED talk 'How to disagree productively and find common ground', fits here; reference it only if you cite it.]

# 4. Methodology, Results and Options Analysis

## 4.1 Research design and its justification

The design runs from philosophy to technique, and Table 2 records the alternative rejected at each stage, with reasons. The position is pragmatist: the problem needs measurable cost data and tacit practitioner knowledge together, and pragmatism admits both without an artificial commitment to one epistemology (Easterby-Smith et al., 2021; Saunders et al., 2019).

Table 2. Methodological decisions and rejected alternatives

| Decision | Position adopted | Alternatives rejected | Justification |
| --- | --- | --- | --- |
| Philosophy | Pragmatism | Positivism; interpretivism | Decision requires both measurable cost data and tacit operational knowledge. Positivism rejected: the cost assumptions are not directly observable and need practitioner validation. Interpretivism rejected: the board needs quantified break-even and payback figures |
| Approach | Abductive | Deduction; pure induction | Framework derived from location theory, then revised against empirical interview data |
| Strategy | Single case study with embedded units (three depots) | Multiple-case; survey | Depth of proprietary cost access outweighs cross-case generalisability (Yin, 2018) |
| Method | Sequential mixed methods (QUAN → qual → QUAN) | Mono-method quantitative | Secondary data defines the problem; interviews test assumptions; modelling resolves it; interview guide and transcript at Appendices 6 and 7 |
| Sampling | Purposive census of [N] expert roles (Operations Manager, Business Development Manager, Scheduler, key material suppliers) | Random; convenience | Every internal role holding the relevant knowledge was interviewed, with key suppliers chosen purposively: [N] in all. As internal managers and external suppliers the group is heterogeneous, so it falls below both the 15–60 norm for workplace interviews and the 12–30 suggested for heterogeneous groups (Saunders, 2012, as cited in Saunders & Townsend, 2016). The defence is purpose: the interviews test the model's assumptions, not thematic saturation, an exception Saunders and Townsend (2016) allow where study purpose and data saliency justify it |
| Conduct | [N] interviews, [in person / Teams], [XX–XX] minutes; [audio-recorded with consent / notes taken]; [transcribed verbatim / summarised]; [information sent in advance] (Appendix 6) | [e.g. unrecorded conversations] | [Why: e.g. a reader could replicate the study; transcripts support the thematic coding] |
| Analysis | Descriptive statistics; thematic analysis; MCDA | Inferential statistics | Expert sample too small for statistical inference; thematic analysis suits explanatory interview data (Braun & Clarke, 2006; Easterby-Smith et al., 2021) |

The sequence in Table 2 matters: interviews first would have produced opinion with nothing to anchor it, and without them the cost model would rest on unchecked assumptions. Validity rests on triangulating theory, secondary data and practitioner evidence; reliability on recording the provenance of every weighting (Table 4; Appendix 2), so another analyst could reproduce the scores.

## 4.2 Positionality, ethics and limitations

I conducted this research as an insider. As Business Manager with profit and loss accountability I have a stake in the outcome and chair the sponsor reviews that scrutinised it, a position with both advantages and hazards (Coghlan & Brannick, 2014; Costley et al., 2010). It gave access to the management accounts and to candid colleagues, but three hazards needed structural mitigation. Confirmation bias towards expansion was countered by specifying the do-nothing and deferral options before analysis and by [REVIEWER_ROLE]'s independent review of the model. Power asymmetry, with three of five interviewees in my reporting line, was countered by framing interviews as a search for flawed assumptions, anonymising material and inviting disagreement. Optimism bias in the ramp-up estimate (Flyvbjerg, 2008, 2021) was countered by anchoring it to the trading history of Procon's most recent opening.

The Managing Director gave organisational consent as sponsor, and the study followed [ETHICS_ROUTE — describe what actually happened; if there was no University ethics review, say what you did and confirm with the programme team]. Participation was voluntary and informed, identifying material was anonymised, and supplier pricing is reported in aggregate.

Three limitations qualify the findings. Competitor costs are proxied from Companies House filings, so conclusions on relative cost position are indicative. MPA volume data comes from a member survey covering just over 60% of Great Britain sales (MPA, 2025a), so regional figures carry sampling uncertainty. Single-case research limits generalisation, but the deliverable is an internal capability, not a general theory.

## 4.3 Findings

Secondary analysis established the demand and competitive baseline. South Yorkshire combines funded Sheffield regeneration (Heart of the City II, £470m; West Bar, £300m) with live council and National Highways frameworks, and two large Leeds accounts have sites there that Procon does not yet serve (Appendix 12). Following Hotelling (1929), the competitor mapping at Appendix 4 measured demand per unit of competing capacity. [CATCHMENT] ranked [POSITION] on absolute demand and [POSITION] per unit of competing capacity, [RANKING_EFFECT — so the second measure changed the ranking / and the two measures agreed].

Cost-volume-profit analysis (Drury, 2021) of the board model gives a contribution of £51.74 per cubic metre and break-even at 26.5 cubic metres a day (Appendix 8). The model omits the 2028 payload effect, which adds £[COST_PER_M3_DELTA] per cubic metre.

The primary research tested the criteria and weightings derived from location theory. The initial matrix weighted [CRITERION] at [W_BEFORE]%. Evidence from [SOURCE — interviewee role, or the declined-work logs] on [TOPIC] showed that [INSIGHT — what the evidence actually showed], and the weighting was [REVISED_TO_OR_CONFIRMED — revised to X% / confirmed]. Applying the final weightings [EFFECT_ON_RANKING — reversed the ranking / narrowed the margin to X points / confirmed the original order]. [NOTE — the capacity headroom criterion in Table 3 may be this change, if it was added after the declined-work evidence; present it that way only if it was.]

This bears on how much weight the evidence can carry. [KEEP ONE, ~25 words: if the interviews changed a weighting, the primary research was formative, because the recommendation rests on inputs the secondary data would not have surfaced; if they confirmed the weightings, the convergence is itself evidence, because the weights came from location theory before practitioners saw them.]

Table 3. Findings by research strand and effect on the framework

| Strand | Principal finding | Evidence | Effect on framework |
| --- | --- | --- | --- |
| Demand and catchment | Funded Sheffield regeneration pipeline; live council and National Highways frameworks, with SDF2 Lot 2 live from 2027; two Leeds accounts and a framework contractor already working in South Yorkshire | CPA (2026); Office for National Statistics (2026); board presentation, Appendix 12; Appendix 3 | Named pre-sell targets for G3; [EFFECT on the infrastructure exposure score] |
| Competition | [FINDING] | Competitor mapping, Appendix 4 | Demand measured per unit of competing capacity |
| Service reliability | 22 of 27 declined enquiries (Apr–Jul 2026) were capacity-related; by volume, price losses (≥250 m³) exceeded capacity losses (75 m³) | Declined-work logs, Appendix 19 | Capacity headroom criterion introduced at [XX]% [CHECK: keep 'introduced' only if the criterion was added after this evidence; if it was, this is the §4.3 weighting change] |
| Cost base | Variable cost £67.26/m³ (materials £61.26, a low-cement mix); certified (BSI) mixes average £75.68 in materials alone; post-2028 £[XX.XX] | Board model; supplier package costs, Appendix 12 | Mix and certification tested in sensitivity (Appendix 9); post-2028 cost to be modelled |
| Land and feasibility | Nine surfaced 1.0–1.5-acre yards in the Sheffield–Doncaster corridor at £50,000–£70,000 a year; one freehold at £1.0m | Land agents; planning portals; Appendix 10 | Lease preferred: rent moves payback by under a month; freehold would stretch it to 43 months |
| Regulatory | Payload reduction of [XX]% from 2028 | DfT (2025a, 2025b) | Payload resilience criterion weighted at [XX]% |

## 4.4 Options analysis

Four options were appraised: two candidate catchments (A and B); deferral of the 2027 opening to consolidate the existing depots (C); and doing nothing, which anchors the cost of inaction. The appraisal is a two-stage cost benefit analysis: multi-criteria decision analysis ranks the options on priced and unpriced criteria, since capacity headroom and payload resilience cannot be collapsed into one monetary figure without hiding trade-offs the board needs to see (Belton & Stewart, 2002), and a financial appraisal then tests the ranking against cash. Weights came from pairwise comparison using Saaty's (2008) analytic hierarchy process, with a consistency ratio of [CR] against his 0.10 ceiling (Appendix 2).

Table 4. Weighted multi-criteria decision matrix (pairwise working at Appendix 2; ranked shortlist at Appendix 11)

| Criterion | Weight % | Provenance of weight | A | B | C | Baseline |
| --- | --- | --- | --- | --- | --- | --- |
| Catchment demand density (8-mile radius) | [XX] | Church & ReVelle (1974); [revised post-interview / confirmed by interviews] | [X] | [X] | [X] | [X] |
| Demand per unit of competitor capacity | [XX] | Hotelling (1929); competitor mapping | [X] | [X] | [X] | [X] |
| Post-2028 payload resilience | [XX] | DfT (2025b); Operations Manager interview | [X] | [X] | [X] | [X] |
| Infrastructure pipeline exposure | [XX] | CPA (2026) sectoral divergence | [X] | [X] | [X] | [X] |
| Operating cost base | [XX] | Weber (1909/1929); internal cost model | [X] | [X] | [X] | [X] |
| Land cost and availability | [XX] | Land agent data; planning feasibility | [X] | [X] | [X] | [X] |
| Low-carbon supply capability | [XX] | PAS 2080 client requirements (BSI, 2023; National Highways, 2024); UK Concrete & MPA (2025); proximity to low-clinker cement and ground granulated blast-furnace slag (GGBS) supply | [X] | [X] | [X] | [X] |
| Service capacity headroom (fleet and driver availability) | [XX] | Hogan & ReVelle (1986) backup coverage; declined-work logs, Appendix 19 | [X] | [X] | [X] | [X] |
| Weighted total | 100 | — | [XX.X] | [XX.X] | [XX.X] | [XX.X] |

Note. Option C and the baseline are scored on the catchments they would continue to serve.

The financial stage treated every option identically (Table 5), using the board's depot model, corrected after review (Table A9.4). Payback, not net present value, is the primary ranking metric, a deliberate departure from convention: because expansion funds itself sequentially, the timing of cash decides whether the 2028 depot happens at all, and an option with higher net present value but slower payback would break the chain it is meant to sustain. Payback's known weaknesses, ignoring the time value of money and cash flows after the cut-off (Drury, 2021), are contained by discounting it at [X]%, [DISCOUNT_RATE_BASIS, e.g. the owners' required return on retained equity], and by excluding any option with a negative net present value. Accounting rate of return was set aside because it ignores timing, on which the chain depends, and internal rate of return because it can mis-rank options of different scale (Drury, 2021).

Table 5. Financial appraisal — identical treatment across options (models at Appendices 5, 8 and 9)

| Measure | Option A | Option B | Option C (defer) | Baseline |
| --- | --- | --- | --- | --- |
| Capital requirement — fleet, plant, yard (£) | 278,520 | [XXX,XXX] | [XX,XXX] | 0 |
| Fixed operating cost p.a. (£) | 369,940 | [XXX,XXX] | [XX,XXX] | [XXX,XXX] |
| Contribution per m³ (£) | 51.74 | [XX.XX] | [XX.XX] | [XX.XX] |
| Break-even volume (m³/month) | 596 | [XXX] | n/a | n/a |
| Break-even volume post-2028 (m³/month) | 761 with a third wagon (payload effect not yet modelled) | [XXX] | n/a | n/a |
| Operating break-even reached (month) | Not estimable: annual model | [XX] | n/a | n/a |
| Payback (months) | 23 | [XX] | n/a | n/a |
| Discounted payback at [X]% (months) | 24.7–25.5 at 8–12% (Table A9.3) | [XX] | n/a | n/a |
| Cash generated by the 2028 opening (£) | 4,217 (year-1 free cash flow) | [XXX,XXX] | n/a | n/a |
| NPV at [X]% over 5 years (£) | 889,618–1,053,412 at 12–8% (Table A9.3) | [XXX,XXX] | [XX,XXX] | 0 |
| Funds 2028 depot without external finance | Only with £274,303 from existing depots | [Y/N] | No | No |

Sensitivity analysis tested the three variables the interviews flagged as least certain, and price (Appendix 9). A first-year volume shortfall of 25% stretches payback from 23 to 26 months; material inflation of 10% cuts contribution to £45.61 per cubic metre and stretches it to 27; rent barely matters. Price matters most: 10% lower, payback reaches 33 months. The board plan prices 9% below the local market average, buying entry with price where Section 3.4 argues reliability should earn it, and the discount pays only if it wins a quarter more volume than market rates would.

The framework has limits of its own. Pairwise weightings are judgements expressed as numbers; the analytic hierarchy process disciplines judgement without removing it. Scoring on a common scale also imposes the commensurability this section denied, so the weighted total is a structured comparison, not a measurement. And a framework validated by internal practitioners may encode Procon's existing assumptions. It still improves on what it replaces, because it turns tacit judgement into explicit, repeatable knowledge (Nonaka, 2008): a board can argue with a weighting, but not with an intuition.

# 5. Recommendations and Implementation Plan

## 5.1 Recommendation

Procon should proceed with Option A, South Yorkshire, at a capital cost of £278,520. It ranks first on the weighted framework, scoring [MCDA_SCORE_A] against [MCDA_SCORE_B] for the nearest alternative; breaks even at 596 cubic metres a month, 29% below planned first-year volume; and recovers its capital in 23 months. It is the only option that allows the 2028 depot to open without external finance and remains viable under post-2028 payload limits. Its advantage over Option B lies in [ADVANTAGE_OVER_B — the Table 4 criteria that separate them].

## 5.2 Funding strategy: a critical evaluation

The board's commitment to self-funding is consistent with pecking-order theory: firms prefer internal finance because information asymmetry makes external capital costly (Myers & Majluf, 1984), and in an owner-managed business the wish to retain control reinforces the preference. But a rational preference is not necessarily optimal, and the board's instinct should be tested, not assumed.

Higgins (1977) makes the cost of that preference measurable: without new equity or higher gearing, growth cannot exceed the return on equity multiplied by the share of profit retained. Procon's chain sharpens the limit, because a depot that has not recovered its capital by the next opening must be underwritten by the existing three. With a 23-month payback against a twelve-month interval, the base business funds £274,303 of a same-cost 2028 depot, as working capital absorbs first-year cash (Figure 1); that figure, not the board's preference, sets the true pace of self-funded growth.

Figure 1. Cumulative cash from the South Yorkshire depot by scenario, against the 2028 opening

Note. Rebuilt from the depot model presented to the board (Appendices 5 and 9); the scenarios apply the board's multipliers to every year, volume included. First-year EBITDA is £152,957, but free cash flow is £4,217, because working capital (£105,438), tax and maintenance absorb it. At the 12–18-month interval the board presentation plans for its next depot, the existing depots fund £126,345–£274,303 of it.

Four routes were evaluated (Table 6). Self-funding preserves control and avoids covenant exposure at a sixty-two-year volume low, but caps expansion at one depot a year, and the cap has a price: with infrastructure growing while capacity leaves the sector (CPA, 2026; MPA, 2026), today's catchments will not stay available, and single-depot pacing forgoes an estimated £[OPPORTUNITY_COST] in contribution. Asset finance, secured on the vehicles rather than the base business, sits between self-funding and debt, though its fixed payments raise cash break-even during ramp-up.

Deferral is underrated in the board's framing. Under real options reasoning (Dixit & Pindyck, 1994), waiting has value when uncertainty is high and commitment irreversible, and both hold here. But the option's value is falling: the CPA forecasts and the DfT's confirmed timetable have already resolved much of the uncertainty that waiting would address, while deferral means entering after competitors have absorbed the payload change. Nor is consolidation a clear cure for the capacity declines that make it look prudent (Section 3.4). Warrington's declines trace to vehicles off the road and driver cover, which are operating fixes, but six of the nine at Leeds record only that nothing was free before about 4pm, with no cause given (Appendix 19). [SCHEDULER_FINDING — what fills the Leeds mornings, from the Scheduler interview. If drivers or scheduling, the operating-fix argument holds for both depots; if vehicles, Leeds needs capacity, which strengthens Option C: say so and show how the recommendation absorbs it.]

The recommendation is to proceed self-funded for 2027 and to depart from strict self-funding only if a defined trigger is met: [TRIGGER, e.g. operating break-even by month [XX] prompts review of asset-financed acceleration of the 2029 opening, since demonstrated performance reduces the information asymmetry behind the pecking-order preference]. That respects the board's risk appetite while preventing a sound preference from hardening into an unexamined constraint.

Table 6. Funding route evaluation

| Route | Advantages | Disadvantages | Assessment |
| --- | --- | --- | --- |
| Self-fund (recommended for 2027) | No gearing; full control; consistent with pecking-order preference | Caps growth to one depot p.a.; opportunity cost £[OPPORTUNITY_COST] | Adopt for 2027, with defined trigger for review |
| Asset finance on fleet (hire purchase or lease) | Releases cash for land and working capital; secured on vehicles, not the base business; 32t-compliant specification protects residual value | Higher fixed payments during ramp-up raise cash break-even; finance cost £125,600 a year for two vehicles in the board model | Preferred acceleration route if the trigger is met |
| Debt-funded acceleration | Captures infrastructure growth window; two depots in 2027 | Interest £[INTEREST_COST]; covenant exposure threatens base business | Reject; asset finance preferred if trigger met |
| Defer to 2028 | Real-option value under uncertainty; more data | Competitors adjust first; land off cycle floor; delay compounds | Reject — option value declining |

## 5.3 Governance, procurement and legal requirements

Capital release of £278,520 exceeds the Managing Director's delegated authority and requires minuted board approval. Fleet procurement must specify 32-tonne-compliant vehicles now, because Vehicle Special Orders lapse at a vehicle's twelfth anniversary of first registration regardless of the 2028 date (DfT, 2025a); buying to the expiring standard would create a depreciating compliance liability. The operator licence must be varied for the new operating centre, with maintenance arrangements evidenced before trading; the twelve Warrington enquiries lost to vehicles off the road (Appendix 19) make maintenance a reputational issue as well as a licence obligation. Supply agreements should run for [TERM] to hedge cement exposure, including CBAM pass-through, and secure lower-clinker cement and GGBS for clients requiring Environmental Product Declarations.

## 5.4 Budget and resources

Table 7. Capital and resource budget

| Item | Cost (£) | Timing | Funding source | Owner |
| --- | --- | --- | --- | --- |
| Land acquisition / yard lease | 0 capital; lease £60,000 a year | [MONTH] | Retained profit | Managing Director |
| Volumetric fleet (2 units, 32t-compliant) | 150,000 | [MONTH] | Retained profit | Business Manager |
| Cement silo and loading shovel | 60,000 | [MONTH] | Retained profit | Operations Manager |
| Yard works, drainage and compliance | 43,200 | [MONTH] | Retained profit | Operations Manager |
| Working capital (45 debtor days, 30 creditor days, 7 days' stock) | 105,438 | Year 1 | Retained profit | Business Manager |
| Recruitment and training | [XX,XXX] | [MONTH] | Retained profit | Operations Manager |
| Contingency (10%) | 25,320 | — | Retained profit | Business Manager |
| Total | 278,520 capital; 105,438 working capital | — | — | — |

Note. Capital from the board model's schedule (£253,200 plus 10% contingency), mostly second-hand estimates; yard works cover blocks, security, fencing, cabins, laboratory, gantry, dust suppression, wash bay and water storage. Recruitment and training are not in the model.

## 5.5 Stakeholder engagement and communication

Stakeholders were mapped on the power-interest matrix (Whittington et al., 2023), adapted from Mendelow's (1981) power-dynamism grid, and their positions drive the communication plan (Appendix 1). Because the grid is static, salience (Mitchell et al., 1997) tracks whose claims turn urgent at each gate, such as the planning authority's at G2. The Operations and Business Development Managers, engaged participatively, supplied evidence that tested the weightings (Section 4.3), and depot teams' concern about capacity dilution is addressed directly, because unaddressed it becomes resistance.

## 5.6 Negotiation and influence

Two negotiations were material to the proposal, and both used principled negotiation, separating stated positions from underlying interests (Fisher et al., 2012).

Upwards, capital approval meant reconciling the proposal with the board's stated position that [BOARD_POSITION]. What they were protecting was not the capital sum but [BOARD_INTEREST]. Recognising that turned an argument about quantum into one about [REFRAME], and the proposal was restructured to [RESTRUCTURE], meeting the interest without cutting the investment. Cialdini's (2007) commitment principle shaped the sequencing: the board endorsed the framework as a governance instrument before the site recommendation was tabled, so it had accepted the method before seeing the output.

Outwards, supplier negotiation on [MATERIAL] pricing and terms addressed the strategic exposure identified through Kraljic (1983). The supplier's stated position was [SUPPLIER_POSITION]; the underlying interest was [SUPPLIER_INTEREST]. With [BATNA, e.g. a second supplier's quotation] as Procon's best alternative to a negotiated agreement, structuring the deal as [AGREEMENT_STRUCTURE] served both interests and secured [OUTCOME — quantified].

[THIRD_NEGOTIATION — delete this sentence entirely if it duplicates §3.5; otherwise state role, issue, resolution, change.]

## 5.7 Implementation, change and risk

Implementation is stage-gated so that irreversible capital commitment follows resolution of the two dependencies most likely to invalidate the appraisal: planning consent and demand assurance (Table 8; Appendix 15). Because volume and price dominate the sensitivity results, pre-selling at agreed rates precedes any fleet commitment. Gates, not the Gantt chart, govern commitment, because consents lie outside Procon's control (Table A14.2).

Adopting the framework is organisational change, moving site decisions from judgement to evidence. In Lewin's (1951) terms the margin and declined-work evidence unfreezes current practice, the 2027 decision is the change, and the board mandate refreezes the method, though its data are refreshed annually. Lewin is criticised for underplaying planning (Hayes, 2022); the stage gates make planning iterative, and G7 and G8 guard against what Kotter (1995) calls declaring victory too soon.

Table 8. Stage-gated implementation timeline

| Gate | Milestone | Target date | Owner | Exit criterion |
| --- | --- | --- | --- | --- |
| G0 | Board approval of framework and capital release (board paper, Appendix 12) | [APPROVAL_DATE] | Managing Director | Minuted approval (Appendix 13) |
| G1 | Site secured subject to planning; application submitted | [MONTH YEAR] | Managing Director | Heads of terms agreed |
| G2 | Planning consent and O-licence variation granted | [MONTH YEAR] | Managing Director | Consents issued; no capital released before this gate |
| G3 | Pre-sell threshold met | [MONTH YEAR] | Business Development Manager | ≥ [XX]% of break-even volume committed |
| G4 | Fleet and plant ordered (32t-compliant) | [MONTH YEAR] | Business Manager | G2 and G3 passed |
| G5 | Yard works, recruitment and training complete | [MONTH YEAR] | Operations Manager | Pre-opening depot audit passed; capital spend reconciled to Table 7 and variances explained (Shank & Churchill, 1977) |
| G6 | Go-live | [MONTH 2027] | Business Manager | First deliveries made |
| G7 | Six-month KPI review | [MONTH YEAR] | Business Manager | Volume on or above break-even path; operating variances explained |
| G8 | Funding-trigger review for later depots | [MONTH YEAR] | Managing Director | §5.2 trigger met or not met; decision minuted |

## 5.8 Progress to date

The board approved both the framework as standard investment governance and the recommended site on [DATE] (Appendix 13). [EARLY_ACTIONS].

# 6. Conclusion

Option A, South Yorkshire, is recommended because it alone sustains the self-funding chain through the 2028 payload change, with asset finance in reserve if the Section 5.2 trigger is met.

The framework outlives this decision, and three changes would make it compound. A post-completion audit at month twelve should compare each depot's trading with its forecast (Drury, 2021), building the reference class that Flyvbjerg (2008) shows judgement-based appraisal lacks. Enforcing the reason codes the depot logs already define (Appendix 19), and adding postcodes, would turn lost orders into a live map of unmet demand. And the framework should be re-run each [MONTH] against refreshed MPA and CPA data. Next steps are [STEPS].

[REFLEXIVITY_NARRATIVE — ~80 words in your own voice: one belief the evidence changed, or confirmed for unexpected reasons, and what changed in the analysis as a result. One candidate: first treating deferral as a procedural alternative, then valuing it as a real option.]

If I repeated the study, I would commission external review of the financial model from the outset and interview customers in the target catchment. Customers appear in this evidence base only indirectly, through declined-enquiry records; that is its clearest gap, and I recognised it too late to close within twelve weeks.

# References

Barney, J. (1991). Firm resources and sustained competitive advantage. Journal of Management, 17(1), 99–120. https://doi.org/10.1177/014920639101700108

Barney, J. B. (1995). Looking inside for competitive advantage. Academy of Management Executive, 9(4), 49–61. https://doi.org/10.5465/ame.1995.9512032192

Belton, V., & Stewart, T. J. (2002). Multiple criteria decision analysis: An integrated approach. Kluwer Academic Publishers.

Beverley-Jones, L. (2026). Shaping and scoping the problem [PowerPoint slides]. BEMM117DA Strategic Business Proposal, University of Exeter ELE. https://ele.exeter.ac.uk/mod/resource/view.php?id=4424890

Boddy, D. (2002). Managing projects: Building and leading the team. Financial Times Prentice Hall.

Braun, V., & Clarke, V. (2006). Using thematic analysis in psychology. Qualitative Research in Psychology, 3(2), 77–101. https://doi.org/10.1191/1478088706qp063oa

British Standards Institution. (2023). PAS 2080:2023 Carbon management in buildings and infrastructure.

Church, R., & ReVelle, C. (1974). The maximal covering location problem. Papers of the Regional Science Association, 32(1), 101–118. https://doi.org/10.1007/BF01942293

Cialdini, R. B. (2007). Influence: The psychology of persuasion (Rev. ed.). Harper Business.

Clancy, T. (2018). Systems thinking: Three system archetypes every manager should know. IEEE Engineering Management Review, 46(2), 32–41. https://doi.org/10.1109/EMR.2018.2844377

Coghlan, D., & Brannick, T. (2014). Doing action research in your own organization (4th ed.). Sage.

Competition and Markets Authority. (2021, September 20). Making environmental claims on goods and services. GOV.UK. https://www.gov.uk/government/publications/green-claims-code-making-environmental-claims/environmental-claims-on-goods-and-services

Construction Products Association. (2026, July 27). CPA releases summer forecasts 2026. https://www.constructionproducts.org.uk/news-media-events/news/2026/july/cpa-releases-summer-forecasts-2026

Costley, C., Elliott, G., & Gibbs, P. (2010). Doing work based research: Approaches to enquiry for insider-researchers. SAGE Publications.

Department for Transport. (2023, October 19). Volumetric concrete mixers review [Call for evidence]. GOV.UK. https://www.gov.uk/government/calls-for-evidence/volumetric-concrete-mixers-review/volumetric-concrete-mixers-review

Department for Transport. (2025a, June 26). Volumetric concrete mixers: Call for evidence outcome. GOV.UK. https://www.gov.uk/government/calls-for-evidence/volumetric-concrete-mixers-review/outcome/volumetric-concrete-mixers-call-for-evidence-outcome

Department for Transport. (2025b, June 26). Volumetric concrete mixers: Fact sheet March 2025. GOV.UK. https://www.gov.uk/government/calls-for-evidence/volumetric-concrete-mixers-review/outcome/volumetric-concrete-mixers-fact-sheet-march-2025

Dixit, A. K., & Pindyck, R. S. (1994). Investment under uncertainty. Princeton University Press.

Doran, G. T. (1981). There's a S.M.A.R.T. way to write management's goals and objectives. Management Review, 70(11), 35–36.

Drury, C. (2021). Management and cost accounting (11th ed.). Cengage Learning.

Easterby-Smith, M., Jaspersen, L. J., Thorpe, R., & Valizade, D. (2021). Management and business research (7th ed.). SAGE.

Fisher, R., Ury, W., & Patton, B. (2012). Getting to yes: Negotiating an agreement without giving in (3rd ed.). Random House Business.

Flyvbjerg, B. (2008). Curbing optimism bias and strategic misrepresentation in planning: Reference class forecasting in practice. European Planning Studies, 16(1), 3–21. https://doi.org/10.1080/09654310701747936

Flyvbjerg, B. (2021). Top ten behavioral biases in project management: An overview. Project Management Journal, 52(6), 531–546. https://doi.org/10.1177/87569728211049046

Fombrun, C., & Shanley, M. (1990). What's in a name? Reputation building and corporate strategy. Academy of Management Journal, 33(2), 233–258. https://doi.org/10.2307/256324

Harvey, W. S., Tourky, M., Knight, E., & Kitchen, P. (2017). Lens or prism? How organisations sustain multiple and competing reputations. European Journal of Marketing, 51(4), 821–844. https://doi.org/10.1108/EJM-03-2016-0122

Hayes, J. (2022). The theory and practice of change management (6th ed.). Red Globe Press.

Higgins, R. C. (1977). How much growth can a firm afford? Financial Management, 6(3), 7–16.

HM Revenue & Customs. (2025). Carbon border adjustment mechanism [Policy paper]. GOV.UK. https://www.gov.uk/government/publications/introduction-of-carbon-border-adjustment-mechanism/carbon-border-adjustment-mechanism

Hogan, K., & ReVelle, C. (1986). Concepts and applications of backup coverage. Management Science, 32(11), 1434–1444.

Hotelling, H. (1929). Stability in competition. The Economic Journal, 39(153), 41–57. https://doi.org/10.2307/2224214

Keller, K. L. (1993). Conceptualizing, measuring, and managing customer-based brand equity. Journal of Marketing, 57(1), 1–22. https://doi.org/10.1177/002224299305700101

Kotter, J. P. (1995). Leading change: Why transformation efforts fail. Harvard Business Review, 73(2), 59–67.

Kraljic, P. (1983). Purchasing must become supply management. Harvard Business Review, 61(5), 109–117.

Leek, S., & Christodoulides, G. (2012). A framework of brand value in B2B markets: The contributing role of functional and emotional components. Industrial Marketing Management, 41(1), 106–114. https://doi.org/10.1016/j.indmarman.2011.11.009

Lewin, K. (1951). Field theory in social science: Selected theoretical papers (D. Cartwright, Ed.). Harper & Row.

Luchins, A. S. (1942). Mechanization in problem solving: The effect of Einstellung. Psychological Monographs, 54(6), i–95. https://doi.org/10.1037/h0093502

Mendelow, A. L. (1981). Environmental scanning: The impact of the stakeholder concept. In Proceedings of the Second International Conference on Information Systems (pp. 407–417). Association for Information Systems. https://aisel.aisnet.org/icis1981/20

Mineral Products Association. (2025a). Profile of the UK mineral products industry: 2025 edition. https://mineralproducts.org/MPA/media/root/Publications/2025/Profile_of_the_UK_Mineral_Products_Industry_2025.pdf

Mineral Products Association. (2025b, August 4). Concrete market plumbs new depths as business confidence shrivels across mineral products sector [Press release]. https://mineralproducts.org/News/2025/release26.aspx

Mineral Products Association. (2026, February 2). Four years of decline in British construction demand threatens jobs and future capacity, warns MPA [Press release]. https://mineralproducts.org/News/2026/release02.aspx

Minsky, L., & Aron, D. (2021, February 23). Are you doing the SWOT analysis backwards? Harvard Business Review. https://hbr.org/2021/02/are-you-doing-the-swot-analysis-backwards

Mitchell, R. K., Agle, B. R., & Wood, D. J. (1997). Toward a theory of stakeholder identification and salience: Defining the principle of who and what really counts. Academy of Management Review, 22(4), 853–886. https://doi.org/10.5465/amr.1997.9711022105

Myers, S. C., & Majluf, N. S. (1984). Corporate financing and investment decisions when firms have information that investors do not have. Journal of Financial Economics, 13(2), 187–221. https://doi.org/10.1016/0304-405X(84)90023-0

National Highways. (2024). Net zero highways progress report 2023–2024. https://nationalhighways.co.uk/our-contribution/protecting-our-environment/environment/net-zero-highways-progress-report-2023-2024/

Nonaka, I. (2008). The knowledge-creating company. Harvard Business Press.

Office for National Statistics. (2026, [RELEASE DATE]). Construction output in Great Britain: [MONTH] 2026 [Statistical bulletin]. https://www.ons.gov.uk/businessindustryandtrade/constructionindustry/bulletins/constructionoutputingreatbritain/[month]2026

Ohno, T. (1988). Toyota production system: Beyond large-scale production. Productivity Press.

Porter, M. E. (2008). The five competitive forces that shape strategy. Harvard Business Review, 86(1), 78–93.

Saaty, T. L. (2008). Decision making with the analytic hierarchy process. International Journal of Services Sciences, 1(1), 83–98. https://doi.org/10.1504/IJSSCI.2008.017590

Saunders, M. N. K., Lewis, P., & Thornhill, A. (2019). Research methods for business students (8th ed.). Pearson.

Saunders, M. N. K., & Townsend, K. (2016). Reporting and justifying the number of interview participants in organization and workplace research. British Journal of Management, 27(4), 836–852. https://doi.org/10.1111/1467-8551.12182

Senge, P. M. (2006). The fifth discipline: The art and practice of the learning organization (Rev. ed.). Random House Business.

Shank, J. K., & Churchill, N. C. (1977). Variance analysis: A management-oriented approach. The Accounting Review, 52(4), 950–957.

UK Concrete & Mineral Products Association. (2025). UK concrete and cement industry roadmap to beyond net zero: Progress report 2025. https://www.thisisukconcrete.co.uk/TIC/media/root/Resources/2025-09-15-CC-Roadmap-to-Beyond-Net-Zero-final.pdf

Weber, A. (1929). Theory of the location of industries (C. J. Friedrich, Trans.). University of Chicago Press. (Original work published 1909)

Whittington, R., Regnér, P., Angwin, D., Johnson, G., & Scholes, K. (2023). Exploring strategy (13th ed.). Pearson.

Yin, R. K. (2018). Case study research and applications: Design and methods (6th ed.). Sage.

Generative AI use: AI tools were used only for the purposes permitted by the assessment brief. Every prompt, with a hyperlink to its output, is listed in Appendix 18.

# Appendices

Schedule of appendices

| # | Appendix | Produced | Cited in |
| --- | --- | --- | --- |
| 1 | Stakeholder map (power-interest matrix, after Whittington et al., 2023) and communication plan | Week 1 | 5.5 |
| 2 | Criteria matrix and weightings (pre- and post-interview) | Week 2 | 4.1, 4.4 |
| 3 | Demand baseline — catchment analysis | Week 3 | 4.3 |
| 4 | Competitor coverage map, PESTEL and SWOT | Week 4 | 3.1, 4.3 |
| 5 | Depot cost model extract | Week 5 | 4.4 |
| 6 | Interview guide | Week 6 | 4.1 |
| 7 | Anonymised interview transcript | Week 6 | 4.1 |
| 8 | Break-even model | Week 7 | 4.3, 4.4 |
| 9 | Scenario and sensitivity pack | Week 8 | 4.4, 5.2 |
| 10 | Site long-list and feasibility notes | Week 9 | 4.3 |
| 11 | MCDA ranked shortlist | Week 10 | 4.4 |
| 12 | Board presentation (13 slides) and depot business-case model, as presented | Week 11 | 4.3, 4.4, 5.7 |
| 13 | Board approval evidence (minutes) | Week 12 | 5.8 — required for S2 |
| 14 | Project and implementation Gantt charts; RACI matrix; planning tools evaluated | Ongoing | 5.7 |
| 15 | RAID log: risks, opportunities, assumptions, issues and dependencies | From week 1 | 5.7 |
| 16 | KSB mapping document | Week 12 | Mandatory; section-by-section KSB evidence |
| 17 | Employer authenticity statement | Week 12 | Mandatory |
| 18 | AI-use log | From day one | Mandatory |
| 19 | Declined-work analysis, Leeds and Warrington (Apr–Jul 2026) | Week [X] | 3.1, 3.4, 4.3, 5.2, 5.3, 6 |

## Appendix 1. Stakeholder map and communication plan

[INSERT: power-interest matrix of the stakeholder set (after Whittington et al., 2023)]

Table A1.1. Communication plan, with salience (Mitchell et al., 1997) and influencing tactics (Boddy, 2002)

| Stakeholder | Power / interest; salience | Strategy and tactics | Key message | Channel | Frequency | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| MD and board | High / High; definitive | Manage closely: rational persuasion, consultation | [MESSAGE] | Sponsor review; board paper | Fortnightly | Business Manager |
| Operations Manager | Medium / High; dominant, definitive at G5 | Engage participatively: consultation | [MESSAGE] | Working session | Weekly | Business Manager |
| Business Development Manager | Medium / High; dominant, definitive at G3 | Engage participatively: consultation | [MESSAGE] | Working session | Weekly | Business Manager |
| Scheduler | Low / High; discretionary, dependent at G6 | Keep informed: rational persuasion | [MESSAGE] | Briefing | Fortnightly | Operations Manager |
| Material suppliers | Medium / Medium; dominant, definitive at G6 | Keep satisfied: exchange | [MESSAGE] | Commercial meeting | Monthly | Business Manager |
| Depot teams | Low / High; discretionary, dependent at G6 | Keep informed; address capacity concern: consultation | [MESSAGE] | Toolbox talk | Monthly | Operations Manager |
| Target catchment customers | Medium / Low; dominant, definitive at G3 | Monitor; pre-sell: rational persuasion | [MESSAGE] | Direct sales contact | [FREQ] | Business Development Manager |
| Planning authority | High / Low; dominant, definitive at G2 | Keep satisfied: legitimating | [MESSAGE] | Formal submission | As required | Managing Director |

## Appendix 4. Competitor coverage map, PESTEL and SWOT

[INSERT: competitor coverage map, showing competing plants inside the eight-mile radius of each candidate catchment]

Table A4.1. PESTEL factors and whether they discriminate between catchments (after Whittington et al., 2023)

| Domain | Factor | Evidence | Discriminates between catchments? |
| --- | --- | --- | --- |
| Political | UK carbon border adjustment mechanism taxes imported cement, 32% of the UK market, from January 2027 | HMRC (2025); MPA (2025a) | Little: input costs rise at every candidate site |
| Economic | Private housing output forecast to fall 10.0% in 2026 while infrastructure grows 3.2% in 2026 and 2027; ready-mixed volumes at their lowest since 1963 | CPA (2026); MPA (2025b) | Yes: catchments differ in their mix of housing and infrastructure demand |
| Social | Business buyers value reliability and the trust it creates | Leek & Christodoulides (2012); Appendix 19 | Little: the expectation is the same everywhere; capacity to meet it is scored separately (Table 4) |
| Technological | On-site volumetric batching reduces waste; lower-clinker cements and GGBS reduce embodied carbon | DfT (2023); UK Concrete & MPA (2025) | Little in itself: batching travels with the fleet; only access to GGBS and low-clinker supply varies, and Table 4 scores it |
| Environmental | Infrastructure clients pass carbon requirements down the supply chain: PAS 2080 for National Highways' Tier 1 suppliers; Environmental Product Declarations requested from material suppliers | National Highways (2024); BSI (2023); MPA (2025a) | Yes, through the economic domain: it bites hardest where infrastructure demand is concentrated |
| Legal | Volumetric mixers revert to 32 tonnes from 2028, with no further extensions; environmental claims must be substantiated | DfT (2025b); CMA (2021) | Yes: a shorter viable haul radius makes catchment geometry decisive |

Table A4.1 tests each PESTEL domain against the question that matters for site selection: does it discriminate between catchments? PESTEL lists its domains one at a time, so it cannot show how they interact, as the economic and environmental domains do through infrastructure demand, or how reliable the data behind each one is. The SWOT below therefore starts from the external factors, as Minsky and Aron (2021) recommend, so that each internal factor is judged against the conditions it must meet. It ends in recommendations, not a grid: each row of Table A4.3 pairs an external condition with an internal capability and names the part of the proposal that acts on it. Every factor is drawn from evidence presented in the proposal.

Table A4.2. SWOT factors, external first (Minsky & Aron, 2021)

| Ref | Factor | Evidence |
| --- | --- | --- |
| O1 | Infrastructure output forecast to grow 3.2% in 2026 and 2027 while private housing falls 10.0% in 2026 | CPA (2026) |
| O2 | Infrastructure clients pass carbon requirements down the supply chain: PAS 2080 verification for National Highways' Tier 1 suppliers; Environmental Product Declarations requested from material suppliers | National Highways (2024); BSI (2023); MPA (2025a) |
| O3 | Capacity is leaving a contracting sector | MPA (2026) |
| T1 | Volumetric weight derogation ends in 2028: 32-tonne limit, no further extensions | DfT (2025b) |
| T2 | Ready-mixed volumes at their lowest since 1963 | MPA (2025b) |
| T3 | Intense price rivalry: 740 MPA-member plants; 200 m³ lost to Chorley Concrete | MPA (2025a); Appendix 19 |
| T4 | Imported cement, 32% of the UK market, taxed under UK CBAM from January 2027 | MPA (2025a); HMRC (2025) |
| S1 | Volumetric batching mixes on site when needed, reducing waste | DfT (2023); returned-load records [to quantify] |
| S2 | Delivery reputation built on reliability | §3.4 |
| S3 | Self-funded growth: no gearing, owner control | §5.2 |
| S4 | Trading history of three depots, including a recent opening usable as a reference case | §4.2 |
| W1 | No repeatable site-selection method or profitability threshold | §2; §3.2 |
| W2 | Capacity constraints: 22 of 27 declines, April–July 2026, for want of drivers, vehicles or slots | Appendix 19 |
| W3 | Fleet reliability: 12 Warrington enquiries lost to vehicles off the road | Appendix 19 |
| W4 | Gross margin per m³ varies [MARGIN_MULTIPLE]-fold across depots | Management accounts |
| W5 | Decline reasons recorded as free text, so the dashboards attribute nothing | Appendix 19 |

Table A4.3. Recommendations generated from the SWOT (sentence structure after Minsky & Aron, 2021)

| Given the condition of… | our ability (or inability) to… | leads to our recommendation that we… | Where |
| --- | --- | --- | --- |
| infrastructure growth while housing falls, and clients' carbon requirements (O1, O2) | mix on site with less waste (S1) | weight infrastructure exposure and low-carbon capability in site selection, and quantify the waste advantage before marketing it | Table 4; §3.1 |
| the 2028 payload reversion (T1) | serve demand when vehicles or drivers are short (W2, W3) | weight payload resilience and capacity headroom, and buy a 32-tonne-compliant fleet with maintenance cover | Table 4; §5.3 |
| price set by rivals (T3) | deliver reliably (S2) | compete on reliability, protected by the capacity weighting and a capacity-decline KPI | §3.4; Table 1 |
| a contracting sector (T2) | choose sites by a repeatable method (W1, W4) | adopt the weighted framework, with a minimum margin, before any capital release | §5.1; Table 1 |
| CBAM on imported cement (T4) | absorb cost shocks inside a self-funding chain (S3) | hedge cement through a fixed-term supply agreement | §5.3 |
| capacity leaving the sector (O3) | fund more than one depot a year (S3) | set a trigger for asset-financed acceleration | §5.2 |
| demand moving between places (O1) | learn from lost orders (W5) | enforce reason codes and record postcodes | §6 |

Table A4.4. Competitors in the South Yorkshire catchment, as listed in the board presentation

| Competitor | Type | Location and notes, as listed |
| --- | --- | --- |
| Volmix | Volumetric, drum and minimix | Ripley and Belper; 22 trucks; largest independent |
| Bear Concrete | Volumetric | Depots at Chesterfield, Aston and Hucknall |
| Procrete Yorkshire | Volumetric | 24/7 on-site mixing; closest to Procon's model |
| 24/7 Concrete & Aggregates | Volumetric | Sheffield, Barnsley, Rotherham and Doncaster |
| Erewash Concrete | Volumetric | Pinxton; 0.5–8 m³, same or next day |
| Breedon | Fixed plant | Hope cement works |
| Heidelberg Materials (Hanson) | Fixed plant | Wigwam Lane |
| Rightmix | Fixed plant | South Sheffield |
| Tarmac; Aggregate Industries | Fixed plant | Mansfield and Chesterfield |
| Retford Ready Mix | Minimix | 1–4 m³ loads |
| Concrete2You; Ashfield Mini Mix | Online, small loads | — |

Note. Board presentation, slide 9 (Appendix 12). Capacity is recorded for one rival only, so demand per unit of competing capacity (Table 4) cannot yet be scored from this list. One rival trades as 24/7 Concrete & Aggregates across the catchment, a name close enough to Procon 24/7 to confuse buyers there (§3.4).

## Appendix 5. Depot cost model extract

The depot model presented to the board is an Excel workbook ('Procon 247 New Depot Case Study') with an assumptions sheet, a capital schedule, a five-year profit and loss account and a cash flow. Table A5.1 gives its inputs with the basis the workbook records for each; the workbook's own banner warns that inputs are placeholders until replaced with site data, so estimates are marked as such. Table A5.2 is the base case.

Table A5.1. Inputs to the board model and their recorded basis

| Input | Value | Basis recorded in the workbook |
| --- | --- | --- |
| Working days | 269.5 a year | 49 weeks of 5.5 days (half of Saturdays) |
| Daily volume | 37.5 m³ in 2027, then 62.5, 70, 74 and 77 | Leeds trading in 2022 |
| Average selling price | £119/m³, rising 2.5% a year | Procon's current average rate for the area |
| Materials | £61.26/m³: cement £25.25, sand £12.58, stone £23.43 | Non-certified supplier costs (slide 7) |
| Admixtures and water; fuel | £3.50 and £2.50 per m³ | Estimate |
| Rent; business rates | £60,000; £30,000 a year | Rent to suit the listed yards (Appendix 10); rates estimated |
| Labour | £37,440 a year | £16 an hour, 45 hours, 52 weeks: one post |
| Office and management labour | £72,000 a year | Trainee scheduler and sales; may be carried at Warrington |
| Other fixed costs | £44,900 a year | Repairs £5,000; utilities £20,000; insurance £10,000; testing £5,000; IT £2,400; other £2,500 (estimates) |
| Fleet | Two mixers; finance £62,800 a year each | £5,233 a month per vehicle |
| Capital | £278,520 | Capital schedule £253,200 plus 10% contingency; mostly second-hand estimates |
| Inflation | Price and variable cost 2.5%; fixed cost 3% a year | Estimate |
| Working capital | 45 debtor days; 30 creditor days; 7 days' stock | Estimate |
| Tax; depreciation; maintenance capital | 25%; ten years; 1% of revenue | Model convention |
| Discount rate | 0% | Not set (Table A9.4) |

Table A5.2. Base case: five-year profit and cash flow (£)

| Line | 2027 | 2028 | 2029 | 2030 | 2031 |
| --- | --- | --- | --- | --- | --- |
| Volume (m³ a day) | 37.5 | 62.5 | 70 | 74 | 77 |
| Price (£/m³) | 119.00 | 121.97 | 125.02 | 128.15 | 131.35 |
| Revenue | 1,202,644 | 2,054,516 | 2,358,585 | 2,555,695 | 2,725,787 |
| Variable costs | 679,746 | 1,161,233 | 1,333,096 | 1,444,505 | 1,540,642 |
| Fixed operating costs | 244,340 | 251,670 | 259,220 | 266,997 | 275,007 |
| Fleet finance | 125,600 | 129,368 | 133,249 | 137,246 | 141,364 |
| EBITDA | 152,957 | 512,245 | 633,020 | 706,947 | 768,774 |
| EBITDA margin | 12.7% | 24.9% | 26.8% | 27.7% | 28.2% |
| Tax | 31,276 | 121,098 | 151,292 | 169,774 | 185,231 |
| Increase in working capital | 105,438 | 74,685 | 26,658 | 17,281 | 14,912 |
| Maintenance capital | 12,026 | 20,545 | 23,586 | 25,557 | 27,258 |
| Free cash flow | 4,217 | 295,916 | 431,484 | 494,335 | 541,373 |
| Cumulative cash (after £278,520 capital) | -274,303 | 21,613 | 453,097 | 947,432 | 1,488,806 |

Note. Reproduces the workbook to the pound; the rebuild used for Appendices 8 and 9 was reconciled to it before use.

## Appendix 8. Break-even model

Table A8.1. Break-even by case

| Case | Fixed costs (£) | Contribution (£/m³) | Break-even (m³/day) | Break-even (m³/month) | Planned (m³/day) | Margin of safety |
| --- | --- | --- | --- | --- | --- | --- |
| 2027, two wagons (board model) | 369,940 | 51.74 | 26.5 | 596 | 37.5 | 29% |
| 2028, two wagons (board model) | 381,038 | 53.03 | 26.7 | 599 | 62.5 | 57% |
| 2028, third wagon and one more driver (slide 11) | 484,285 | 53.03 | 33.9 | 761 | 62.5 | 46% |
| 2027, full downside | 369,940 | 44.81 | 30.6 | 688 | 28.125 | -9% |

Note. Break-even follows the workbook's definition: fixed operating and fleet costs divided by contribution per cubic metre, before tax and working capital. Month figures use 269.5 working days. None of the cases includes the 2028 payload effect.

## Appendix 9. Scenario and sensitivity pack

The workbook was rebuilt line by line outside Excel and reconciled to it: first-year revenue (£1,202,644), EBITDA (£152,957) and five-year cumulative cash (£1,488,806) match. The rebuild was then used to correct the faults in Table A9.4 and to run the tests below. Payback is interpolated within the year in which cumulative cash turns positive.

Table A9.1. Scenarios, with the board's multipliers applied to every year

| Measure | Downside | Base | Upside |
| --- | --- | --- | --- |
| Multipliers: volume, price, variable cost, capital | 0.75, 0.97, 1.05, 1.10 | 1.00 throughout | 1.20, 1.02, 0.98, 0.95 |
| Capital (£) | 306,372 | 278,520 | 264,594 |
| Year-1 EBITDA (£) | -30,317 | 152,957 | 302,714 |
| Year-1 free cash flow (£) | -113,202 | 4,217 | 87,818 |
| Cumulative cash at month 12 (£) | -419,574 | -274,303 | -176,776 |
| Payback (months) | 44.5 | 23.1 | 16.6 |
| Five-year cumulative cash (£) | 304,342 | 1,488,806 | 2,436,108 |
| Board decision rule | NO-GO | GO | GO |

Note. The decision rule is the workbook's: GO if year-1 EBITDA and five-year cash are positive and payback is four years or less; NO-GO if year-1 EBITDA is negative. The workbook's dashboard applies the price, cost and capital multipliers but not the volume multiplier, because volumes are typed into the profit and loss sheet, so its Downside shows GO with year-1 EBITDA of £82,891.

Table A9.2. One-at-a-time sensitivities (base payback 23.1 months; base-business share £274,303)

| Variable | Change | Payback (months) | Change (months) | Base-business share of a same-cost 2028 depot (£) |
| --- | --- | --- | --- | --- |
| First-year volume | −25% | 26.1 | +3.0 | 344,385 |
| Volume, all years | −10% | 26.1 | +3.0 | 301,774 |
| Volume, all years | +10% | 20.4 | -2.7 | 246,832 |
| Volume on the workbook's stated ramp percentages | 57.2–72.5 m³/day from 2028 | 24.6 | +1.4 | 274,303 |
| Price | −10% | 32.9 | +9.8 | 348,472 |
| Price | +10% | 17.5 | -5.6 | 200,135 |
| Price at the local market average (slide 8) | £130.75/m³ | 17.5 | -5.6 | 201,094 |
| Materials | +10% | 27.4 | +4.3 | 316,835 |
| Materials | −10% | 19.5 | -3.7 | 231,771 |
| Materials at the five-mix average (slide 7) | £66.55/m³ | 26.8 | +3.6 | 311,017 |
| Materials at the certified (BSI) average (slide 7) | £75.68/m³ | 38.0 | +14.9 | 379,576 |
| Fixed costs | +10% | 25.0 | +1.9 | 302,049 |
| Rent | £50,000 a year | 22.5 | -0.6 | 266,803 |
| Rent | £70,000 a year | 23.7 | +0.6 | 281,803 |
| Freehold yard (Attercliffe) instead of a lease | £1.0m capital; no rent | 43.0 | +19.9 | — |
| Capital | +10% | 24.1 | +1.0 | 301,459 |
| Third wagon and one more driver from 2028 (slide 11) | +£100,240 a year | 25.9 | +2.8 | 274,303 |
| Second driver from opening | +£37,440 a year | 25.1 | +1.9 | 302,383 |

Note. The base-business share is the 2028 depot's capital, assumed equal to this depot's, less the free cash flow this depot generates in its first twelve months. Price and materials are the largest effects; rent and capital the smallest.

Table A9.3. Payback and net present value at alternative discount rates

| Discount rate | Net present value over five years (£) | Discounted payback (months) |
| --- | --- | --- |
| 0% (as presented) | 1,488,806 | 23.1 |
| 8% | 1,053,412 | 24.7 |
| 10% | 967,841 | 25.1 |
| 12% | 889,618 | 25.5 |

Note. Cash flows discounted at each year end. The rate the board should apply is [DISCOUNT_RATE_BASIS] (§4.4).

Table A9.4. Review of the board model: findings and treatment

| # | Finding | Effect | Treatment in this proposal |
| --- | --- | --- | --- |
| 1 | Payback counted in whole years: the dashboard shows 2 | Interpolated payback is 23.1 months; the self-funding test needs months | Months used throughout (§4.4, §5.2) |
| 2 | Discount rate set at 0%, so the 'NPV' line equals undiscounted five-year cash (£1,488,806) | Value overstated | NPV at 8–12% reported (Table A9.3) |
| 3 | Volume multiplier not linked to the profit and loss sheet | The dashboard's Downside shows GO | Scenarios rerun (Table A9.1): the full downside is NO-GO under the board's own rule |
| 4 | Scenarios sheet applies ramp-up twice (the author's own note) | Sheet unusable | Not used |
| 5 | Typed volumes (62.5–77 m³/day) run ahead of the stated ramp percentages (57.2–72.5) | On the stated ramp, payback is 24.6 months | Assumption A3 tested at G7 (Appendix 15) |
| 6 | Fleet appears twice: £150,000 capital for two volumetrics and £125,600 a year finance for two wagons | If the finance is for these vehicles, capital falls to £113,520 and payback to 16.7 months; if the capital line is Leeds vehicles transferred, Leeds loses capacity it already lacks (§3.4) | [CONFIRM which applies]; base left as presented |
| 7 | One driver costed (£37,440) for two wagons | A second driver adds 1.9 months to payback | [CONFIRM how the second wagon is crewed] |
| 8 | Third wagon planned for 2028 (slide 11) is not in the model | Adds 2.8 months; 2028 break-even rises to 33.9 m³/day | Shown in Tables A8.1 and A9.2 |
| 9 | Materials priced for a low-cement mix (£61.26/m³, against £70.17 for C28/35 on slide 7) | At the five-mix average payback is 26.8 months; at the certified (BSI) average, 38.0 | [CONFIRM the expected mix and share of certified work] |
| 10 | No adjustment for the 2028 payload reversion | Post-2028 cost understated by £[COST_PER_M3_DELTA]/m³ | To be modelled before G4 |
| 11 | Annual periods only | The month of operating break-even cannot be estimated | Monthly ramp to be modelled for the G7 review |

## Appendix 10. Site long-list and feasibility notes

Table A10.1. Surfaced yards shortlisted in the Sheffield–Doncaster corridor

| Location | Size (acres) | Basis | Annual rate | Listing |
| --- | --- | --- | --- | --- |
| Blyth, S81 | 1.1 | To let | £60,000 | LoopNet 38167046 |
| Sheffield S4 | 1.5 | To let | £70,000 | Rightmove 7545999 |
| Sheffield S9, Stevenson Road | 1.1 | To let | £50,000 | LoopNet 31665199 |
| Sheffield S71 (Barnsley) | 1.0 | To let | £50,000 | Knight Frank HUB2530520 |
| Hurst Lane, Auckley | 1.25 | To let | £50,000 | Flint 301 |
| Mission Springs, Doncaster | 1.25 | To let | £50,000 | Flint 76 |
| Neale Road, Doncaster DN2 | 1.0 | To let | £50,000 (slide 5: to be confirmed) | Rightmove 7605502 |
| Rotherham Road, Rotherham | 1.25 | To let | £50,000 (slide 6: to be confirmed) | Knight Frank HUB2687897 |
| Sheffield S9, Attercliffe | 1.4 | Freehold | £1.0m purchase | Knight Frank, S9 2PF |

Note. Board presentation, slides 4 to 6 (Appendix 12). All are bare surfaced yards that suit silos and cabins without a building. Slide 6 describes rents as per acre; the listings are per site. The presentation uses a 10-mile Sheffield core, the framework an 8-mile radius (§2). Rent across the leased yards moves payback by under a month (Table A9.2); buying Attercliffe would stretch it to 43 months, and a lease keeps the commitment reversible (Dixit & Pindyck, 1994).

## Appendix 12. Board presentation and depot model

[INSERT: the presentation as shown to the board on [DATE], 13 slides. Slides 5 and 6 still carry 'add screenshot' placeholders; complete or remove them first.]

Table A12.1. Content of the board presentation and where this proposal uses it

| Slide | Content | Used in |
| --- | --- | --- |
| 1 | Title: scaling plan, South Yorkshire depot | — |
| 2 | Why Sheffield and South Yorkshire: an unserved market at the edge of the network, shared labour and resources with Leeds, little cannibalisation, regeneration pipeline | §4.3; Table 3 |
| 3 | Target customers, council frameworks, National Highways Area 12 and SDF2 Lot 2 | §4.3; Table 3 |
| 4–6 | Nine surfaced yards in the Sheffield–Doncaster corridor | Appendix 10 |
| 7 | Delivered material cost by mix, non-certified and BSI | Appendices 5 and 9 |
| 8 | Market rates and planned pricing; materials margin by mix | §4.4; Appendix 9 |
| 9 | Local competition | Appendix 4 |
| 10 | Financial case: dashboard of the depot model | §4.4; §5.2; Appendices 5, 8 and 9 |
| 11 | Operating structure; fleet of 11 wagons, two at South Yorkshire and three from year 2 | Appendices 8 and 9 |
| 12–13 | Next locations and the five-depot estate | §5.2 (Figure 1) |

Note. Market rates on slide 8 come from two volumetric and four drum quotations, the drum prices pro-rated to 4 m³, so the 9% discount to the market average (§4.4) rests on six quotes.

## Appendix 14. Implementation Gantt chart and RACI matrix

[INSERT: project and implementation Gantt charts]

Table A14.1. RACI matrix: implementation

| Activity | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| Framework maintenance and annual re-run | Business Manager | Managing Director | Operations Manager | Board |
| Planning submission and consent | Managing Director | Managing Director | Business Manager | Board |
| Land acquisition / lease | Business Manager | Managing Director | Operations Manager | Depot teams |
| Fleet procurement (32t-compliant) | Business Manager | Managing Director | Operations Manager; Scheduler | Board |
| Pre-sell programme | Business Development Manager | Business Manager | Scheduler | Board |
| Recruitment and training | Operations Manager | Business Manager | Depot teams | Board |
| Go-live and KPI monitoring | Business Manager | Managing Director | Operations Manager | Board |

Table A14.2. Planning tools evaluated for this proposal

| Tool | Strength | Limitation | Use in this proposal |
| --- | --- | --- | --- |
| Gantt chart | Shows sequence and overlap at a glance; familiar to the board | Implies certainty about dates Procon does not control; laborious to update | Shows sequence only; commitment is governed by the gates |
| Critical path analysis | Identifies the activities that set the opening date | Depends on duration estimates; activities drift to their latest start | Not used formally: the critical path runs through consents outside Procon's control |
| Stage gates (Table 8) | Capital is released only when exit criteria are met | Can delay opening if criteria are set too high | Adopted; each gate is a stop-or-go decision, a guard against escalation of commitment (Flyvbjerg, 2021) |
| RACI matrix (Table A14.1) | Makes accountability explicit; suits Procon's clear hierarchy | Dates quickly; handles ambiguity and unforeseen events poorly | Adopted; reissued at each gate |
| RAID log (Appendix 15) | Separates risks from assumptions, issues and dependencies; records opportunities as well as threats | Can grow into a list nobody acts on | Adopted; every entry has an owner and a review gate |

Note. Strengths and limitations of the Gantt chart, critical path analysis and RACI matrix follow Beverley-Jones (2026, slides 25, 27 and 45).

## Appendix 15. RAID log

Risks are uncertain events that may help or harm the objectives; issues have already happened: 'If you can smell it, it's a risk, if you're standing in it, it's an issue' (Maylor & Turner, 2022, as cited in Beverley-Jones, 2026, slide 42). Threats carry one of four responses, tolerate, treat, transfer or terminate (Beverley-Jones, 2026, slide 40), opportunities an action to capture them, assumptions a test and dependencies an owner. Every entry is reviewed at the gate shown in Table 8.

Table A15.1. Risks (threats): responses, mitigations and escalation triggers

| Ref | Risk | L / I | Response | Mitigation | Owner | Trigger for escalation |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Volume ramp-up below model | [M/H] | Treat | Pre-sell [XX]% of break-even volume before fleet commitment | Business Development Manager | <[XX]% pre-sold at month [X] |
| R2 | 2028 payload change erodes delivery margin further than modelled | [M/H] | Treat | Procure 32t-compliant fleet from outset; model post-2028 case as base | Business Manager | Cost/m³ exceeds £[XX.XX] |
| R3 | Cement cost inflation (imports 32% of UK market; UK CBAM on imports from January 2027) | [H/M] | Transfer (contract terms) | [TERM] supply agreement; quarterly repricing review | Business Manager | Input cost +[XX]% |
| R4 | Planning consent refused or delayed | [M/H] | Terminate (capital exposure); treat (delay) | Consent as precondition of capital release; second site retained | Managing Director | No decision by [DATE] |
| R5 | Sector contraction exceeds CPA forecast | [M/H] | Tolerate | Infrastructure weighting limits exposure; the residual is accepted, since the downturn is also the opening (OP3); break-even monitored monthly | Business Manager | Regional volumes −[XX]% |
| R6 | Service reliability dilution damages brand | [L/H] | Treat | Capacity headroom weighted in selection (Table 4); capacity-related declines tracked monthly; contractors who also buy from other depots served first in the new catchment (§3.4) | Operations Manager | Capacity-related declines above [X] per month at any depot |
| R7 | Fleet roadworthiness and O-licence maintenance compliance (12 Warrington enquiries lost to vehicles off the road, May–Jun 2026) | [M/H] | Treat | Maintenance capacity and a spare unit specified in the fleet plan; inspection pass rate monitored | Operations Manager | Inspection failure or unit off road > [X] days |
| R8 | Pricing 9% below the local market average fails to win the extra volume it needs, a quarter more than market rates would | [M/H] | Treat | Rate card tested against market quotations at G3 and G7; payback sensitivity to price tracked (Appendix 9) | Business Manager | Volume below plan at G7 or average rate below £[XXX]/m³ |

Table A15.2. Opportunities (positive risks)

| Ref | Opportunity | Action to capture it | Owner | Review |
| --- | --- | --- | --- | --- |
| OP1 | Infrastructure demand in the target catchment exceeds the CPA (2026) forecast | Prioritise infrastructure contractors in the pre-sell; a strong start brings the §5.2 funding trigger forward | Business Development Manager | G3, G7 |
| OP2 | Low-carbon supply wins work from clients applying PAS 2080 | Quantify the waste advantage from returned-load records; make only substantiated claims (CMA, 2021) | Business Manager | G6 |
| OP3 | Competitors withdraw capacity from the catchment (MPA, 2026) | Track closures; rescore catchments at the annual re-run | Business Manager | Annual |

Table A15.3. Assumptions, issues and dependencies

| Ref | Type | Description | Test or action | Owner |
| --- | --- | --- | --- | --- |
| A1 | Assumption | CPA infrastructure and housing forecasts hold across the payback period (CPA, 2026) | Re-tested at the annual framework re-run | Business Manager |
| A2 | Assumption | The 2028 reversion to 32 tonnes proceeds as confirmed (DfT, 2025b) | Confirmed policy; DfT updates monitored | Business Manager |
| A3 | Assumption | Volume rises from 37.5 to 77 m³ a day over five years, based on Leeds's 2022 trading (board model) | Tested at G7; the model's typed volumes run ahead of its own ramp percentages (Table A9.4) | Business Manager |
| A4 | Assumption | Cement and aggregates available at modelled prices for [TERM] | Supply agreement signed before go-live (§5.3) | Business Manager |
| A5 | Assumption | Drivers recruited and trained before go-live | G5 exit criterion | Operations Manager |
| A6 | Assumption | Two volumetrics supplied for the depot, possibly transferred from Leeds (capital schedule: 'use from Leeds depot?') | Decided before G4; a transfer removes capacity Leeds already lacks (I1) | Business Manager |
| I1 | Issue | Capacity-related declines at Leeds and Warrington: 22 of 27, April–July 2026 | Confirm the Leeds cause with the Scheduler (§5.2); track monthly as KPI 5 (Table 1) | Operations Manager |
| I2 | Issue | Decline reasons recorded as free text, so the dashboards attribute nothing | Enforce codes R01–R08 and record postcodes (§6) | Operations Manager |
| I3 | Issue | Warrington vehicles off the road on 26 May, 3 June and 12 June 2026: 12 enquiries lost | Maintenance capacity and a spare unit in the fleet plan (R7) | Operations Manager |
| D1 | Dependency | Board approval and capital release (G0) | Minuted approval (Appendix 13) | Managing Director |
| D2 | Dependency | Planning consent and operator licence variation (G2): local planning authority; Traffic Commissioner | No capital released before G2 | Managing Director |
| D3 | Dependency | Pre-sell threshold met before the fleet order (G3 before G4) | G3 exit criterion | Business Development Manager |
| D4 | Dependency | 32-tonne-compliant vehicles delivered within [X] weeks of order | Lead time confirmed with suppliers before G4 | Business Manager |
| D5 | Dependency | The 2028 depot depends on this depot's cash generation | Payback tracked monthly; §5.2 trigger reviewed at G8 | Managing Director |

## Appendix 16. KSB mapping

The table maps each of the fifteen KSBs assessed in this module to the sections of the proposal that evidence it, in Procon's context.

Table A16.1. KSB mapping by section

| KSB | Section | How the proposal evidences it |
| --- | --- | --- |
| K3 New market strategies, changing customer demands and trend analysis | §2 | Trend analysis of the UK RMC market (MPA, 2025b, 2026) and the housing/infrastructure demand divergence (CPA, 2026) as the basis for catchment selection. |
|  | §3 | PESTEL weighted to the domains that discriminate between catchments; supplier power traced to cement imports and UK CBAM from January 2027; demand measured per unit of competitor capacity rather than absolute volume. PESTEL carried into an external-first SWOT whose recommendations map onto the selection criteria (Minsky & Aron, 2021; Appendix 4). |
| K5 Systems thinking, knowledge and data management, research methodologies, programme management | §3 | Systems thinking: the expansion read as the limits-to-growth archetype (Clancy, 2018; Senge, 2006), with self-funding as the reinforcing loop and service capacity as the balancing one, and the leverage placed on the constraint through the capacity-headroom criterion (§3.4); root cause traced through a 5 Whys chain (§3.3). |
|  | §4 | Research methodology and data management: sequential mixed-methods design defended against rejected alternatives (Table 2); data managed across internal records, sector datasets and interview transcripts; validity through triangulation and recorded weighting provenance (§4.1). Knowledge management: the framework turns directors' tacit judgement into explicit, repeatable knowledge (Nonaka, 2008; §4.4). |
|  | §5 | Programme management: stage-gated implementation with owners and exit criteria (Table 8), with the change managed through Lewin's three stages and planning revisited at each gate (§5.7). Planning tools evaluated for fit before selection (§5.7; Table A14.2). |
| K8 Financial strategies, modelling, and evaluation of financial and non-financial information | §4 | Financial modelling — cost base, break-even, scenario and sensitivity analysis; economic theory applied through location and cost-volume-profit method. Non-financial information evaluated alongside financial: low-carbon supply capability weighted in the MCDA (Table 4) as a commercial variable affecting access to infrastructure demand, not as a compliance cost. Payback adopted as primary metric and critically defended, with discounted payback and an NPV hurdle containing its known weaknesses (§4.4). Accounting rate of return and internal rate of return evaluated and set aside, with reasons (§4.4). The appraisal is a two-stage cost benefit analysis: MCDA ranks the options on priced and unpriced criteria, and the financial appraisal tests the ranking against cash (§4.4). The depot model presented to the board was rebuilt, reconciled to the workbook and reviewed; its faults are corrected and their effect on payback shown (Table A9.4). |
|  | §5 | Funding strategy critically evaluated across four routes using pecking-order theory, Higgins's sustainable-growth limit and real options; the self-funding chain tested against payback; opportunity cost quantified (§5.2, Table 6). |
| K9 Financial governance, legal requirements and procurement strategies | §5 | Financial governance (board approval threshold), legal requirements (O-licence variation and maintenance obligations, planning consent) and procurement strategy (32-tonne-compliant fleet; cement hedging including CBAM pass-through; lower-clinker and GGBS specification for EPD-requiring clients) — §5.3. |
| K12 Influencing and negotiating strategies, upwards and outwards | §5 | Influencing and negotiating upwards: board capital approval negotiated on underlying interests rather than stated positions, with the framework endorsed before the site recommendation was tabled (§5.6). |
| K14 Working with board and other company leadership structures | §5 | Works with the board as sponsor and approver through fortnightly reviews and a formal board paper (Table A1.1; Table 8, G0). The move from judgement to evidence in board decisions is managed as organisational change, refrozen by the board mandate, with later gates guarding against declaring victory too soon (§5.7). |
| K15 Brand and reputation management | §3 | §3.4 critically evaluates delivery reputation: questions the transfer of consumer-brand theory to B2B buyers (Leek & Christodoulides, 2012), evidences the risk from Procon's declined-work records, shows the 2028 payload change tightening the same constraint, and builds brand protection into site selection through backup-coverage logic (Hogan & ReVelle, 1986). Reputation treated as plural (Harvey et al., 2017), with the transfer of that finding tested against the share of volume from customers who buy from more than one depot (§3.4; RAID R6). |
|  | §5 | Brand protection carried into implementation via capacity-headroom risk control (RAID R6, Appendix 15) and the pre-sell sequencing decision. |
| K16 Markets, stakeholders' requirements and the sustainability agenda | §2 | Positions Procon within its market, the regulatory regime governing it (DfT, 2025b) and the stakeholder set the expansion depends on. |
|  | §3 | Five Forces locates Procon in its market and supply chain. Sustainability agenda treated as a client requirement (National Highways' PAS 2080 supply-chain mandate) and as a brand risk (green claims must be substantiated; CMA, 2021) (§3.1). |
| S2 Set strategic direction and gain support for it from key stakeholders | §2 | Sets the strategic direction — aim, five objectives and SMART KPIs (Table 1) — that board approval is subsequently sought for. |
|  | §5 | Secures board support for the strategic direction — approval evidenced at Appendix 13. |
| S3 Undertake research; critically analyse and integrate complex information | §2 | Integrates internal margin data, sector statistics and regulatory evidence into a single problem statement. |
|  | §3 | Critical analysis of complex secondary evidence; causes, drivers and symptoms separated as distinct analytical layers. The capability gap's persistence explained through the Einstellung effect (Luchins, 1942; §3.2). |
|  | §4 | Primary and secondary research critically analysed and synthesised through MCDA into a ranked, auditable shortlist. |
| S11 Use financial data to allocate resources | §4 | Financial data used to compare capital allocation across four options under identical treatment (Table 5). Fleet, price and material inputs of the board model tested for their effect on payback and on the 2028 funding gap (Appendix 9). |
|  | §5 | Allocates resources across the capital and working-capital budget (Table 7). Capital spend reconciled to budget and variances explained at gates G5 and G7 (Table 8). |
| S13 Use presence and storytelling to translate vision into operational strategies | §1 | Answer-first structure: recommendation, cost and board approval in the first three sentences, then why it matters and how it was reached: a costed ask the board can act on. |
|  | §5 | Translates the recommendation into an operational implementation plan with owners, sequencing and KPIs. Manages the organisational change the framework requires (§5.7). |
|  | §6 | Translates the decision into lasting organisational capability: post-completion audit building a reference class, coded declined-work data as a live demand map, and an annual re-run of the framework. |
| S19 Manage relationships across multiple and diverse stakeholders | §5 | Manages relationships across a diverse stakeholder set — board, operations, commercial, scheduling, suppliers, customers, planning authority (power-interest mapping and communication plan, Appendix 1). Salience (Mitchell et al., 1997) shows whose claims become urgent at each implementation gate (§5.5; Table A1.1). |
| S20 Lead and influence upwards and outwards; negotiate; use advocacy | §5 | Influencing and negotiating outwards: supplier terms negotiated on interests with a defined BATNA; advocacy sustaining Procon's reputation through the expansion. Influencing tactics matched to each stakeholder (Boddy, 2002; Table A1.1). |
| B3 Curious and innovative: explore ambiguity and complexity; find creative solutions | §3 | Ambiguity of comparing dissimilar catchments resolved through location theory (Weber; Hotelling; Church & ReVelle), extended to service reliability through backup coverage (§3.4). |
|  | §4 | Creative resolution of a genuinely ambiguous comparison — non-commensurable criteria reconciled via weighted MCDA with stated provenance — followed by critical examination of the instrument's own limits (§4.4). |
|  | §6 | Reflexive account of ambiguity encountered and how the analysis was revised in response. |

## Appendix 19. Declined-work analysis, Leeds and Warrington (April to July 2026)

Leeds and Warrington record declined enquiries on the same log template, issued in April 2026, which defines eight reason codes, R01 to R08; staff recorded free-text reasons instead, so the logs' summary dashboards attribute nothing. The author coded each of the 27 entries against the log's own scheme (Table A19.2). Entries saying only that nothing was free before about 4pm cannot be split between a missing vehicle (R02) and a missing driver (R03), so they are coded R02/R03, capacity with the cause not recorded. Leeds entries run from 5 May to 29 July 2026 and Warrington entries from 25 April to 19 June 2026; the Warrington log has no later entries.

Three Leeds entries are dated 2025 and one has no year; all four sit among May and June 2026 entries in a template first issued in April 2026, so they are treated as 2026. One Warrington volume is logged as '50m+' and is counted as 50 cubic metres, so price-related volume is a minimum. Revenue is recorded for only three entries, so lost revenue is not analysed. Customer names are withheld and sites are given by area; reasons are reproduced as logged, with one staff name removed. Three readings are the author's: W03 records rates of £145 and £119 by load size without saying whose they are; W11 is read as a loss to a competitor ('MCR') quoting £111 a cubic metre against Procon's £117; and W02 as an unresolved scheduling query.

By count, capacity accounts for 22 of the 27 declines. Those 22 involve 16 customers: three were refused more than once, one of them five times. None of the 21 customers in the two logs appears at both depots. By volume it accounts for 75 of at least 384 cubic metres, while two jobs lost on price account for at least 250 (Table A19.1; Figure A19.1). All twelve Warrington vehicle declines fall on three days: 26 May, 3 June (a failed six-weekly inspection) and 12 June (a breakdown). At Leeds, six of the nine capacity declines record only a morning shortage with no cause, and a seventh (L10) an afternoon one.

Table A19.1. Declined enquiries by coded reason

| Code | Category | Leeds | Warrington | Total | m³ |
| --- | --- | --- | --- | --- | --- |
| R02 | Capacity: vehicle unavailable | 0 | 12 | 12 | 37 |
| R03 | Capacity: driver unavailable | 2 | 1 | 3 | 13.5 |
| R02/R03 | Capacity: cause not recorded | 7 | 0 | 7 | 24.5 |
|  | Subtotal: capacity | 9 | 13 | 22 | 75 |
| R06 | Price not agreed (lost to competitor) | 0 | 2 | 2 | ≥250 |
| R01 | Beyond range / distance | 0 | 1 | 1 | 18 |
| R08 | Other (unclear) | 0 | 1 | 1 | 6 |
| — | No reason recorded | 1 | 0 | 1 | 35 |
|  | Total | 10 | 17 | 27 | ≥384 |

Figure A19.1. Declined enquiries by number and by volume, Leeds and Warrington, April to July 2026

Note. Data from the Leeds and Warrington declined-work logs, April to July 2026, coded by the author (Table A19.2). Price-related volume is a minimum, because one job was logged as '50m+'.

Table A19.2. Coded register of declined enquiries (L = Leeds, W = Warrington)

| ID | Date (as logged) | Area | m³ | Reason as logged | Code |
| --- | --- | --- | --- | --- | --- |
| L01 | 05/05/2026 | Cookridge | 3 | Offered 3.30pm no availbility before didnt book moved on | R02/R03 |
| L02 | 23/5/26 | Rotherham, out of hours | 2.5 | No driver availbility | R03 |
| L03 | 29/5/ (no year; treated as 2026) | Wakefield | 2.5 | No Availability until 4pm | R02/R03 |
| L04 | 3.6.25 (treated as 2026) | Wetherby | 3 | wanted am slot nothing available offerd pm did not book | R02/R03 |
| L05 | 4.6.25 (treated as 2026) | Leeds (Otley Road) | 2 | No Availability until 4pm | R02/R03 |
| L06 | 4.6.25 (treated as 2026) | Dewsbury | 2 | No Availability until 4pm | R02/R03 |
| L07 | 4.6.26 | Site noted as 'Castle' | 9 | No Availability until 4pm | R02/R03 |
| L08 | 18/07/2026 | Huddersfield (HD2), Saturday | 9 | No drivers to work the afternoons Saturday x2 OHH £750 & £450 | R03 |
| L09 | 20/07/2026 | Batley | 35 | (none recorded) | — |
| L10 | 29/07/2026 | Leeds | 3 | cant take afternoon slots | R02/R03 |
| W01 | 25/04/2026 | Carrington, out of hours | 2 | No Driver | R03 |
| W02 | 28/04/2026 | Atherton (M46) | 6 | Ask [staff member] was slots on clear after first job ? | R08 |
| W03 | 22/5/26 | Leigh | 200 | Chorley Concrete won this 1m3 deliveries £145.00 2m3 £119.00 on Gen3 | R06 |
| W04 | 26/5/26 | Golborne | 4 | Truck off the road | R02 |
| W05 | 26/5/26 | Manchester | 4 | Truck off the road | R02 |
| W06 | 26/5/26 | Westhoughton | 2 | Truck off the road | R02 |
| W07 | 26/5/26 | Stockport | 2 | Truck off the road | R02 |
| W08 | 3.6.26 | Stockport (two sites) | 4 | Didnt pass 6 weekly taken off the road | R02 |
| W09 | 3.6.26 | Golborne | 4 | Didnt pass 6 weekly taken off the road | R02 |
| W10 | 3.6.26 | Manchester | 3 | Didnt pass 6 weekly taken off the road | R02 |
| W11 | 8.6.26 | Culcheth | ≥50 | 4.5 miles from depot MCR £111.00 [rate recorded: £117/m³] | R06 |
| W12 | 12.6.26 | Stockport (am) | 2 | No truck broke down no commander unit | R02 |
| W13 | 12.6.26 | Chorley | 3 | No truck broke down no commander unit | R02 |
| W14 | 12.6.26 | Manchester | 2 | No truck broke down no commander unit | R02 |
| W15 | 12.6.26 | Great Sankey | 5 | No truck broke down no commander unit | R02 |
| W16 | 12.6.26 | Stockport (pm) | 2 | No truck broke down no commander unit | R02 |
| W17 | 19/06/2026 | Wirral | 18 | Too far to tarvel on return for a slab | R01 |