A Site-Selection and Investment Framework for Procon 24/7's Self-Funded Five-Year Expansion in the UK Ready-Mixed Concrete Sector, Applied to the 2027 Location Decision

| Item | Detail |
| --- | --- |
| Module | BEMM117DA Strategic Business Proposal — Assessment 2 |
| End-point assessment | CMI Assessment Method 1 — L7 Senior Leader (ST0480 v1.2) |
| Apprentice | [NAME] |
| Organisation | Procon 24/7 Ltd |
| Role | Business Manager (P&L accountability) |
| Submission | 9 November 2026 |
| Word count | [WORD_COUNT] (excluding tables, figures, references and appendices) |
| KSB mapping | Appendix 16 (all fifteen KSBs, by section) |
| Employer verification | Appendix 17 |

Contents

1. Executive Summary	3

2. Introduction and Statement of the Problem	4

3. Discussion of the Proposal and Problem	6

3.1 External drivers	6

3.2 The internal cause	6

3.3 Symptoms and quantified consequences	7

3.4 Brand and reputation: a critical evaluation	7

3.5 Resistance and conflicting views	8

4. Methodology, Results and Options Analysis	9

4.1 Research design and its justification	9

4.2 Positionality, ethics and limitations	10

4.3 Findings	11

4.4 Options analysis	12

5. Recommendations and Implementation Plan	16

5.1 Recommendation	16

5.2 Funding strategy: a critical evaluation	16

5.3 Governance, procurement and legal requirements	18

5.4 Budget and resources	18

5.5 Stakeholder engagement and communication	19

5.6 Negotiation and influence	19

5.7 Implementation, change and risk	20

5.8 Progress to date	21

6. Conclusion	22

References	23

Appendices	28

Appendix 1. Stakeholder map and communication plan	29

Appendix 4. Competitor coverage map, PESTEL and SWOT	31

Appendix 5. Depot cost model extract	34

Appendix 8. Break-even model	36

Appendix 9. Scenario and sensitivity pack	37

Appendix 10. Site long-list and feasibility notes	40

Appendix 12. Board presentation and depot model	41

Appendix 14. Implementation Gantt chart and RACI matrix	42

Appendix 15. RAID log	43

Appendix 16. KSB mapping	46

Appendix 19. Declined-work analysis, Leeds and Warrington (April to July 2026)	49

# 1. Executive Summary

This proposal recommends that Procon 24/7 open its 2027 depot in South Yorkshire (Option A) at a capital cost of £278,520. It breaks even at 596 cubic metres a month, against 842 planned for its first year, and recovers its capital in 23 months. That is too slow to pay for a successor a year later, so existing depots must fund about £274,000 of the 2028 depot. The board approved the recommendation and its framework on [APPROVAL_DATE] (Appendix 13).

The decision matters because Procon's five-year plan opens one self-funded depot a year, yet the business has had no repeatable way of choosing where. Gross margin per cubic metre varies [MARGIN_MULTIPLE]-fold across its three depots. Ready-mixed concrete volumes are the lowest since 1963, and from 2028 volumetric mixers lose the weight derogation on which their payload depends.

I built a weighted site-selection framework from industrial location theory, tested it through [N] semi-structured interviews and applied it to four options, deferral among them. Service capacity is weighted to protect the delivery reliability on which Procon's reputation rests. Six indicators measure success (Table 1), led by framework adoption and a minimum margin of £44 per cubic metre.

# 2. Introduction and Statement of the Problem

Procon 24/7 Ltd is an owner-managed supplier of ready-mixed concrete, operating volumetric and static plant from depots in Pontefract, Leeds and Warrington. In [YEAR] the board adopted a five-year growth strategy of sequential self-funding, under which a new depot opens each year from 2027 and is capitalised by the retained profit of the one before. It depends on something Procon has never had: a repeatable way of deciding where to expand and whether a site will return enough, quickly enough, to fund its successor.

Desk research and Procon's own records point to three reasons why that gap matters now.

The first is that site economics outweigh commercial effort. Gross margin per cubic metre varies [MARGIN_MULTIPLE]-fold between Procon's strongest and weakest depots ([INTERNAL SOURCE: management accounts, FY20XX]). Ready-mixed concrete is usually supplied within eight miles of the point of use (Mineral Products Association [MPA], 2025a), and volumetric batching removes the setting-time limit but not haul time (Appendix 19). Profitability is therefore largely fixed when the site is chosen.

The second is that the sector is contracting sharply, which makes a wrong choice more expensive. Great Britain volumes for the four quarters to Q2 2025 were 11.9 million cubic metres, the lowest since 1963, and fell for a fourth consecutive year in 2025 (MPA, 2025b, 2026). The Construction Products Association (CPA, 2026) forecasts private housing down 10.0% in 2026 while infrastructure grows 3.2% in both 2026 and 2027, so demand is moving between sectors and therefore between places.

The third is a regulatory change that falls inside the funding chain itself. From 2028 volumetric mixers lose the derogation allowing them to run at 38.4 tonnes (four-axle) and 44 tonnes (five-axle) and revert to the standard 32-tonne limit, with no further extensions (Department for Transport [DfT], 2025b). Payload per journey falls by around [PAYLOAD_LOSS_PCT]%, delivered cost rises by an estimated £[COST_PER_M3_DELTA] per cubic metre and the viable haul radius shrinks, all in the year the 2027 depot is meant to fund its successor.

Yet site decisions still rest on directors' judgement, and no profitability threshold has ever been modelled.

The aim is to develop and apply a weighted site-selection and investment framework that lets Procon 24/7 appraise expansion locations on modelled evidence, and to recommend the 2027 location to the board by 5 November 2026. Five objectives support it: establish the demand and competitive baseline for candidate catchments; build a validated cost and break-even model incorporating the 2028 payload reduction; design and weight selection criteria with operational input; appraise the options against a do-nothing baseline; and secure board approval. Site-level design, pricing policy and the choice of 2028–2031 sites are out of scope. Table 1's indicators meet Doran's (1981) SMART criteria, but SMART favours results over decision quality, so KPI 6 audits the forecast itself.

Table 1. Key performance indicators and intended impact

| KPI | Baseline | Target | Measurement | Owner | Review |
| --- | --- | --- | --- | --- | --- |
| Framework adopted as standard investment governance | No process exists | Adopted and mandated for all site decisions by [DATE] | Board minute | Managing Director | [DATE] |
| Minimum gross margin per m³ for approval | Undefined | £44/m³ (Option A's contribution in the full downside), set by [DATE] | Management accounts | Business Manager | Quarterly |
| Months to capital payback, 2027 depot | n/a | 24 months or fewer (board model: 23.1) | Depot P&L | Business Manager | Monthly |
| 2028 depot funded from retained trading profit | Existing depots' free cash £[BASE_FCF] in FY[XX] (management accounts) | No external finance; base-business share £274,303 or less | Cash flow forecast | Managing Director | [DATE] |
| Capacity-related declined enquiries, existing depots (reputation) | 22 of 27 declines, Apr–Jul 2026 | At or below half the April–July 2026 monthly rate by month 12 | Declined-work logs | Operations Manager | Monthly |
| Forecast accuracy of the appraisal (decision quality) | No forecast has been audited | Month-12 volume and contribution within 15% of forecast | Post-completion audit (§6) | Business Manager | Month 12 |

# 3. Discussion of the Proposal and Problem

## 3.1 External drivers

A PESTEL analysis (Whittington et al., 2023) covers six domains, but they do not bear equally on this decision, and Appendix 4 carries them into an external-first SWOT (Minsky & Aron, 2021). Political, social and technological factors hardly distinguish one catchment from another. The legal domain is decisive, because the 2028 weight reversion (DfT, 2025b) is a dated, confirmed change to the unit economics of Procon's delivery model and bridge-loading evidence makes reversal implausible (DfT, 2025a).

The economic domain comes second, because the CPA (2026) forecasts private housing and infrastructure diverging, so housing-led and infrastructure-led catchments will move in opposite directions over the depot's payback period. Here the economic and environmental domains interact. National Highways requires verified PAS 2080 carbon management of its large and medium Tier 1 suppliers (National Highways, 2024), and the standard expects material suppliers to share product carbon data (British Standards Institution [BSI], 2023), so it reaches Procon when contractors ask for Environmental Product Declarations (MPA, 2025a), and low-carbon capability is becoming a condition of entry to the growth segment. Volumetric batching should help, since mixing on site reduces waste (DfT, 2023), but Procon cannot market that until returned-load records quantify it, because environmental claims must be substantiated (Competition and Markets Authority [CMA], 2021), and an unsupported one would damage the reputation it was meant to build.

Porter's (2008) five forces show rivalry that is intense for structural reasons. MPA members alone operate 740 ready-mixed concrete plants (MPA, 2025a), the product is close to a commodity and price is set largely outside the firm. Supplier power is rising too. Cement imports grew from 11% of the UK market in 2004 to 32% in 2023 (MPA, 2025a), and from January 2027 the UK carbon border adjustment mechanism (CBAM) taxes the embodied emissions of imported cement (HM Revenue & Customs [HMRC], 2025), so input costs are likely to rise in the new depot's first year. In Kraljic's (1983) terms cement is a strategic purchase, one to manage through the supply relationship rather than buy transactionally.

In South Yorkshire, then, the binding constraint is price rivalry from established volumetric operators: Table A4.4 lists five, one trading across all four corridor towns, and the board plan already prices 9% below the local market average (Appendix 9).

## 3.2 The internal cause

Barney's (1995) VRIO test explains why Procon is poorly equipped to make the decision. An evidence-based site-selection capability would be valuable, since the [MARGIN_MULTIPLE]-fold margin variation shows selection quality turning directly into returns. It would be rare among owner-managed operators, who decide by judgement, and hard to imitate, because its value comes from combining the method with Procon's own data. Procon fails the fourth condition, organisation, having no process, threshold or repeatable appraisal. Experience can entrench the gap, since familiar methods blind people to better ones, the Einstellung effect (Luchins, 1942).

The framework draws on industrial location theory because the underlying problem is spatial. In Weber's (1909/1929) least-cost model the best site minimises the combined cost of assembling inputs and distributing output, which fits ready-mixed concrete closely, with materials hauled in and concrete hauled out against the clock. Hotelling (1929) shows that competitors cluster rather than disperse, so absolute demand misleads and the measure that matters is demand per unit of competing capacity. Church and ReVelle's (1974) maximal covering location problem formalises the eight-mile radius: cover as much demand as possible within a fixed service distance.

## 3.3 Symptoms and quantified consequences

A 5 Whys analysis (Ohno, 1988) traces the symptom back to its cause. Because funding is sequential, one weak site stalls the plan, stranding £278,520 in plant, fleet and yard and delaying every later opening by at least 12 months. Weak sites get through because no margin threshold exists to stop them, which is also why margins vary [MARGIN_MULTIPLE]-fold. No threshold exists because judgement is unmodelled, and judgement is unmodelled because Procon has no repeatable method. Flyvbjerg (2008) shows that cost underestimation and benefit overestimation are strongest where appraisal relies on judgement and ignores reference data, which is how Procon chooses sites today.

## 3.4 Brand and reputation: a critical evaluation

Fombrun and Shanley (1990) treat reputation as an intangible asset built through repeated signals of reliability. Keller's (1993) brand equity model was developed for consumer markets, and how far it transfers to business buyers is contested. Leek and Christodoulides (2012), who interviewed ten supplier managers, find that business brand value rests on functional qualities such as reliability and capacity, and on the trust and reduced risk that follow from them. A contractor booking a pour is buying confidence that the wagon will arrive, so where price is set externally, reliability becomes the main source of differentiation and pricing power. In resource-based terms (Barney, 1991), Procon's delivery reputation is a strategic asset, costly to imitate because it has to be earned through performance.

Procon's records suggest that asset is already under strain. Between April and July 2026 the Leeds and Warrington depots declined 27 enquiries, and when I coded the logs, 22 proved to be for want of drivers, vehicles or slots (Appendix 19). By volume the picture reverses, because those 22 came to 75 cubic metres, under a third of the 250 or more lost on price. For reputational risk the count is the better measure, since each refusal reaches a buyer. The 22 reached 16 customers, one of them five times. The logs also record what buyers did next, which Leek and Christodoulides's interviews cannot. Two Leeds customers who were offered an afternoon slot did not book, and one 'moved on'. Reputation is also plural. Harvey et al. (2017), studying one consulting firm, find competing reputations across stakeholders and places, each sustained through the stakeholder's own relationship with the firm. If that transfers, a failure in a new catchment, or a success, will travel mainly through customers who buy from more than one depot, and they account for [CROSS_DEPOT_SHARE]% of 2025/26 volume (sales ledger).

Rapid sequential expansion is the strategy most likely to over-extend service capacity and damage the asset its economics rely on, and the same evidence strengthens the case for consolidating first (Option C), which Section 5.2 tests. The pattern is the limits-to-growth archetype (Clancy, 2018; Senge, 2006), in which self-funding drives growth, service capacity constrains it, and the leverage lies in easing the constraint. Location science suggests how, since backup coverage models value a second unit able to serve demand when the first is unavailable (Hogan & ReVelle, 1986). The framework applies that logic by weighting service capacity headroom (Table 4) and tracking capacity-related declines as a KPI (Table 1), so a catchment that demands more than Procon has shown it can deliver ranks down whatever its demand.

## 3.5 Resistance and conflicting views

[RESISTANCE_NARRATIVE — ~80 words in your own voice: role; stated position; the interest beneath it; how it was resolved; what changed in the proposal. Optional lens from Masterclass 1: Lewin's force-field analysis, driving versus restraining forces, and whether you pushed or reduced the obstacle (Hayes, 2022); one clause at most. The reading list's Essential item on disagreement, Julia Dhar's TED talk 'How to disagree productively and find common ground', fits here; reference it only if you cite it.]

# 4. Methodology, Results and Options Analysis

## 4.1 Research design and its justification

The design runs from philosophy to technique, and Table 2 records the alternative I rejected at each stage and why. I took a pragmatist position because the problem needs measurable cost data and tacit practitioner knowledge together, and pragmatism admits both without an artificial commitment to one epistemology (Easterby-Smith et al., 2021; Saunders et al., 2019).

Table 2. Methodological decisions and rejected alternatives

| Decision | Position adopted | Alternatives rejected | Justification |
| --- | --- | --- | --- |
| Philosophy | Pragmatism | Positivism; interpretivism | Decision requires both measurable cost data and tacit operational knowledge. Positivism rejected: the cost assumptions are not directly observable and need practitioner validation. Interpretivism rejected: the board needs quantified break-even and payback figures |
| Approach | Abductive | Deduction; pure induction | Framework derived from location theory, then revised against empirical interview data |
| Strategy | Single case study with embedded units (three depots) | Multiple-case; survey | Depth of proprietary cost access outweighs cross-case generalisability (Yin, 2018) |
| Method | Sequential mixed methods (QUAN → qual → QUAN) | Mono-method quantitative | Secondary data defines the problem; interviews test assumptions; modelling resolves it; interview guide and transcript at Appendices 6 and 7 |
| Sampling | Purposive census of [N] expert roles (Operations Manager, Business Development Manager, Scheduler, key material suppliers) | Random; convenience | Every internal role holding the relevant knowledge was interviewed, with key suppliers chosen purposively: [N] in all. As internal managers and external suppliers the group is heterogeneous, so it falls below both the 15–60 norm for workplace interviews and the 12–30 suggested for heterogeneous groups (Saunders, 2012, as cited in Saunders & Townsend, 2016). The defence is purpose: the interviews test the model's assumptions, not thematic saturation, an exception Saunders and Townsend (2016) allow where study purpose and data saliency justify it |
| Conduct | [N] interviews, [in person / Teams], [XX–XX] minutes; [audio-recorded with consent / notes taken]; [transcribed verbatim / summarised]; [information sent in advance] (Appendix 6) | [e.g. unrecorded conversations] | [Why: e.g. a reader could replicate the study; transcripts support the thematic coding] |
| Analysis | Descriptive statistics; thematic analysis; MCDA | Inferential statistics | Expert sample too small for statistical inference; thematic analysis suits explanatory interview data (Braun & Clarke, 2006; Easterby-Smith et al., 2021) |

The sequence in Table 2 matters, because interviews first would have produced opinion with nothing to anchor it, and without them the cost model would rest on unchecked assumptions. Validity comes from triangulating theory, secondary data and practitioner evidence, and reliability from recording the provenance of every weighting (Table 4; Appendix 2), so that another analyst could reproduce the scores.

## 4.2 Positionality, ethics and limitations

I conducted this research as an insider. As Business Manager with profit and loss accountability I have a stake in the outcome and chair the sponsor reviews that scrutinised it, a position with advantages and hazards alike (Coghlan & Brannick, 2014; Costley et al., 2010). It gave me access to the accounts and to candid colleagues, but it exposed the work to three hazards. I countered confirmation bias towards expansion by specifying the do-nothing and deferral options before analysis and by having [REVIEWER_ROLE] review the model independently. Three of five interviewees are in my reporting line, so to offset that power asymmetry I framed interviews as a search for flawed assumptions, anonymised the material and invited disagreement. Optimism bias in the ramp-up estimate (Flyvbjerg, 2008, 2021) I could counter only in part, by resting first-year volume on Leeds's 2022 trading and re-testing later years at G7 (Table A9.4).

The Managing Director gave organisational consent as sponsor, and the study followed [ETHICS_ROUTE — describe what actually happened; if there was no University ethics review, say what you did and confirm with the programme team]. Participation was voluntary and informed, identifying material was anonymised, and supplier pricing is reported in aggregate.

Three limitations qualify the findings. Competitor costs are proxied from Companies House filings, so conclusions on relative cost position are indicative only. MPA volume data comes from a member survey covering just over 60% of Great Britain sales (MPA, 2025a), which leaves regional figures with sampling uncertainty. A single case also limits generalisation, though the deliverable is an internal capability and claims no general theory.

## 4.3 Findings

Secondary analysis established the demand and competitive baseline. Heart of the City completed in February 2026 (Sheffield City Council, 2026), so South Yorkshire's pipeline is West Bar's second phase (Urbo Regeneration, n.d.) and live council and National Highways frameworks, where two Leeds accounts already have sites (Appendix 12). Census 2021 built-up areas put 719,300 people within eight miles of Sheffield and 402,845 of Hull (author's calculation from ONS, 2023; see Appendix 11), and two volumetric rivals advertise in Hull (Appendix 11). Procon's trading supports that ratio but not its breadth: Leeds delivered 2,422 cubic metres to HU postcodes in 2022–2026, 63% of its S-postcode volume, from 15 customers against 157.

Cost-volume-profit analysis (Drury, 2021) of the board model gives a contribution of £51.74 per cubic metre and break-even at 26.5 cubic metres a day (Appendix 8). The model omits the 2028 payload effect, which adds £[COST_PER_M3_DELTA] per cubic metre.

The primary research tested the criteria and weightings derived from location theory. The initial matrix weighted [CRITERION] at [W_BEFORE]%. Evidence from [SOURCE — interviewee role, or the declined-work logs] on [TOPIC] showed that [INSIGHT — what the evidence actually showed], and the weighting was [REVISED_TO_OR_CONFIRMED — revised to X% / confirmed]. Applying the final weightings [EFFECT_ON_RANKING — reversed the ranking / narrowed the margin to X points / confirmed the original order].

This bears on how much weight the evidence can carry. [KEEP ONE, ~25 words: if the interviews changed a weighting, the primary research was formative, because the recommendation rests on inputs the secondary data would not have surfaced; if they confirmed the weightings, the convergence is itself evidence, because the weights came from location theory before practitioners saw them.]

Table 3. Findings by research strand and effect on the framework

| Strand | Principal finding | Evidence | Effect on framework |
| --- | --- | --- | --- |
| Demand and catchment | West Bar's second phase from 2027; live council and National Highways frameworks, with SDF2 Lot 2 live from 2027; two Leeds accounts and a framework contractor already working in South Yorkshire; Heart of the City completed in February 2026. Option B: 402,845 people within eight miles of Hull against 719,300 for Sheffield; the Humber Freeport's decade-long pipeline; Procon's HU volume came from 15 customers | Sheffield City Council (2026); Urbo Regeneration (n.d.); CPA (2026); Office for National Statistics (2026); board presentation, Appendix 12; Appendix 3; ONS (2023); Procon job records; Appendix 11 | Named pre-sell targets for G3; [EFFECT on the infrastructure exposure score]; Option B volumes scaled to the same market share (Appendix 11) |
| Competition | Five volumetric rivals, one trading across Sheffield, Barnsley, Rotherham and Doncaster, plus fixed-plant, minimix and online operators; capacity is recorded for one rival only. Option B: two volumetric operators advertise in Hull (Ready Crete; Mixamate), with three fixed plants in the city and one at Bridlington | Competitor mapping, Appendix 4; Appendix 11 | Demand measured per unit of competing capacity |
| Service reliability | 22 of 27 declined enquiries (Apr–Jul 2026) were capacity-related; by volume, price losses (≥250 m³) exceeded capacity losses (75 m³) | Declined-work logs, Appendix 19 | Capacity headroom criterion introduced at [XX]% [CHECK: keep 'introduced' only if the criterion was added after this evidence; if it was, this is the §4.3 weighting change] |
| Cost base | Variable cost £67.26/m³ (materials £61.26, a low-cement mix); certified (BSI) mixes average £75.68 in materials alone; post-2028 £[XX.XX] | Board model; supplier package costs, Appendix 12 | Mix and certification tested in sensitivity (Appendix 9); post-2028 cost to be modelled |
| Land and feasibility | Nine surfaced 1.0–1.5-acre yards in the Sheffield–Doncaster corridor at £50,000–£70,000 a year; one freehold at £1.0m; Option B: 1-acre yards in Hull at £30,000–£50,000, with 98% of the city at high flood risk | Land agents; planning portals; Appendix 10; Appendix 11 | Lease preferred: rent moves payback by under a month; freehold would stretch it to 43 months |
| Regulatory | Payload reduction of [XX]% from 2028 | DfT (2025a, 2025b) | Payload resilience criterion weighted at [XX]% |

## 4.4 Options analysis

I appraised four options: South Yorkshire (A), Hull and the Humber (B), deferring the 2027 opening to consolidate the existing depots (C), and doing nothing, which anchors the cost of inaction. The appraisal is a two-stage cost-benefit analysis. Multi-criteria decision analysis first ranks the options on priced and unpriced criteria, because capacity headroom and payload resilience cannot be collapsed into one monetary figure without hiding trade-offs the board needs to see (Belton & Stewart, 2002), and a financial appraisal then tests the ranking against cash. Weights came from pairwise comparison using Saaty's (2008) analytic hierarchy process, with a consistency ratio of [CR] against his 0.10 ceiling (Appendix 2).

Table 4. Weighted multi-criteria decision matrix (pairwise working at Appendix 2; ranked shortlist at Appendix 11)

| Criterion | Weight % | Provenance of weight | A | B | C | Baseline |
| --- | --- | --- | --- | --- | --- | --- |
| Catchment demand density (8-mile radius) | [XX] | Church & ReVelle (1974); [revised post-interview / confirmed by interviews] | [X] | [X] | [X] | [X] |
| Demand per unit of competitor capacity | [XX] | Hotelling (1929); competitor mapping | [X] | [X] | [X] | [X] |
| Post-2028 payload resilience | [XX] | DfT (2025b); Operations Manager interview | [X] | [X] | [X] | [X] |
| Infrastructure pipeline exposure | [XX] | CPA (2026) sectoral divergence | [X] | [X] | [X] | [X] |
| Operating cost base | [XX] | Weber (1909/1929); internal cost model | [X] | [X] | [X] | [X] |
| Land cost and availability | [XX] | Land agent data; planning feasibility | [X] | [X] | [X] | [X] |
| Low-carbon supply capability | [XX] | PAS 2080 client requirements (BSI, 2023; National Highways, 2024); UK Concrete & MPA (2025); proximity to low-clinker cement and ground granulated blast-furnace slag (GGBS) supply | [X] | [X] | [X] | [X] |
| Service capacity headroom (fleet and driver availability) | [XX] | Hogan & ReVelle (1986) backup coverage; declined-work logs, Appendix 19 | [X] | [X] | [X] | [X] |
| Weighted total | 100 | — | [XX.X] | [XX.X] | [XX.X] | [XX.X] |

Note. Option C and the baseline are scored on the catchments they would continue to serve. Weights (Saaty's 1–9 pairwise scale) and option scores (1–5) set by [WHO] on [SCORING_DATE] against the evidence in Table A11.1, and recorded at Appendix 2. Where weighted totals sit within a point of each other the matrix has not separated the options, and the financial stage decides (Section 4.4).

The financial stage treated every option identically (Table 5), using the depot model presented to the board as corrected after review (Table A9.4). I made payback, not net present value, the primary ranking metric, a deliberate departure from convention. Because expansion funds itself sequentially, the timing of cash decides whether the 2028 depot happens at all, and an option with higher net present value but slower payback would break the chain it is meant to sustain. Payback's known weaknesses are that it ignores the time value of money and cash flows after the cut-off (Drury, 2021). I contained them by discounting it at [X]%, [DISCOUNT_RATE_BASIS, e.g. the owners' required return on retained equity], and by excluding any option with a negative net present value. I set aside accounting rate of return because it ignores timing, on which the chain depends, and internal rate of return because it can mis-rank options of different scale (Drury, 2021).

Table 5. Financial appraisal — identical treatment across options (models at Appendices 5, 8 and 9)

| Measure | Option A | Option B | Option C (defer) | Baseline |
| --- | --- | --- | --- | --- |
| Capital requirement — fleet, plant, yard (£) | 278,520 | 278,520 | [XX,XXX] | 0 |
| Fixed operating cost p.a. (£) | 369,940 | 339,940 | [XX,XXX] | [XXX,XXX] |
| Contribution per m³ (£) | 51.74 | 51.74 | [XX.XX] | [XX.XX] |
| Break-even volume (m³/month) | 596 | 548 (472 planned) | n/a | n/a |
| Break-even volume post-2028 (m³/month) | 761 with a third wagon (payload effect not yet modelled) | 550 with two wagons | n/a | n/a |
| Operating break-even reached (month) | Not estimable: annual model | Year 2: below break-even throughout 2027 | n/a | n/a |
| Payback (months) | 23 | 49 | n/a | n/a |
| Discounted payback at [X]% (months) | 24.7–25.5 at 8–12% (Table A9.3) | 56–61 at 8–12% (Table A11.7) | n/a | n/a |
| Cash generated by the 2028 opening (£) | 4,217 (year-1 free cash flow) | −112,877 (year-1 free cash flow) | n/a | n/a |
| NPV at [X]% over 5 years (£) | 889,618–1,053,412 at 12–8% (Table A9.3) | −8,556 to 42,110 at 12–8% (Table A11.7) | [XX,XXX] | 0 |
| Funds 2028 depot without external finance | Only with £274,303 from existing depots | No: existing depots would fund £391,397 | No | No |

Sensitivity analysis tested price alongside the three variables the interviews flagged as least certain (Appendix 9). A first-year volume shortfall of 25% stretches payback from 23 to 26 months and material inflation of 10% cuts contribution to £45.61 per cubic metre and stretches payback to 27, while rent barely matters. Price matters most, since a 10% cut takes payback to 33 months. That is significant because the board plan prices 9% below the local market average, buying entry with price where Section 3.4 argues reliability should earn it, and the discount pays only if it wins about 23% more volume than market rates would.

The framework has limits of its own. Pairwise weightings are judgements expressed as numbers, and the analytic hierarchy process disciplines judgement without removing it. Scoring on a common scale also brings back the commensurability I argued against above, so the weighted total is a structured comparison and should not be read as a measurement. A framework validated by internal practitioners may also encode Procon's existing assumptions. It still improves on what it replaces, because it turns tacit judgement into explicit, repeatable knowledge (Nonaka, 2008). The board can challenge a written weighting in a way it cannot challenge a director's intuition.

# 5. Recommendations and Implementation Plan

## 5.1 Recommendation

Procon should proceed with Option A, South Yorkshire, at a capital cost of £278,520. It ranks first on the weighted framework, scoring [MCDA_SCORE_A] against [MCDA_SCORE_B] for the nearest alternative. It breaks even at 596 cubic metres a month, 29% below planned first-year volume, and recovers its capital in 23 months. With help from the existing depots (Section 5.2) it lets the 2028 depot open without external finance, with a 46% margin of safety in 2028 before the payload effect (Table A8.1). Its advantage over Option B is demand: at the same market share Hull loses £47,091 in its first year and fails the board's GO rule (Appendix 11).

## 5.2 Funding strategy: a critical evaluation

The board's commitment to self-funding is what pecking-order theory would predict. Firms prefer internal finance because information asymmetry makes external capital costly (Myers & Majluf, 1984), and in an owner-managed business the wish to keep control reinforces the preference. A preference can be rational, however, and still cost the business something.

Higgins (1977) makes the cost of that preference measurable. Without new equity or higher gearing, growth cannot exceed the return on equity multiplied by the share of profit retained. Procon's chain tightens the limit, because a depot that has not recovered its capital by the next opening must be underwritten by the existing three. With a 23-month payback against a 12-month interval, and working capital absorbing first-year cash, the base business funds £274,303 of a same-cost 2028 depot (Figure 1). That figure, more than the board's preference, sets the true pace of self-funded growth. If the 2028 depot is East Yorkshire, as slide 12 plans, its first-year loss leaves the estate £391,397 to find for 2029 (Appendix 11).

Figure 1. Cumulative cash from the South Yorkshire depot by scenario, against the 2028 opening

Note. Rebuilt from the depot model presented to the board (Appendices 5 and 9); the scenarios apply the board's multipliers to every year, volume included. First-year EBITDA is £152,957, but free cash flow is £4,217, because working capital (£105,438), tax and maintenance absorb it. At the 12–18-month interval the board presentation plans for its next depot, the existing depots fund £126,345–£274,303 of it.

I evaluated four routes (Table 6). Self-funding preserves control and avoids covenant exposure at a 62-year volume low, but it caps expansion at one depot a year, and the cap has a price. With infrastructure growing while capacity leaves the sector (CPA, 2026; MPA, 2026), today's catchments will not stay available, and single-depot pacing forgoes an estimated £78,000–£95,000 of value a year (Table A9.3).

The board's framing underrates deferral. Under real options reasoning (Dixit & Pindyck, 1994), waiting has value when uncertainty is high and commitment irreversible, and both hold here. The option's value is falling, though. The CPA forecasts and the DfT's confirmed timetable have already resolved much of the uncertainty that waiting would address, and deferral means entering after competitors have absorbed the payload change. Nor is consolidation a certain cure for the capacity declines that make it look prudent (Section 3.4). Warrington's declines trace to vehicles off the road and driver cover, which can be fixed operationally, but six of the nine at Leeds record only that nothing was free before about 4pm and give no cause (Appendix 19). [SCHEDULER_FINDING — what fills the Leeds mornings, from the Scheduler interview. If drivers or scheduling, the operating-fix argument holds for both depots; if vehicles, Leeds needs capacity, which strengthens Option C: say so and show how the recommendation absorbs it.]

I therefore recommend proceeding self-funded for 2027 and departing from strict self-funding only if a defined trigger is met: volume at or above break-even (596 cubic metres a month) for three consecutive months by month nine prompts review of asset-financed acceleration of the 2029 opening, since demonstrated performance reduces the information asymmetry behind the pecking-order preference. That respects the board's risk appetite while testing the preference for self-funding against evidence instead of letting it harden into habit.

Table 6. Funding route evaluation

| Route | Advantages | Disadvantages | Assessment |
| --- | --- | --- | --- |
| Self-fund (recommended for 2027) | No gearing; full control; consistent with pecking-order preference | Caps growth to one depot p.a.; opportunity cost £78,000–£95,000 for each year a viable catchment waits (NPV × r/(1 + r) at 8–12%) | Adopt for 2027, with defined trigger for review |
| Asset finance on fleet (hire purchase or lease) | Releases cash for land and working capital; secured on vehicles, not the base business; 32t-compliant specification protects residual value | Higher fixed payments during ramp-up raise cash break-even; finance cost £125,600 a year for two vehicles in the board model | Preferred acceleration route if the trigger is met |
| Debt-funded acceleration | Captures infrastructure growth window; two depots in 2027 | Interest £31,000–£46,000 a year (8–12% on about £384,000); covenant exposure threatens base business | Reject; asset finance preferred if trigger met |
| Defer to 2028 | Real-option value under uncertainty; more data | Competitors adjust first; land off cycle floor; delay compounds | Reject — option value declining |

## 5.3 Governance, procurement and legal requirements

A capital release of £278,520 exceeds the Managing Director's delegated authority and requires minuted board approval. Fleet procurement must specify 32-tonne-compliant vehicles now, because Vehicle Special Orders lapse at a vehicle's twelfth anniversary of first registration (DfT, 2025a) and buying to the expiring standard would strand the asset. The operator licence must be varied for the new operating centre, with maintenance arrangements evidenced before trading, and the 12 Warrington enquiries lost to vehicles off the road (Appendix 19) show that maintenance is a reputational matter as much as a licence obligation. The cement silo also needs a Part B environmental permit (Table 8). Supply agreements should run for 24 months, both to hedge cement exposure, including CBAM pass-through, and to secure lower-clinker cement and GGBS for clients requiring Environmental Product Declarations.

## 5.4 Budget and resources

Table 7. Capital and resource budget

| Item | Cost (£) | Timing | Funding source | Owner |
| --- | --- | --- | --- | --- |
| Land acquisition / yard lease | 0 capital; lease £60,000 a year | [MONTH] | Retained profit | Managing Director |
| Volumetric fleet (2 units, 32t-compliant) | 150,000 | [MONTH] | Retained profit | Business Manager |
| Cement silo and loading shovel | 60,000 | [MONTH] | Retained profit | Operations Manager |
| Yard works, drainage and compliance | 43,200 | [MONTH] | Retained profit | Operations Manager |
| Working capital (45 debtor days, 30 creditor days, 7 days' stock) | 105,438 | Year 1 | Retained profit | Business Manager |
| Recruitment and training | [XX,XXX] | [MONTH] | Retained profit | Operations Manager |
| Contingency (10%) | 25,320 | — | Retained profit | Business Manager |
| Total | 278,520 capital; 105,438 working capital | — | — | — |

Note. Capital from the board model's schedule (£253,200 plus 10% contingency), mostly second-hand estimates; yard works cover blocks, security, fencing, cabins, laboratory, gantry, dust suppression, wash bay and water storage. Recruitment and training are not in the model.

## 5.5 Stakeholder engagement and communication

I mapped stakeholders on the power-interest matrix (Whittington et al., 2023), adapted from Mendelow's (1981) power-dynamism grid, and their positions drive the communication plan (Appendix 1). The grid is static, so I used salience (Mitchell et al., 1997) to track whose claims turn urgent at each gate, as the planning authority's claim does at G2. The Operations and Business Development Managers were engaged as participants and supplied evidence that tested the weightings (Section 4.3), and the depot teams' concern about capacity dilution is addressed directly.

## 5.6 Negotiation and influence

Two negotiations were material to the proposal. In both I used principled negotiation, separating stated positions from underlying interests (Fisher et al., 2012).

Upwards, capital approval meant reconciling the proposal with the board's stated position that [BOARD_POSITION]. What the directors were protecting was less the capital sum than [BOARD_INTEREST]. Recognising that turned an argument about quantum into one about [REFRAME], and I restructured the proposal to [RESTRUCTURE], which met the interest without cutting the investment. Cialdini's (2007) commitment principle shaped the sequencing. The board endorsed the framework as a governance instrument before the site recommendation was tabled, so it had accepted the method before seeing the output, though it could still reject the site.

Outwards, negotiation with the supplier on [MATERIAL] pricing and terms addressed the strategic exposure identified through Kraljic (1983). The supplier's stated position was [SUPPLIER_POSITION], and the interest behind it was [SUPPLIER_INTEREST]. With [BATNA, e.g. a second supplier's quotation] as Procon's best alternative to a negotiated agreement, structuring the deal as [AGREEMENT_STRUCTURE] served both interests and secured [OUTCOME — quantified].

## 5.7 Implementation, change and risk

Implementation is stage-gated so that no irreversible capital is committed until planning consent and demand assurance, the two dependencies most likely to invalidate the appraisal, are resolved (Table 8; Appendix 15). Because price is the largest sensitivity, pre-selling at agreed rates and volumes precedes any fleet commitment. Gantt dates are indicative because consents lie outside Procon's control (Table A14.2).

Adopting the framework is itself organisational change, because it moves site decisions from judgement to evidence. In Lewin's (1951) terms the margin and declined-work evidence unfreezes current practice, the 2027 decision is the change, and the board mandate refreezes the method, though its data is refreshed annually. Lewin's model is criticised for underplaying planning (Hayes, 2022), a criticism the stage gates answer by making planning iterative, and G7 and G8 guard against what Kotter (1995) calls declaring victory too soon.

Table 8. Stage-gated implementation timeline

| Gate | Milestone | Target date | Owner | Exit criterion |
| --- | --- | --- | --- | --- |
| G0 | Board approval of framework and capital release, with all four options as appraised here (board paper, Appendix 12) | [APPROVAL_DATE] | Managing Director | Minuted approval (Appendix 13) |
| G1 | Site secured subject to planning; application submitted | [MONTH YEAR] | Managing Director | Heads of terms agreed |
| G2 | Planning consent, O-licence variation and Part B permit for bulk cement storage granted (Environmental Permitting (England and Wales) Regulations 2016, Sch. 1, Pt 2, s. 3.1) | [MONTH YEAR] | Managing Director | Consents issued; no capital released before this gate |
| G3 | Pre-sell threshold met | [MONTH YEAR] | Business Development Manager | ≥ 50% of break-even volume (about 300 m³ a month) committed |
| G4 | Fleet and plant ordered (32t-compliant) | [MONTH YEAR] | Business Manager | G2 and G3 passed |
| G5 | Yard works, recruitment and training complete | [MONTH YEAR] | Operations Manager | Pre-opening depot audit passed; capital spend reconciled to Table 7 and variances explained (Shank & Churchill, 1977) |
| G6 | Go-live | [MONTH 2027] | Business Manager | First deliveries made |
| G7 | Six-month KPI review | [MONTH YEAR] | Business Manager | Volume on or above break-even path; operating variances explained |
| G8 | Funding-trigger review for later depots | [MONTH YEAR] | Managing Director | §5.2 trigger met or not met; East Yorkshire re-appraised on Hull evidence (A7, Table A15.3); decision minuted |

## 5.8 Progress to date

The board approved both the framework as standard investment governance and the recommended site on [APPROVAL_DATE] (Appendix 13). [EARLY_ACTIONS].

# 6. Conclusion

I recommend Option A, South Yorkshire, but the evidence revises the plan's premise. With a 23-month payback this depot cannot fund its successor a year later, so existing depots will underwrite about £274,000 of the 2028 opening (Section 5.2). The plan's third depot, in East Yorkshire, should stay conditional, since Hull passes the board's rule only with 16% more market share.

Three changes would make the framework more useful with each use. A post-completion audit at month 12 should compare each depot's trading with its forecast (Drury, 2021), building the reference class that Flyvbjerg (2008) shows judgement-based appraisal lacks. Enforcing the reason codes the depot logs already define (Appendix 19), and adding postcodes, would turn lost orders into a running map of unmet demand. Finally, the framework should be re-run each August, after the CPA's summer forecasts, against refreshed MPA and CPA data. The next steps are to confirm the 32-tonne compliance of the second-hand volumetrics, model the payload effect before the fleet order, and start pre-selling against the G3 threshold.

[REFLEXIVITY_NARRATIVE — ~80 words in your own voice: one belief the evidence changed, or confirmed for unexpected reasons, and what changed in the analysis as a result. One candidate: first treating deferral as a procedural alternative, then valuing it as a real option.]

If I repeated the study I would commission an external review of the financial model from the outset, and I would interview customers in the target catchment. Customers appear only indirectly, through the declined-enquiry records, the evidence's clearest gap, which I recognised too late to close within 12 weeks.

# References

Agg-Net. (n.d.-a). Hull concrete plant. Retrieved October 7, 2026, from https://www.agg-net.com/aggregates/hull-concrete-plant-0

Agg-Net. (n.d.-b). Hull concrete plant & aggregates wharf. Retrieved October 7, 2026, from https://agg-net.com/aggregates/hull-concrete-plant-aggregates-wharf

Barney, J. (1991). Firm resources and sustained competitive advantage. Journal of Management, 17(1), 99–120. https://doi.org/10.1177/014920639101700108

Barney, J. B. (1995). Looking inside for competitive advantage. Academy of Management Executive, 9(4), 49–61. https://doi.org/10.5465/ame.1995.9512032192

Belton, V., & Stewart, T. J. (2002). Multiple criteria decision analysis: An integrated approach. Kluwer Academic Publishers.

Beverley-Jones, L. (2026). Shaping and scoping the problem [PowerPoint slides]. BEMM117DA Strategic Business Proposal, University of Exeter ELE. https://ele.exeter.ac.uk/mod/resource/view.php?id=4424890

Boddy, D. (2002). Managing projects: Building and leading the team. Financial Times Prentice Hall.

Braun, V., & Clarke, V. (2006). Using thematic analysis in psychology. Qualitative Research in Psychology, 3(2), 77–101. https://doi.org/10.1191/1478088706qp063oa

British Standards Institution. (2023). PAS 2080:2023 Carbon management in buildings and infrastructure.

Church, R., & ReVelle, C. (1974). The maximal covering location problem. Papers of the Regional Science Association, 32(1), 101–118. https://doi.org/10.1007/BF01942293

Cialdini, R. B. (2007). Influence: The psychology of persuasion (Rev. ed.). Harper Business.

Clancy, T. (2018). Systems thinking: Three system archetypes every manager should know. IEEE Engineering Management Review, 46(2), 32–41. https://doi.org/10.1109/EMR.2018.2844377

Coghlan, D., & Brannick, T. (2014). Doing action research in your own organization (4th ed.). SAGE.

Companies House. (n.d.). READY CRETE LTD (14978531): Company overview. Retrieved October 7, 2026, from https://find-and-update.company-information.service.gov.uk/company/14978531

Competition and Markets Authority. (2021, September 20). Making environmental claims on goods and services. GOV.UK. https://www.gov.uk/government/publications/green-claims-code-making-environmental-claims/environmental-claims-on-goods-and-services

Concrete Connect. (n.d.). Ashcourt Concrete completes key pour for A63 project. Retrieved October 7, 2026, from https://concreteconnect.co.uk/news/ashcourt-concrete-completes-key-pour-for-a63-project

Construction Products Association. (2026, July 27). CPA releases summer forecasts 2026. https://www.constructionproducts.org.uk/news-media-events/news/2026/july/cpa-releases-summer-forecasts-2026

Costley, C., Elliott, G., & Gibbs, P. (2010). Doing work based research: Approaches to enquiry for insider-researchers. SAGE.

Department for Transport. (2023, October 19). Volumetric concrete mixers review [Call for evidence]. GOV.UK. https://www.gov.uk/government/calls-for-evidence/volumetric-concrete-mixers-review/volumetric-concrete-mixers-review

Department for Transport. (2025a, June 26). Volumetric concrete mixers: Call for evidence outcome. GOV.UK. https://www.gov.uk/government/calls-for-evidence/volumetric-concrete-mixers-review/outcome/volumetric-concrete-mixers-call-for-evidence-outcome

Department for Transport. (2025b, June 26). Volumetric concrete mixers: Fact sheet March 2025. GOV.UK. https://www.gov.uk/government/calls-for-evidence/volumetric-concrete-mixers-review/outcome/volumetric-concrete-mixers-fact-sheet-march-2025

Dixit, A. K., & Pindyck, R. S. (1994). Investment under uncertainty. Princeton University Press.

Doran, G. T. (1981). There's a S.M.A.R.T. way to write management's goals and objectives. Management Review, 70(11), 35–36.

Drury, C. (2021). Management and cost accounting (11th ed.). Cengage Learning.

Easterby-Smith, M., Jaspersen, L. J., Thorpe, R., & Valizade, D. (2021). Management and business research (7th ed.). SAGE.

Environmental Permitting (England and Wales) Regulations 2016, SI 2016/1154. https://www.legislation.gov.uk/uksi/2016/1154/contents

Fisher, R., Ury, W., & Patton, B. (2012). Getting to yes: Negotiating an agreement without giving in (3rd ed.). Random House Business.

Flyvbjerg, B. (2008). Curbing optimism bias and strategic misrepresentation in planning: Reference class forecasting in practice. European Planning Studies, 16(1), 3–21. https://doi.org/10.1080/09654310701747936

Flyvbjerg, B. (2021). Top ten behavioral biases in project management: An overview. Project Management Journal, 52(6), 531–546. https://doi.org/10.1177/87569728211049046

Fombrun, C., & Shanley, M. (1990). What's in a name? Reputation building and corporate strategy. Academy of Management Journal, 33(2), 233–258. https://doi.org/10.2307/256324

Future Humber. (2026, May 29). Humber Freeport promotes £3bn development potential with investment prospectus launch. https://www.futurehumber.com/news/humber-freeport-promotes-3bn-development-potential-with-investment-prospectus-launch

Harvey, W. S., Tourky, M., Knight, E., & Kitchen, P. (2017). Lens or prism? How organisations sustain multiple and competing reputations. European Journal of Marketing, 51(4), 821–844. https://doi.org/10.1108/EJM-03-2016-0122

Hayes, J. (2022). The theory and practice of change management (6th ed.). Red Globe Press.

Heidelberg Materials. (n.d.). Ready-mixed concrete Bridlington. Retrieved October 7, 2026, from https://www.heidelbergmaterials.co.uk/en/concrete/bridlington

Higgins, R. C. (1977). How much growth can a firm afford? Financial Management, 6(3), 7–16. https://doi.org/10.2307/3665251

HM Revenue & Customs. (2025). Carbon border adjustment mechanism [Policy paper]. GOV.UK. https://www.gov.uk/government/publications/introduction-of-carbon-border-adjustment-mechanism/carbon-border-adjustment-mechanism

Hogan, K., & ReVelle, C. (1986). Concepts and applications of backup coverage. Management Science, 32(11), 1434–1444. https://doi.org/10.1287/mnsc.32.11.1434

Hotelling, H. (1929). Stability in competition. The Economic Journal, 39(153), 41–57. https://doi.org/10.2307/2224214

Hull City Council. (2019, November 15). How Hull is tackling flooding [Press release]. https://news.hull.gov.uk/15/11/2019/how-hull-is-tackling-flooding

Hull Daily Mail. (2026, March 26). New era for the A63 in Hull as 'transformative' split-level junction opens. https://hulldailymail.co.uk/news/hull-east-yorkshire-news/new-era-a63-hull-transformative-10886152

Humber Bridge Board. (n.d.). Toll prices. Retrieved October 7, 2026, from https://www.humberbridge.co.uk/plan-your-trip/toll-prices/

Keller, K. L. (1993). Conceptualizing, measuring, and managing customer-based brand equity. Journal of Marketing, 57(1), 1–22. https://doi.org/10.1177/002224299305700101

Kotter, J. P. (1995). Leading change: Why transformation efforts fail. Harvard Business Review, 73(2), 59–67.

Kraljic, P. (1983). Purchasing must become supply management. Harvard Business Review, 61(5), 109–117.

Leek, S., & Christodoulides, G. (2012). A framework of brand value in B2B markets: The contributing role of functional and emotional components. Industrial Marketing Management, 41(1), 106–114. https://doi.org/10.1016/j.indmarman.2011.11.009

Lewin, K. (1951). Field theory in social science: Selected theoretical papers (D. Cartwright, Ed.). Harper & Row.

Luchins, A. S. (1942). Mechanization in problem solving: The effect of Einstellung. Psychological Monographs, 54(6), i–95. https://doi.org/10.1037/h0093502

Mendelow, A. L. (1981). Environmental scanning: The impact of the stakeholder concept. In Proceedings of the Second International Conference on Information Systems (pp. 407–417). Association for Information Systems. https://aisel.aisnet.org/icis1981/20

Mineral Products Association. (2025a). Profile of the UK mineral products industry: 2025 edition. https://mineralproducts.org/MPA/media/root/Publications/2025/Profile_of_the_UK_Mineral_Products_Industry_2025.pdf

Mineral Products Association. (2025b, August 4). Concrete market plumbs new depths as business confidence shrivels across mineral products sector [Press release]. https://mineralproducts.org/News/2025/release26.aspx

Mineral Products Association. (2026, February 2). Four years of decline in British construction demand threatens jobs and future capacity, warns MPA [Press release]. https://mineralproducts.org/News/2026/release02.aspx

Minsky, L., & Aron, D. (2021, February 23). Are you doing the SWOT analysis backwards? Harvard Business Review. https://hbr.org/2021/02/are-you-doing-the-swot-analysis-backwards

Mitchell, R. K., Agle, B. R., & Wood, D. J. (1997). Toward a theory of stakeholder identification and salience: Defining the principle of who and what really counts. Academy of Management Review, 22(4), 853–886. https://doi.org/10.5465/amr.1997.9711022105

Mixamate. (n.d.). Volumetric concrete Hull. Retrieved October 7, 2026, from https://mixamate.co.uk/hull/volumetric-concrete/

Myers, S. C., & Majluf, N. S. (1984). Corporate financing and investment decisions when firms have information that investors do not have. Journal of Financial Economics, 13(2), 187–221. https://doi.org/10.1016/0304-405X(84)90023-0

National Highways. (2024). Net zero highways progress report 2023–2024. https://nationalhighways.co.uk/our-contribution/protecting-our-environment/environment/net-zero-highways-progress-report-2023-2024/

Nonaka, I. (2008). The knowledge-creating company. Harvard Business Press.

Office for National Statistics. (2013, June 28). Characteristics of built-up areas. https://www.ons.gov.uk/peoplepopulationandcommunity/housing/articles/characteristicsofbuiltupareas/2013-06-28

Office for National Statistics. (2023, August 2). Towns and cities, characteristics of built-up areas, England and Wales: Census 2021 [Data set]. https://www.ons.gov.uk/peoplepopulationandcommunity/housing/datasets/townsandcitiescharacteristicsofbuiltupareasenglandandwalescensus2021

Office for National Statistics. (2026, September 11). Construction output in Great Britain: July 2026 [Statistical bulletin]. https://www.ons.gov.uk/businessindustryandtrade/constructionindustry/bulletins/constructionoutputingreatbritain/july2026

Ohno, T. (1988). Toyota production system: Beyond large-scale production. Productivity Press.

Porter, M. E. (2008). The five competitive forces that shape strategy. Harvard Business Review, 86(1), 78–93.

Saaty, T. L. (2008). Decision making with the analytic hierarchy process. International Journal of Services Sciences, 1(1), 83–98. https://doi.org/10.1504/IJSSCI.2008.017590

Saunders, M. N. K., Lewis, P., & Thornhill, A. (2019). Research methods for business students (8th ed.). Pearson.

Saunders, M. N. K., & Townsend, K. (2016). Reporting and justifying the number of interview participants in organization and workplace research. British Journal of Management, 27(4), 836–852. https://doi.org/10.1111/1467-8551.12182

Senge, P. M. (2006). The fifth discipline: The art and practice of the learning organization (Rev. ed.). Random House Business.

Shank, J. K., & Churchill, N. C. (1977). Variance analysis: A management-oriented approach. The Accounting Review, 52(4), 950–957.

Sheffield City Council. (2026, February 19). Heart of the City transformation delivers strong financial performance [Press release]. https://www.sheffield.gov.uk/news/2026/heart-city-transformation-delivers-strong-financial-performance

UK Concrete & Mineral Products Association. (2025). UK concrete and cement industry roadmap to beyond net zero: Progress report 2025. https://www.thisisukconcrete.co.uk/TIC/media/root/Resources/2025-09-15-CC-Roadmap-to-Beyond-Net-Zero-final.pdf

Urbo Regeneration. (n.d.). West Bar, Sheffield. Retrieved October 7, 2026, from https://urboregen.com/west-bar/

Weber, A. (1929). Theory of the location of industries (C. J. Friedrich, Trans.). University of Chicago Press. (Original work published 1909)

Whittington, R., Regnér, P., Angwin, D., Johnson, G., & Scholes, K. (2023). Exploring strategy (13th ed.). Pearson.

Yin, R. K. (2018). Case study research and applications: Design and methods (6th ed.). SAGE.

Generative AI use: AI tools were used only for the purposes permitted by the assessment brief. Every prompt, with a hyperlink to its output, is listed below and in Appendix 18.

Prompt list

[INSERT one line per prompt: date; tool; prompt as entered; hyperlink to the output. Include every session, among them 22 September (introduction), 1 October (humanising), 2–5 October (v8–v12 revisions and the depot model review), 6 October (v13 review and the v14–v17 drafts, including the v15 humanising pass) and 7 October (Option B desk search and model run; the v19 edit, which re-based Option B on Census 2021 populations, corrected the Hull competitor search, applied the v18 marking note and cut the text to the word limit).]

# Appendices

Schedule of appendices

| # | Appendix | Produced | Cited in |
| --- | --- | --- | --- |
| 1 | Stakeholder map (power-interest matrix, after Whittington et al., 2023) and communication plan | Week 1 | 5.5 |
| 2 | Criteria matrix and weightings (pre- and post-interview) | Week 2 | 4.1, 4.4 |
| 3 | Demand baseline — catchment analysis | Week 3 | 4.3 |
| 4 | Competitor coverage map, PESTEL and SWOT | Week 4 | 3.1, 4.3 |
| 5 | Depot cost model extract | Week 5 | 4.4 |
| 6 | Interview guide | Week 6 | 4.1 |
| 7 | Anonymised interview transcript | Week 6 | 4.1 |
| 8 | Break-even model | Week 7 | 4.3, 4.4 |
| 9 | Scenario and sensitivity pack | Week 8 | 4.4, 5.2 |
| 10 | Site long-list and feasibility notes | Week 9 | 4.3 |
| 11 | MCDA ranked shortlist and Option B appraisal (Hull and the Humber) | Week 10 | 4.3, 4.4, 5.1 |
| 12 | Board presentation (13 slides) and depot business-case model, as presented | Week 11 | 4.3, 4.4, 5.7 |
| 13 | Board approval evidence (minutes) | Week 12 | 5.8 — required for S2 |
| 14 | Project and implementation Gantt charts; RACI matrix; planning tools evaluated | Ongoing | 5.7 |
| 15 | RAID log: risks, opportunities, assumptions, issues and dependencies | From week 1 | 5.7 |
| 16 | KSB mapping document | Week 12 | Mandatory; section-by-section KSB evidence |
| 17 | Employer authenticity statement | Week 12 | Mandatory |
| 18 | AI-use log | From day one | Mandatory |
| 19 | Declined-work analysis, Leeds and Warrington (Apr–Jul 2026) | Week [X] | 3.1, 3.4, 4.3, 5.2, 5.3, 6 |

## Appendix 1. Stakeholder map and communication plan

Figure A1.1. Stakeholder power-interest matrix (after Whittington et al., 2023)

Note. Placement follows the power and interest ratings in Table A1.1; the labels in each corner are the standard strategies for that quadrant.

Table A1.1. Communication plan, with salience (Mitchell et al., 1997) and influencing tactics (Boddy, 2002)

| Stakeholder | Power / interest; salience | Strategy and tactics | Key message | Channel | Frequency | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| MD and board | High / High; definitive | Manage closely: rational persuasion, consultation | A repeatable, evidence-based site decision: Option A breaks even at 596 m³ a month against 842 planned, and capital is released only gate by gate. | Sponsor review; board paper | Fortnightly | Business Manager |
| Operations Manager | Medium / High; dominant, definitive at G5 | Engage participatively: consultation | Capacity headroom is both a selection criterion and a gate: the depot opens only with its own drivers, maintenance and spare cover in place (G5). | Working session | Weekly | Business Manager |
| Business Development Manager | Medium / High; dominant, definitive at G3 | Engage participatively: consultation | Pre-sold volume at agreed rates gates the fleet order (G3); the offer is reliability, not discount. | Working session | Weekly | Business Manager |
| Scheduler | Low / High; discretionary, dependent at G6 | Keep informed: rational persuasion | Morning capacity at Leeds is the constraint the plan must not worsen; coded decline logs with postcodes will show whether it does. | Briefing | Fortnightly | Operations Manager |
| Material suppliers | Medium / Medium; dominant, definitive at G6 | Keep satisfied: exchange | A second site means more volume under a 24-month agreement, in return for price stability and lower-clinker cement and GGBS supply. | Commercial meeting | Monthly | Business Manager |
| Depot teams | Low / High; discretionary, dependent at G6 | Keep informed; address capacity concern: consultation | Capacity-related declines at your depot are reported monthly (KPI 5), and the new depot opens with its own crew and maintenance cover. | Toolbox talk | Monthly | Operations Manager |
| Target catchment customers | Medium / Low; dominant, definitive at G3 | Monitor; pre-sell: rational persuasion | A local volumetric depot with Procon's reliability at agreed rates, distinct from similarly named rivals. | Direct sales contact | Fortnightly in pre-sell (G1–G3), then monthly | Business Development Manager |
| Planning authority | High / Low; dominant, definitive at G2 | Keep satisfied: legitimating | A surfaced yard with dust suppression and a managed wash bay, with the Part B permit applied for alongside the planning application. | Formal submission | As required | Managing Director |

## Appendix 4. Competitor coverage map, PESTEL and SWOT

[INSERT: competitor coverage map, showing competing plants inside the eight-mile radius of each candidate catchment]

Table A4.1. PESTEL factors and whether they discriminate between catchments (after Whittington et al., 2023)

| Domain | Factor | Evidence | Discriminates between catchments? |
| --- | --- | --- | --- |
| Political | UK carbon border adjustment mechanism taxes imported cement, 32% of the UK market, from January 2027 | HMRC (2025); MPA (2025a) | Little: input costs rise at every candidate site |
| Economic | Private housing output forecast to fall 10.0% in 2026 while infrastructure grows 3.2% in 2026 and 2027; ready-mixed volumes at their lowest since 1963 | CPA (2026); MPA (2025b) | Yes: catchments differ in their mix of housing and infrastructure demand |
| Social | Business buyers value reliability and the trust it creates | Leek & Christodoulides (2012); Appendix 19 | Little: the expectation is the same everywhere; capacity to meet it is scored separately (Table 4) |
| Technological | On-site volumetric batching reduces waste; lower-clinker cements and GGBS reduce embodied carbon | DfT (2023); UK Concrete & MPA (2025) | Little in itself: batching travels with the fleet; only access to GGBS and low-clinker supply varies, and Table 4 scores it |
| Environmental | Infrastructure clients pass carbon requirements down the supply chain: PAS 2080 for National Highways' Tier 1 suppliers; Environmental Product Declarations requested from material suppliers | National Highways (2024); BSI (2023); MPA (2025a) | Yes, through the economic domain: it bites hardest where infrastructure demand is concentrated |
| Legal | Volumetric mixers revert to 32 tonnes from 2028, with no further extensions; environmental claims must be substantiated | DfT (2025b); CMA (2021) | Yes: a shorter viable haul radius makes catchment geometry decisive |

Table A4.1 tests each PESTEL domain against the question that matters for site selection: does it discriminate between catchments? PESTEL lists its domains one at a time, so it cannot show how they interact, as the economic and environmental domains do through infrastructure demand, or how reliable the data behind each one is. The SWOT below therefore starts from the external factors, as Minsky and Aron (2021) recommend, so that each internal factor is judged against the conditions it must meet. It ends in recommendations, not a grid: each row of Table A4.3 pairs an external condition with an internal capability and names the part of the proposal that acts on it. Every factor is drawn from evidence presented in the proposal.

Table A4.2. SWOT factors, external first (Minsky & Aron, 2021)

| Ref | Factor | Evidence |
| --- | --- | --- |
| O1 | Infrastructure output forecast to grow 3.2% in 2026 and 2027 while private housing falls 10.0% in 2026 | CPA (2026) |
| O2 | Infrastructure clients pass carbon requirements down the supply chain: PAS 2080 verification for National Highways' Tier 1 suppliers; Environmental Product Declarations requested from material suppliers | National Highways (2024); BSI (2023); MPA (2025a) |
| O3 | Capacity is leaving a contracting sector | MPA (2026) |
| T1 | Volumetric weight derogation ends in 2028: 32-tonne limit, no further extensions | DfT (2025b) |
| T2 | Ready-mixed volumes at their lowest since 1963 | MPA (2025b) |
| T3 | Intense price rivalry: 740 MPA-member plants; 200 m³ lost to Chorley Concrete | MPA (2025a); Appendix 19 |
| T4 | Imported cement, 32% of the UK market, taxed under UK CBAM from January 2027 | MPA (2025a); HMRC (2025) |
| S1 | Volumetric batching mixes on site when needed, reducing waste | DfT (2023); returned-load records [to quantify] |
| S2 | Delivery reputation built on reliability | §3.4 |
| S3 | Self-funded growth: no gearing, owner control | §5.2 |
| S4 | Trading history of three depots, including a recent opening usable as a reference case | §4.2 |
| W1 | No repeatable site-selection method or profitability threshold | §2; §3.2 |
| W2 | Capacity constraints: 22 of 27 declines, April–July 2026, for want of drivers, vehicles or slots | Appendix 19 |
| W3 | Fleet reliability: 12 Warrington enquiries lost to vehicles off the road | Appendix 19 |
| W4 | Gross margin per m³ varies [MARGIN_MULTIPLE]-fold across depots | Management accounts |
| W5 | Decline reasons recorded as free text, so the dashboards attribute nothing | Appendix 19 |

Table A4.3. Recommendations generated from the SWOT (sentence structure after Minsky & Aron, 2021)

| Given the condition of… | our ability (or inability) to… | leads to our recommendation that we… | Where |
| --- | --- | --- | --- |
| infrastructure growth while housing falls, and clients' carbon requirements (O1, O2) | mix on site with less waste (S1) | weight infrastructure exposure and low-carbon capability in site selection, and quantify the waste advantage before marketing it | Table 4; §3.1 |
| the 2028 payload reversion (T1) | serve demand when vehicles or drivers are short (W2, W3) | weight payload resilience and capacity headroom, and buy a 32-tonne-compliant fleet with maintenance cover | Table 4; §5.3 |
| price set by rivals (T3) | deliver reliably (S2) | compete on reliability, protected by the capacity weighting and a capacity-decline KPI | §3.4; Table 1 |
| a contracting sector (T2) | choose sites by a repeatable method (W1, W4) | adopt the weighted framework, with a minimum margin, before any capital release | §5.1; Table 1 |
| CBAM on imported cement (T4) | absorb cost shocks inside a self-funding chain (S3) | hedge cement through a fixed-term supply agreement | §5.3 |
| capacity leaving the sector (O3) | fund more than one depot a year (S3) | set a trigger for asset-financed acceleration | §5.2 |
| demand moving between places (O1) | learn from lost orders (W5) | enforce reason codes and record postcodes | §6 |

Table A4.4. Competitors in the South Yorkshire catchment, as listed in the board presentation

| Competitor | Type | Location and notes, as listed |
| --- | --- | --- |
| Volmix | Volumetric, drum and minimix | Ripley and Belper; 22 trucks; largest independent |
| Bear Concrete | Volumetric | Depots at Chesterfield, Aston and Hucknall |
| Procrete Yorkshire | Volumetric | 24/7 on-site mixing; closest to Procon's model |
| 24/7 Concrete & Aggregates | Volumetric | Sheffield, Barnsley, Rotherham and Doncaster |
| Erewash Concrete | Volumetric | Pinxton; 0.5–8 m³, same or next day |
| Breedon | Fixed plant | Hope cement works |
| Heidelberg Materials (Hanson) | Fixed plant | Wigwam Lane |
| Rightmix | Fixed plant | South Sheffield |
| Tarmac; Aggregate Industries | Fixed plant | Mansfield and Chesterfield |
| Retford Ready Mix | Minimix | 1–4 m³ loads |
| Concrete2You; Ashfield Mini Mix | Online, small loads | — |

Note. Board presentation, slide 9 (Appendix 12). Capacity is recorded for one rival only, so demand per unit of competing capacity (Table 4) cannot yet be scored from this list. One rival trades as 24/7 Concrete & Aggregates across the catchment, a name close enough to Procon 24/7 to confuse buyers there (RAID R9).

## Appendix 5. Depot cost model extract

The depot model presented to the board is an Excel workbook ('Procon 247 New Depot Case Study') with an assumptions sheet, a capital schedule, a five-year profit and loss account and a cash flow. Table A5.1 gives its inputs with the basis the workbook records for each; the workbook's own banner warns that inputs are placeholders until replaced with site data, so estimates are marked as such. Table A5.2 is the base case.

Table A5.1. Inputs to the board model and their recorded basis

| Input | Value | Basis recorded in the workbook |
| --- | --- | --- |
| Working days | 269.5 a year | 49 weeks of 5.5 days (half of Saturdays) |
| Daily volume | 37.5 m³ in 2027, then 62.5, 70, 74 and 77 | Leeds trading in 2022 |
| Average selling price | £119/m³, rising 2.5% a year | Procon's current average rate for the area |
| Materials | £61.26/m³: cement £25.25, sand £12.58, stone £23.43 | Non-certified supplier costs (slide 7) |
| Admixtures and water; fuel | £3.50 and £2.50 per m³ | Estimate |
| Rent; business rates | £60,000; £30,000 a year | Rent to suit the listed yards (Appendix 10); rates estimated |
| Labour | £37,440 a year | £16 an hour, 45 hours, 52 weeks: one post |
| Office and management labour | £72,000 a year | Trainee scheduler and sales; may be carried at Warrington |
| Other fixed costs | £44,900 a year | Repairs £5,000; utilities £20,000; insurance £10,000; testing £5,000; IT £2,400; other £2,500 (estimates) |
| Fleet | Two mixers; finance £62,800 a year each | £5,233 a month per vehicle |
| Capital | £278,520 | Capital schedule £253,200 plus 10% contingency; mostly second-hand estimates |
| Inflation | Price and variable cost 2.5%; fixed cost 3% a year | Estimate |
| Working capital | 45 debtor days; 30 creditor days; 7 days' stock | Estimate |
| Tax; depreciation; maintenance capital | 25%; ten years; 1% of revenue | Model convention |
| Discount rate | 0% | Not set (Table A9.4) |

Table A5.2. Base case: five-year profit and cash flow (£)

| Line | 2027 | 2028 | 2029 | 2030 | 2031 |
| --- | --- | --- | --- | --- | --- |
| Volume (m³ a day) | 37.5 | 62.5 | 70 | 74 | 77 |
| Price (£/m³) | 119.00 | 121.97 | 125.02 | 128.15 | 131.35 |
| Revenue | 1,202,644 | 2,054,516 | 2,358,585 | 2,555,695 | 2,725,787 |
| Variable costs | 679,746 | 1,161,233 | 1,333,096 | 1,444,505 | 1,540,642 |
| Fixed operating costs | 244,340 | 251,670 | 259,220 | 266,997 | 275,007 |
| Fleet finance | 125,600 | 129,368 | 133,249 | 137,246 | 141,364 |
| EBITDA | 152,957 | 512,245 | 633,020 | 706,947 | 768,774 |
| EBITDA margin | 12.7% | 24.9% | 26.8% | 27.7% | 28.2% |
| Tax | 31,276 | 121,098 | 151,292 | 169,774 | 185,231 |
| Increase in working capital | 105,438 | 74,685 | 26,658 | 17,281 | 14,912 |
| Maintenance capital | 12,026 | 20,545 | 23,586 | 25,557 | 27,258 |
| Free cash flow | 4,217 | 295,916 | 431,484 | 494,335 | 541,373 |
| Cumulative cash (after £278,520 capital) | -274,303 | 21,613 | 453,097 | 947,432 | 1,488,806 |

Note. Reproduces the workbook to the pound; the rebuild used for Appendices 8 and 9 was reconciled to it before use.

## Appendix 8. Break-even model

Table A8.1. Break-even by case

| Case | Fixed costs (£) | Contribution (£/m³) | Break-even (m³/day) | Break-even (m³/month) | Planned (m³/day) | Margin of safety |
| --- | --- | --- | --- | --- | --- | --- |
| 2027, two wagons (board model) | 369,940 | 51.74 | 26.5 | 596 | 37.5 | 29% |
| 2028, two wagons (board model) | 381,038 | 53.03 | 26.7 | 599 | 62.5 | 57% |
| 2028, third wagon and one more driver (slide 11) | 484,285 | 53.03 | 33.9 | 761 | 62.5 | 46% |
| 2027, full downside | 369,940 | 44.81 | 30.6 | 688 | 28.125 | -9% |

Note. Break-even follows the workbook's definition: fixed operating and fleet costs divided by contribution per cubic metre, before tax and working capital. Month figures use 269.5 working days. None of the cases includes the 2028 payload effect.

## Appendix 9. Scenario and sensitivity pack

The workbook was rebuilt line by line outside Excel and reconciled to it: first-year revenue (£1,202,644), EBITDA (£152,957) and five-year cumulative cash (£1,488,806) match. The rebuild was then used to correct the faults in Table A9.4 and to run the tests below. Payback is interpolated within the year in which cumulative cash turns positive.

Table A9.1. Scenarios, with the board's multipliers applied to every year

| Measure | Downside | Base | Upside |
| --- | --- | --- | --- |
| Multipliers: volume, price, variable cost, capital | 0.75, 0.97, 1.05, 1.10 | 1.00 throughout | 1.20, 1.02, 0.98, 0.95 |
| Capital (£) | 306,372 | 278,520 | 264,594 |
| Year-1 EBITDA (£) | -30,317 | 152,957 | 302,714 |
| Year-1 free cash flow (£) | -113,202 | 4,217 | 87,818 |
| Cumulative cash at month 12 (£) | -419,574 | -274,303 | -176,776 |
| Payback (months) | 44.5 | 23.1 | 16.6 |
| Five-year cumulative cash (£) | 304,342 | 1,488,806 | 2,436,108 |
| Board decision rule | NO-GO | GO | GO |

Note. The decision rule is the workbook's: GO if year-1 EBITDA and five-year cash are positive and payback is four years or less; NO-GO if year-1 EBITDA is negative. The workbook's dashboard applies the price, cost and capital multipliers but not the volume multiplier, because volumes are typed into the profit and loss sheet, so its Downside shows GO with year-1 EBITDA of £82,891.

Table A9.2. One-at-a-time sensitivities (base payback 23.1 months; base-business share £274,303)

| Variable | Change | Payback (months) | Change (months) | Base-business share of a same-cost 2028 depot (£) |
| --- | --- | --- | --- | --- |
| First-year volume | −25% | 26.1 | +3.0 | 344,385 |
| Volume, all years | −10% | 26.1 | +3.0 | 301,774 |
| Volume, all years | +10% | 20.4 | -2.7 | 246,832 |
| Volume on the workbook's stated ramp percentages | 57.2–72.5 m³/day from 2028 | 24.6 | +1.4 | 274,303 |
| Price | −10% | 32.9 | +9.8 | 348,472 |
| Price | +10% | 17.5 | -5.6 | 200,135 |
| Price at the local market average (slide 8) | £130.75/m³ | 17.5 | -5.6 | 201,094 |
| Materials | +10% | 27.4 | +4.3 | 316,835 |
| Materials | −10% | 19.5 | -3.7 | 231,771 |
| Materials at the five-mix average (slide 7) | £66.55/m³ | 26.8 | +3.6 | 311,017 |
| Materials at the certified (BSI) average (slide 7) | £75.68/m³ | 38.0 | +14.9 | 379,576 |
| Fixed costs | +10% | 25.0 | +1.9 | 302,049 |
| Rent | £50,000 a year | 22.5 | -0.6 | 266,803 |
| Rent | £70,000 a year | 23.7 | +0.6 | 281,803 |
| Freehold yard (Attercliffe) instead of a lease | £1.0m capital; no rent | 43.0 | +19.9 | — |
| Capital | +10% | 24.1 | +1.0 | 301,459 |
| Third wagon and one more driver from 2028 (slide 11) | +£100,240 a year | 25.9 | +2.8 | 274,303 |
| Second driver from opening | +£37,440 a year | 25.1 | +1.9 | 302,383 |

Note. The base-business share is the 2028 depot's capital, assumed equal to this depot's, less the free cash flow this depot generates in its first twelve months. Price and materials are the largest effects; rent and capital the smallest.

Table A9.3. Payback and net present value at alternative discount rates

| Discount rate | Net present value over five years (£) | Discounted payback (months) |
| --- | --- | --- |
| 0% (as presented) | 1,488,806 | 23.1 |
| 8% | 1,053,412 | 24.7 |
| 10% | 967,841 | 25.1 |
| 12% | 889,618 | 25.5 |

Note. Cash flows discounted at each year end. The rate the board should apply is [DISCOUNT_RATE_BASIS] (§4.4).

Table A9.4. Review of the board model: findings and treatment

| # | Finding | Effect | Treatment in this proposal |
| --- | --- | --- | --- |
| 1 | Payback counted in whole years: the dashboard shows 2 | Interpolated payback is 23.1 months; the self-funding test needs months | Months used throughout (§4.4, §5.2) |
| 2 | Discount rate set at 0%, so the 'NPV' line equals undiscounted five-year cash (£1,488,806) | Value overstated | NPV at 8–12% reported (Table A9.3) |
| 3 | Volume multiplier not linked to the profit and loss sheet | The dashboard's Downside shows GO | Scenarios rerun (Table A9.1): the full downside is NO-GO under the board's own rule |
| 4 | Scenarios sheet applies ramp-up twice (noted on the sheet itself) | Sheet unusable | Not used |
| 5 | Typed volumes (62.5–77 m³/day) run ahead of the stated ramp percentages (57.2–72.5) | On the stated ramp, payback is 24.6 months | Assumption A3 tested at G7 (Appendix 15) |
| 6 | Fleet appears twice: £150,000 capital for two volumetrics and £125,600 a year finance for two wagons | If the finance is for these vehicles, capital falls to £113,520 and payback to 16.7 months; if the capital line is Leeds vehicles transferred, Leeds loses capacity it already lacks (§3.4) | [CONFIRM which applies]; base left as presented |
| 7 | One driver costed (£37,440) for two wagons | A second driver adds 1.9 months to payback | [CONFIRM how the second wagon is crewed] |
| 8 | Third wagon planned for 2028 (slide 11) is not in the model | Adds 2.8 months; 2028 break-even rises to 33.9 m³/day | Shown in Tables A8.1 and A9.2 |
| 9 | Materials priced for a low-cement mix (£61.26/m³, against £70.17 for C28/35 on slide 7) | At the five-mix average payback is 26.8 months; at the certified (BSI) average, 38.0 | [CONFIRM the expected mix and share of certified work] |
| 10 | No adjustment for the 2028 payload reversion | Post-2028 cost understated by £[COST_PER_M3_DELTA]/m³ | To be modelled before G4 |
| 11 | Annual periods only | The month of operating break-even cannot be estimated | Monthly ramp to be modelled for the G7 review |
| 12 | Second-hand volumetrics costed at £75,000 each, with no record of compliance with the 32-tonne standard | A unit bought to the expiring standard becomes a compliance liability (§5.3) | [CONFIRM before G4] |

## Appendix 10. Site long-list and feasibility notes

Table A10.1. Surfaced yards shortlisted in the Sheffield–Doncaster corridor

| Location | Size (acres) | Basis | Annual rate | Listing |
| --- | --- | --- | --- | --- |
| Blyth, S81 | 1.1 | To let | £60,000 | LoopNet 38167046 |
| Sheffield S4 | 1.5 | To let | £70,000 | Rightmove 7545999 |
| Sheffield S9, Stevenson Road | 1.1 | To let | £50,000 | LoopNet 31665199 |
| Sheffield S71 (Barnsley) | 1.0 | To let | £50,000 | Knight Frank HUB2530520 |
| Hurst Lane, Auckley | 1.25 | To let | £50,000 | Flint 301 |
| Mission Springs, Doncaster | 1.25 | To let | £50,000 | Flint 76 |
| Neale Road, Doncaster DN2 | 1.0 | To let | £50,000 (slide 5: to be confirmed) | Rightmove 7605502 |
| Rotherham Road, Rotherham | 1.25 | To let | £50,000 (slide 6: to be confirmed) | Knight Frank HUB2687897 |
| Sheffield S9, Attercliffe | 1.4 | Freehold | £1.0m purchase | Knight Frank, S9 2PF |

Note. Board presentation, slides 4 to 6 (Appendix 12). All are bare surfaced yards that suit silos and cabins without a building. Slide 6 describes rents as per acre; the listings are per site. The presentation uses a 10-mile Sheffield core, the framework an 8-mile radius (§2). Rent across the leased yards moves payback by under a month (Table A9.2); buying Attercliffe would stretch it to 43 months, and a lease keeps the commitment reversible (Dixit & Pindyck, 1994).

## Appendix 11. MCDA ranked shortlist and Option B appraisal (Hull and the Humber)

Option B was appraised with the same framework (Table 4) and depot model (Appendices 5, 8 and 9) as Option A, changing only the inputs where evidence shows a site difference; inputs only Procon can confirm are marked [CONFIRM]. Catchment size decides the result. Census 2021 built-up areas put 402,845 people within eight miles of Hull centre and 719,300 within eight miles of Sheffield's (author's calculation from ONS, 2023), a ratio of 0.560, and 18,085 of Hull's live south of the Humber, behind a toll crossing. Because the board model's volumes come from Leeds's trading, not from a market share (Table A5.1), the base case assumes Option B wins the same share of its market as Option A and scales Option A's volumes by 0.560. An earlier draft used 2011 built-up areas (ONS, 2013), in which Sheffield's included Rotherham; that ratio, 0.458, made Option B look far weaker (Table A11.6). Procon's own deliveries support the new ratio by volume but not by breadth (Table A11.1), so the base case tests catchment size rather than forecasting Hull. Table A11.6 shows the share Option B would need to pass each financial test. Desk searches and model runs for this appendix were AI-assisted and are logged in the prompt list.

Table A11.1. Criterion evidence for scoring Option A and Option B

| Criterion | Option A, South Yorkshire | Option B, Hull and the Humber |
| --- | --- | --- |
| Catchment demand density (8-mile radius) | 719,300 people within eight miles of Sheffield centre in Census 2021 built-up areas (author's calculation from ONS, 2023); radius entirely on land. Leeds delivered 3,854 m³ to S postcodes from January 2022 to May 2026, to 157 customers; the largest took 31% | 402,845 within eight miles of Hull centre (author's calculation from ONS, 2023), 18,085 of them south of the Humber, where a three-axle HGV pays £12–£15 a crossing (Humber Bridge Board, n.d.). Leeds delivered 2,422 m³ to HU postcodes over the same period, to 15 customers; the largest took 57%. The declined-work logs hold no Hull enquiries (Appendix 19) |
| Demand per unit of competing capacity | Five volumetric rivals, plus fixed-plant, minimix and online operators (Table A4.4); none publishes capacity | Two volumetric operators advertise in Hull, Ready Crete (Dunswell) and Mixamate, alongside three fixed plants in the city and one at Bridlington (Table A11.9); none publishes capacity |
| Post-2028 payload resilience | No evidence of a difference until haul distances and load sizes are compared | As Option A |
| Infrastructure pipeline exposure | West Bar's second phase from 2027 (Urbo Regeneration, n.d.); National Highways and council frameworks; SDF2 Lot 2 (Table 3). Heart of the City completed in February 2026 (Sheffield City Council, 2026) | Humber Freeport: over £2bn secured and up to £3bn more over a decade (Future Humber, 2026). The A63 Castle Street scheme opened in March 2026 (Hull Daily Mail, 2026), so it is no longer in the pipeline |
| Operating cost base | Fixed costs £369,940 a year (Table A5.1); domestic cement at Hope, about 15 miles from Sheffield (Table A4.4) | Fixed costs £339,940 a year, since rent and rates are £30,000 lower (Table A11.2); delivered material prices to Hull not yet quoted [CONFIRM with supplier] |
| Land cost and availability | Nine surfaced 1.0–1.5-acre yards at £50,000–£70,000 a year (Appendix 10) | Three priced 1-acre yards at £30,000–£50,000, plus port and riverside open storage (Table A11.8); 98% of the city is at high flood risk (Hull City Council, 2019), so every site needs a flood risk assessment and an insurance quote [CONFIRM with broker] |
| Low-carbon supply capability | No evidence of a difference | No evidence of a difference |
| Service capacity headroom (fleet and driver availability) | Nearest depot Pontefract, 22 miles (Leeds 29), for spare vehicles and drivers | Nearest depot Pontefract, 40 miles (Leeds 50), so breakdown and driver cover take longer |

Note. Evidence for the scoring session (Table 4 note); no scores are proposed here. Distances are straight lines between town centres; road distances are longer. Deliveries are from the Leeds (Hunslet) job records, January 2022 to May 2026, by delivery postcode. Radius populations sum the Census 2021 usual-resident population of every built-up area whose centroid falls within eight miles of the city centre, from the ONS built-up area populations (ONS, 2023) and the ONS/OS built-up area boundaries; they are a calculation from published data, not a published figure. Workings at [APPENDIX]. Since January 2025 Leeds has delivered 1,068 m³ to HU postcodes, more than its 793 m³ to S postcodes, but to 7 customers against 86.

Table A11.2. Inputs to the Option B model and their basis

| Input | Value | Basis |
| --- | --- | --- |
| Working days | 269.5 a year | As Option A |
| Daily volume | 21.0 m³ in 2027, then 35.0, 39.2, 41.4 and 43.1 | Option A's volumes × 0.560, the ratio of the Census 2021 built-up-area populations within eight miles of Hull and Sheffield (402,845 and 719,300; author's calculation from ONS, 2023): the same market share as the board assumes for Option A. Other bases in Table A11.6 |
| Average selling price | £119/m³, rising 2.5% a year | As Option A. Procon has no Hull rate yet; six local quotes should test it, as slide 8 did for Option A [CONFIRM] |
| Materials | £61.26/m³ | As Option A, pending delivered quotes for Hull [CONFIRM with supplier] |
| Admixtures and water; fuel | £3.50 and £2.50 per m³ | As Option A |
| Rent; business rates | £40,000; £20,000 a year | Midpoint of the priced 1-acre yards, £30,000–£50,000 (Table A11.8); rates at Option A's ratio to rent |
| Labour; office and management; other fixed costs | £37,440; £72,000; £44,900 a year | As Option A. Insurance, within other fixed costs, may be higher in a flood-risk area [CONFIRM with broker] |
| Fleet | Two mixers; finance £62,800 a year each | As Option A. At Option B's volumes a third wagon is not needed |
| Capital | £278,520 | As Option A's schedule. Flood-resilience works, such as raised silo bases, are not costed [CONFIRM after site survey] |
| Inflation; working capital; tax; depreciation; maintenance capital | As Table A5.1 | As Option A |

Table A11.3. Option B base case: five-year profit and cash flow (£)

| Line | 2027 | 2028 | 2029 | 2030 | 2031 |
| --- | --- | --- | --- | --- | --- |
| Volume (m³ a day) | 21.0 | 35.0 | 39.2 | 41.4 | 43.1 |
| Price (£/m³) | 119.00 | 121.97 | 125.02 | 128.15 | 131.35 |
| Revenue | 673,542 | 1,150,635 | 1,320,929 | 1,431,321 | 1,526,581 |
| Variable costs | 380,693 | 650,350 | 746,602 | 808,997 | 862,839 |
| Fixed operating costs | 214,340 | 220,770 | 227,393 | 234,215 | 241,242 |
| Fleet finance | 125,600 | 129,368 | 133,249 | 137,247 | 141,364 |
| EBITDA | −47,091 | 150,146 | 213,684 | 250,862 | 281,137 |
| EBITDA margin | −7.0% | 13.0% | 16.2% | 17.5% | 18.4% |
| Tax | 0 | 30,574 | 46,458 | 55,753 | 63,321 |
| Increase in working capital | 59,051 | 41,828 | 14,930 | 9,678 | 8,352 |
| Maintenance capital | 6,735 | 11,506 | 13,209 | 14,313 | 15,266 |
| Free cash flow | −112,877 | 66,239 | 139,087 | 171,118 | 194,198 |
| Cumulative cash (after £278,520 capital) | −391,397 | −325,158 | −186,071 | −14,953 | 179,245 |

Note. Same mechanics as Table A5.2. As in Option A's rebuild, tax is floored at zero with no relief for the 2027 loss; if the depot trades inside Procon 24/7 Ltd, that loss would cut group tax by about £19,000 and improve 2027 cash by the same amount.

Table A11.4. Option B break-even by case

| Case | Fixed costs (£) | Contribution (£/m³) | Break-even (m³/day) | Break-even (m³/month) | Planned (m³/day) | Margin of safety |
| --- | --- | --- | --- | --- | --- | --- |
| 2027, two wagons | 339,940 | 51.74 | 24.4 | 548 | 21.0 | −16% |
| 2028, two wagons | 350,138 | 53.03 | 24.5 | 550 | 35.0 | 30% |
| 2027, full downside | 339,940 | 44.81 | 28.2 | 632 | 15.8 | −79% |

Note. Same definition as Table A8.1. Option B opens 16% below break-even, where Option A opens 29% above it.

Table A11.5. Option B scenarios, with the board's multipliers applied to every year

| Measure | Downside | Base | Upside |
| --- | --- | --- | --- |
| Multipliers: volume, price, variable cost, capital | 0.75, 0.97, 1.05, 1.10 | 1.00 throughout | 1.20, 1.02, 0.98, 0.95 |
| Capital (£) | 306,372 | 278,520 | 264,594 |
| Year-1 EBITDA (£) | −149,734 | −47,091 | 36,781 |
| Year-1 free cash flow (£) | −196,154 | −112,877 | −47,473 |
| Cumulative cash at month 12 (£) | −502,526 | −391,397 | −312,067 |
| Payback (months) | Not within five years | 48.9 | 31.1 |
| Five-year cumulative cash (£) | −531,183 | 179,245 | 733,880 |
| Board decision rule | NO-GO | NO-GO | GO |

Note. The board's rule (Table A9.1 note) is NO-GO whenever year-1 EBITDA is negative: the base case fails it by £47,091, and only the upside passes.

Table A11.6. Option B sensitivities, and the market share it would need

| Variable | Change | Payback (months) | Five-year cash (£) | Board rule |
| --- | --- | --- | --- | --- |
| Base case | Same market share as Option A: Census 2021, eight miles (0.560 of A's volume) | 48.9 | 179,245 | NO-GO |
| Population basis | Hull north bank only (0.535) | 53.4 | 95,363 | NO-GO |
| Population basis | Census 2021 built-up areas, Hull to Sheffield (0.541) | 52.2 | 115,821 | NO-GO |
| Population basis | Eight miles around the shortlisted yards, HU8 and S9 (0.497) | Not within five years (about 63 if 2031 cash continues) | −30,618 | NO-GO |
| Population basis | 2011 built-up areas, as in the earlier draft (0.458; ONS, 2013) | Not within five years (about 78 if 2031 cash continues) | −160,645 | NO-GO |
| Volume | Enough for payback within four years (1.01 times A's share; 57% of A's volume) | 48.0 | 199,283 | NO-GO |
| Volume | Enough for 2027 EBITDA of zero (1.16 times A's share; 65% of A's volume) | 37.6 | 479,701 | GO |
| Volume | Enough to match Option A's payback (1.69 times A's share; 95% of A's volume) | 23.1 | 1,433,655 | GO |
| Volume | Equal to Option A's (1.79 times A's share) | 21.5 | 1,608,261 | GO |
| Volume | 25% above base, all years | 33.4 | 646,368 | GO |
| First-year volume | −25% | 53.3 | 107,717 | NO-GO |
| Fleet | One wagon in 2027 (finance −£62,800 that year); no backup unit | 44.6 | 242,045 | GO |
| Rent | £30,000 a year (rates £15,000) | 45.7 | 242,723 | NO-GO |
| Rent | £50,000 a year (rates £25,000) | 52.3 | 115,768 | NO-GO |
| Price | −10% | Not within five years | −270,395 | NO-GO |
| Materials | +10% | Not within five years (about 65 if 2031 cash continues) | −60,103 | NO-GO |

Note. 'Share' means Option B's share of its local market relative to the share the board model assumes for Option A. Paybacks beyond 60 months are extrapolated from 2031 free cash flow and are indicative only. At Option A's volumes Hull would pay back faster than South Yorkshire, because its yard costs £30,000 a year less, so the case against Option B is demand, not cost. The population basis moves the result more than any other input, and one wagon passes the board's rule only by giving up the backup cover Section 3.4 values.

Table A11.7. Option B net present value and discounted payback at alternative discount rates

| Discount rate | Net present value over five years (£) | Discounted payback (months) |
| --- | --- | --- |
| 0% (as presented) | 179,245 | 48.9 |
| 8% | 42,110 | 56.2 |
| 10% | 15,563 | 58.5 |
| 12% | −8,556 | Not within five years (about 61) |

Note. Positive at 8% and 10% and negative at 12%, so whether Option B survives the Section 4.4 exclusion depends on the rate the board sets; it fails the board's GO rule at any rate, because of its first-year loss.

Figure A11.1. Cumulative cash from Option A and Option B, base cases, against the 2028 opening

Note. Rebuilt from the depot model (Tables A5.2 and A11.3). The dotted line shows Option B if it matched Option A's volumes, which would need 1.8 times Option A's market share.

Table A11.8. Surfaced yards identified in Hull and the western corridor

| Location | Size (acres) | Basis | Annual rate | Listing |
| --- | --- | --- | --- | --- |
| Lime Street, Hull HU8 (former dry dock; concreted; River Hull frontage) | 1.0 | To let | £35,000 | PrimeLocation 70900914 |
| Century Yard, Hedon Road, Hull HU12 (fenced; two container offices) | 1.0 | To let | £50,000 | Garness Jones 12605 |
| Stonepit Road, South Cave HU15 (hard-core surface; can be split) | 8.0 in total | To let | £30,000 per acre | Garness Jones 7956 |
| Foster Street, Hull HU8 (mostly concrete; River Hull frontage) | 2.0–7.0 | To let, three-year minimum | Not quoted | PrimeLocation 70900788 |
| Alexandra Dock, Port of Hull (tarmac; 24-hour security) | 1.16 | To let | Not quoted | ABP Property 138733 |
| King George Dock, Port of Hull (heavy-duty surface) | Up to 4 | To let | Not quoted | ABP Property, Port of Hull |

Note. Agents' listings, October 2026. South Cave is about 12 miles west of Hull centre, so a yard there would move the catchment towards Brough and the M62. A 0.8-acre Cottingham site (£12,000) was excluded as below the 1-acre minimum used for Option A. Foster Street is also home to two competitors' plants (Table A11.9).

Table A11.9. Competitors in the Hull catchment

| Competitor | Type | Location and notes |
| --- | --- | --- |
| Ready Crete Ltd | Volumetric | Dunswell, HU6; active, incorporated July 2023, SIC 23630 ready-mixed concrete (Companies House, n.d.); its website (readycrete.co.uk) advertises a volumetric mixer for Hull and surrounding areas |
| Mixamate Concrete & Screed | Volumetric with built-in pump | National operator advertising same- or next-day volumetric supply across Hull, HU7 (Mixamate, n.d.); local base and fleet size not stated [CONFIRM] |
| Cemex | Fixed plant and aggregates wharf | West Quay, Alexandra Dock, HU9 (Agg-Net, n.d.-b) |
| Ashcourt Concrete | Fixed plants, truck mixers and pump | Foster Street, Hull, and Melton; supplied a 1,200 m³ pour for the A63 Castle Street scheme from two plants and 10–16 mixers (Concrete Connect, n.d.) |
| Sandsfield Gravel Co. | Fixed plant | Foster Street, HU8 (Agg-Net, n.d.-a) |
| Heidelberg Materials | Fixed plant; Supamix mini-mix | Bridlington, delivering within 25 miles; open weekdays 07:00–17:00 and Saturdays to 12:00 (Heidelberg Materials, n.d.) |

Note. Desk search (AI-assisted; prompt list), October 2026, corrected after review: an earlier draft missed both volumetric operators, so Option B is not uncontested. No competitor in either catchment publishes capacity, so competition is scored on a count of operators until the Business Development Manager confirms who runs volumetric mixers around Hull, and at what scale [CONFIRM]. The fixed plants keep set hours; both volumetric rivals offer same- or next-day supply.

Table A11.10. Ranked shortlist

| Rank | Option | Weighted score (Table 4) | Payback (months) | NPV at 8–12% (£) | Outcome |
| --- | --- | --- | --- | --- | --- |
| 1 | A, South Yorkshire | [XX.X] | 23.1 | 889,618–1,053,412 | Recommended |
| [ ] | B, Hull and the Humber | [XX.X] | 48.9 | −8,556 to 42,110 | Not recommended for 2027: first-year loss fails the board's GO rule; Depot 3 conditional (§5.2; §6) |
| [ ] | C, defer and consolidate | [XX.X] | n/a | [XX,XXX] | [ ] |
| — | Do nothing (baseline) | [XX.X] | n/a | 0 | Anchor for the cost of inaction |

Note. Rank by weighted score once Table 4 is complete; an option that fails the financial test is excluded whatever its score (Section 4.4).

## Appendix 12. Board presentation and depot model

[INSERT: the presentation as shown to the board on [DATE], 13 slides. Slides 5 and 6 still carry 'add screenshot' placeholders; complete or remove them first.]

Table A12.1. Content of the board presentation and where this proposal uses it

| Slide | Content | Used in |
| --- | --- | --- |
| 1 | Title: scaling plan, South Yorkshire depot | — |
| 2 | Why Sheffield and South Yorkshire: an unserved market at the edge of the network, shared labour and resources with Leeds, little cannibalisation, regeneration pipeline | §4.3; Table 3 |
| 3 | Target customers, council frameworks, National Highways Area 12 and SDF2 Lot 2 | §4.3; Table 3 |
| 4–6 | Nine surfaced yards in the Sheffield–Doncaster corridor | Appendix 10 |
| 7 | Delivered material cost by mix, non-certified and BSI | Appendices 5 and 9 |
| 8 | Market rates and planned pricing; materials margin by mix | §4.4; Appendix 9 |
| 9 | Local competition | Appendix 4 |
| 10 | Financial case: dashboard of the depot model | §4.4; §5.2; Appendices 5, 8 and 9 |
| 11 | Operating structure; fleet of 11 wagons, two at South Yorkshire and three from year 2 | Appendices 8 and 9 |
| 12–13 | Next locations and the five-depot estate | §5.2; §6; Appendix 11 (Depot 3, East Yorkshire) |

Note. Market rates on slide 8 come from two volumetric and four drum quotations, the drum prices pro-rated to 4 m³, so the 9% discount to the market average (§4.4) rests on six quotes. Option B was appraised after this presentation and goes to the board with this proposal at G0 (Table 8).

## Appendix 14. Implementation Gantt chart and RACI matrix

[INSERT: project and implementation Gantt charts]

Table A14.1. RACI matrix: implementation

| Activity | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| Framework maintenance and annual re-run | Business Manager | Managing Director | Operations Manager | Board |
| Planning submission and consent | Managing Director | Managing Director | Business Manager | Board |
| Land acquisition / lease | Business Manager | Managing Director | Operations Manager | Depot teams |
| Fleet procurement (32t-compliant) | Business Manager | Managing Director | Operations Manager; Scheduler | Board |
| Pre-sell programme | Business Development Manager | Business Manager | Scheduler | Board |
| Recruitment and training | Operations Manager | Business Manager | Depot teams | Board |
| Go-live and KPI monitoring | Business Manager | Managing Director | Operations Manager | Board |

Table A14.2. Planning tools evaluated for this proposal

| Tool | Strength | Limitation | Use in this proposal |
| --- | --- | --- | --- |
| Gantt chart | Shows sequence and overlap at a glance; familiar to the board | Implies certainty about dates Procon does not control; laborious to update | Shows sequence only; commitment is governed by the gates |
| Critical path analysis | Identifies the activities that set the opening date | Depends on duration estimates; activities drift to their latest start | Not used formally: the critical path runs through consents outside Procon's control |
| Stage gates (Table 8) | Capital is released only when exit criteria are met | Can delay opening if criteria are set too high | Adopted; each gate is a stop-or-go decision, a guard against escalation of commitment (Flyvbjerg, 2021) |
| RACI matrix (Table A14.1) | Makes accountability explicit; suits Procon's clear hierarchy | Dates quickly; handles ambiguity and unforeseen events poorly | Adopted; reissued at each gate |
| RAID log (Appendix 15) | Separates risks from assumptions, issues and dependencies; records opportunities as well as threats | Can grow into a list nobody acts on | Adopted; every entry has an owner and a review gate |

Note. Strengths and limitations of the Gantt chart, critical path analysis and RACI matrix follow Beverley-Jones (2026, slides 25, 27 and 45).

## Appendix 15. RAID log

Risks are uncertain events that may help or harm the objectives; issues have already happened: 'If you can smell it, it's a risk, if you're standing in it, it's an issue' (Maylor & Turner, 2022, as cited in Beverley-Jones, 2026, slide 42). Threats carry one of four responses, tolerate, treat, transfer or terminate (Beverley-Jones, 2026, slide 40), opportunities an action to capture them, assumptions a test and dependencies an owner. Every entry is reviewed at the gate shown in Table 8.

Table A15.1. Risks (threats): responses, mitigations and escalation triggers

| Ref | Risk | L / I | Response | Mitigation | Owner | Trigger for escalation |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Volume ramp-up below model | M / H | Treat | Pre-sell 50% of break-even volume before fleet commitment | Business Development Manager | <50% pre-sold at G3 |
| R2 | 2028 payload change erodes delivery margin further than modelled | M / H | Treat | Procure 32t-compliant fleet from outset; model post-2028 case as base | Business Manager | Variable cost exceeds £68.37/m³ (payback beyond 24 months) |
| R3 | Cement cost inflation (imports 32% of UK market; UK CBAM on imports from January 2027) | H / M | Transfer (contract terms) | 24-month supply agreement; quarterly repricing review | Business Manager | Input cost +2% (payback beyond 24 months) |
| R4 | Planning consent refused or delayed | M / H | Terminate (capital exposure); treat (delay) | Consent as precondition of capital release; second site retained | Managing Director | No decision by [DATE] |
| R5 | Sector contraction exceeds CPA forecast | M / H | Tolerate | Infrastructure weighting limits exposure; the residual is accepted, since the downturn is also the opening (OP3); break-even monitored monthly | Business Manager | Depot volume 2.5% below plan for three months |
| R6 | Service reliability dilution damages brand | M / H | Treat | Capacity headroom weighted in selection (Table 4); capacity-related declines tracked monthly; contractors who also buy from other depots served first in the new catchment (§3.4) | Operations Manager | Capacity-related declines above the April–July 2026 monthly rate at any depot |
| R7 | Fleet roadworthiness and O-licence maintenance compliance (12 Warrington enquiries lost to vehicles off the road, May–Jun 2026) | M / H | Treat | Maintenance capacity and a spare unit specified in the fleet plan; inspection pass rate monitored | Operations Manager | Inspection failure, or a unit off the road for more than two working days with no spare in place |
| R8 | Pricing 9% below the local market average fails to win the extra volume it needs, about 23% more than market rates would | M / H | Treat | Rate card tested against market quotations at G3 and G7; payback sensitivity to price tracked (Appendix 9) | Business Manager | Volume below plan at G7 or average rate below £118/m³ |
| R9 | Buyers confuse Procon 24/7 with 24/7 Concrete & Aggregates, which trades across the target corridor (Table A4.4) | L / M | Treat | Record misdirected enquiries from G6; [DECISION: distinct livery or trade-mark search before entry] | Business Development Manager | Any misdirected enquiry or complaint |

Table A15.2. Opportunities (positive risks)

| Ref | Opportunity | Action to capture it | Owner | Review |
| --- | --- | --- | --- | --- |
| OP1 | Infrastructure demand in the target catchment exceeds the CPA (2026) forecast | Prioritise infrastructure contractors in the pre-sell; a strong start brings the §5.2 funding trigger forward | Business Development Manager | G3, G7 |
| OP2 | Low-carbon supply wins work from clients applying PAS 2080 | Quantify the waste advantage from returned-load records; make only substantiated claims (CMA, 2021) | Business Manager | G6 |
| OP3 | Competitors withdraw capacity from the catchment (MPA, 2026) | Track closures; rescore catchments at the annual re-run | Business Manager | Annual |

Table A15.3. Assumptions, issues and dependencies

| Ref | Type | Description | Test or action | Owner |
| --- | --- | --- | --- | --- |
| A1 | Assumption | CPA infrastructure and housing forecasts hold across the payback period (CPA, 2026) | Re-tested at the annual framework re-run | Business Manager |
| A2 | Assumption | The 2028 reversion to 32 tonnes proceeds as confirmed (DfT, 2025b) | Confirmed policy; DfT updates monitored | Business Manager |
| A3 | Assumption | Volume rises from 37.5 to 77 m³ a day over five years, based on Leeds's 2022 trading (board model) | Tested at G7; the model's typed volumes run ahead of its own ramp percentages (Table A9.4) | Business Manager |
| A4 | Assumption | Cement and aggregates available at modelled prices for 24 months | Supply agreement signed before go-live (§5.3) | Business Manager |
| A5 | Assumption | Drivers recruited and trained before go-live | G5 exit criterion | Operations Manager |
| A6 | Assumption | Two volumetrics supplied for the depot, possibly transferred from Leeds (capital schedule: 'use from Leeds depot?') | Decided before G4; a transfer removes capacity Leeds already lacks (I1) | Business Manager |
| A7 | Assumption | Option B would win the same share of its market as Option A (Census 2021 ratio 0.560), although Procon's HU volume comes from 15 customers | Before Depot 3 is committed: six Hull quotes, delivered material prices, a broker's flood-risk quote, HU enquiry data and the scoring session | Business Development Manager |
| I1 | Issue | Capacity-related declines at Leeds and Warrington: 22 of 27, April–July 2026 | Confirm the Leeds cause with the Scheduler (§5.2); track monthly as KPI 5 (Table 1) | Operations Manager |
| I2 | Issue | Decline reasons recorded as free text, so the dashboards attribute nothing | Enforce codes R01–R08 and record postcodes (§6) | Operations Manager |
| I3 | Issue | Warrington vehicles off the road on 26 May, 3 June and 12 June 2026: 12 enquiries lost | Maintenance capacity and a spare unit in the fleet plan (R7) | Operations Manager |
| D1 | Dependency | Board approval and capital release (G0) | Minuted approval (Appendix 13) | Managing Director |
| D2 | Dependency | Planning consent, operator licence variation and Part B permit (G2): local planning authority; Traffic Commissioner; local authority environmental health | No capital released before G2 | Managing Director |
| D3 | Dependency | Pre-sell threshold met before the fleet order (G3 before G4) | G3 exit criterion | Business Development Manager |
| D4 | Dependency | 32-tonne-compliant vehicles delivered within [X] weeks of order | Lead time confirmed with suppliers before G4 | Business Manager |
| D5 | Dependency | The 2028 depot depends on this depot's cash generation | Payback tracked monthly; §5.2 trigger reviewed at G8 | Managing Director |

## Appendix 16. KSB mapping

The table maps each of the fifteen KSBs assessed in this module to the sections of the proposal that evidence it, in Procon's context.

Table A16.1. KSB mapping by section

| KSB | Section | How the proposal evidences it |
| --- | --- | --- |
| K3 New market strategies, changing customer demands and trend analysis | §2 | Trend analysis of the UK RMC market (MPA, 2025b, 2026) and the housing/infrastructure demand divergence (CPA, 2026) as the basis for catchment selection. |
|  | §3 | PESTEL weighted to the domains that discriminate between catchments; supplier power traced to cement imports and UK CBAM from January 2027; demand measured per unit of competitor capacity rather than absolute volume. PESTEL carried into an external-first SWOT whose recommendations map onto the selection criteria (Minsky & Aron, 2021; Appendix 4). |
| K5 Systems thinking, knowledge and data management, research methodologies, programme management | §3 | Systems thinking: the expansion read as the limits-to-growth archetype (Clancy, 2018; Senge, 2006), with self-funding as the reinforcing loop and service capacity as the balancing one, and the leverage placed on the constraint through the capacity-headroom criterion (§3.4); root cause traced through a 5 Whys chain (§3.3). |
|  | §4 | Research methodology and data management: sequential mixed-methods design defended against rejected alternatives (Table 2); data managed across internal records, sector datasets and interview transcripts; validity through triangulation and recorded weighting provenance (§4.1). Knowledge management: the framework turns directors' tacit judgement into explicit, repeatable knowledge (Nonaka, 2008; §4.4). |
|  | §5 | Programme management: stage-gated implementation with owners and exit criteria (Table 8), with the change managed through Lewin's three stages and planning revisited at each gate (§5.7). Planning tools evaluated for fit before selection (§5.7; Table A14.2). |
| K8 Financial strategies, modelling, and evaluation of financial and non-financial information | §4 | Financial modelling — cost base, break-even, scenario and sensitivity analysis; economic theory applied through location and cost-volume-profit method. Non-financial information evaluated alongside financial: low-carbon supply capability weighted in the MCDA (Table 4) as a commercial variable affecting access to infrastructure demand, not as a compliance cost. Payback adopted as primary metric and critically defended, with discounted payback and an NPV hurdle containing its known weaknesses (§4.4). Accounting rate of return and internal rate of return evaluated and set aside, with reasons (§4.4). The appraisal is a two-stage cost-benefit analysis: MCDA ranks the options on priced and unpriced criteria, and the financial appraisal tests the ranking against cash (§4.4). The depot model presented to the board was rebuilt, reconciled to the workbook and reviewed; its faults are corrected and their effect on payback shown (Table A9.4). |
|  | §5 | Funding strategy critically evaluated across four routes using pecking-order theory, Higgins's sustainable-growth limit and real options; the self-funding chain tested against payback; opportunity cost quantified (§5.2, Table 6). |
| K9 Financial governance, legal requirements and procurement strategies | §5 | Financial governance (board approval threshold), legal requirements (O-licence variation and maintenance obligations, planning consent) and procurement strategy (32-tonne-compliant fleet; cement hedging including CBAM pass-through; lower-clinker and GGBS specification for EPD-requiring clients) — §5.3. |
| K12 Influencing and negotiating strategies, upwards and outwards | §5 | Influencing and negotiating upwards: board capital approval negotiated on underlying interests rather than stated positions, with the framework endorsed before the site recommendation was tabled (§5.6). |
| K14 Working with board and other company leadership structures | §5 | Works with the board as sponsor and approver through fortnightly reviews and a formal board paper (Table A1.1; Table 8, G0). The move from judgement to evidence in board decisions is managed as organisational change, refrozen by the board mandate, with later gates guarding against declaring victory too soon (§5.7). |
| K15 Brand and reputation management | §3 | §3.4 critically evaluates delivery reputation: questions the transfer of consumer-brand theory to B2B buyers (Leek & Christodoulides, 2012), evidences the risk from Procon's declined-work records, shows the 2028 payload change tightening the same constraint, and builds brand protection into site selection through backup-coverage logic (Hogan & ReVelle, 1986). Reputation treated as plural (Harvey et al., 2017), with the transfer of that finding tested against the share of volume from customers who buy from more than one depot (§3.4; RAID R6). |
|  | §5 | Brand protection carried into implementation via capacity-headroom risk control (RAID R6, Appendix 15) and the pre-sell sequencing decision. |
| K16 Markets, stakeholders' requirements and the sustainability agenda | §2 | Positions Procon within its market, the regulatory regime governing it (DfT, 2025b) and the stakeholder set the expansion depends on. |
|  | §3 | Five Forces locates Procon in its market and supply chain. Sustainability agenda treated as a client requirement (National Highways' PAS 2080 supply-chain mandate) and as a brand risk (green claims must be substantiated; CMA, 2021) (§3.1). |
| S2 Set strategic direction and gain support for it from key stakeholders | §2 | Sets the strategic direction — aim, five objectives and SMART KPIs (Table 1) — that board approval is subsequently sought for. |
|  | §5 | Secures board support for the strategic direction — approval evidenced at Appendix 13. |
| S3 Undertake research; critically analyse and integrate complex information | §2 | Integrates internal margin data, sector statistics and regulatory evidence into a single problem statement. |
|  | §3 | Critical analysis of complex secondary evidence; causes, drivers and symptoms separated as distinct analytical layers. The capability gap's persistence explained through the Einstellung effect (Luchins, 1942; §3.2). |
|  | §4 | Primary and secondary research critically analysed and synthesised through MCDA into a ranked, auditable shortlist. |
| S11 Use financial data to allocate resources | §4 | Financial data used to compare capital allocation across four options under identical treatment (Table 5). Fleet, price and material inputs of the board model tested for their effect on payback and on the 2028 funding gap (Appendix 9). |
|  | §5 | Allocates resources across the capital and working-capital budget (Table 7). Capital spend reconciled to budget and variances explained at gates G5 and G7 (Table 8). |
| S13 Use presence and storytelling to translate vision into operational strategies | §1 | Answer-first structure: recommendation, cost and board approval in the first three sentences, then why it matters and how it was reached: a costed ask the board can act on. |
|  | §5 | Translates the recommendation into an operational implementation plan with owners, sequencing and KPIs. Manages the organisational change the framework requires (§5.7). |
|  | §6 | Translates the decision into lasting organisational capability: post-completion audit building a reference class, coded declined-work data as a live demand map, and an annual re-run of the framework. |
| S19 Manage relationships across multiple and diverse stakeholders | §5 | Manages relationships across a diverse stakeholder set — board, operations, commercial, scheduling, suppliers, customers, planning authority (power-interest mapping and communication plan, Appendix 1). Salience (Mitchell et al., 1997) shows whose claims become urgent at each implementation gate (§5.5; Table A1.1). |
| S20 Lead and influence upwards and outwards; negotiate; use advocacy | §5 | Influencing and negotiating outwards: supplier terms negotiated on interests with a defined BATNA; advocacy sustaining Procon's reputation through the expansion. Influencing tactics matched to each stakeholder (Boddy, 2002; Table A1.1). |
| B3 Curious and innovative: explore ambiguity and complexity; find creative solutions | §3 | Ambiguity of comparing dissimilar catchments resolved through location theory (Church & ReVelle, 1974; Hotelling, 1929; Weber, 1909/1929), extended to service reliability through backup coverage (§3.4). |
|  | §4 | Creative resolution of a genuinely ambiguous comparison — non-commensurable criteria reconciled via weighted MCDA with stated provenance — followed by critical examination of the instrument's own limits (§4.4). |
|  | §6 | Reflexive account of ambiguity encountered and how the analysis was revised in response. |

## Appendix 19. Declined-work analysis, Leeds and Warrington (April to July 2026)

Leeds and Warrington record declined enquiries on the same log template, issued in April 2026, which defines eight reason codes, R01 to R08; staff recorded free-text reasons instead, so the logs' summary dashboards attribute nothing. The author coded each of the 27 entries against the log's own scheme (Table A19.2). Entries saying only that nothing was free before about 4pm cannot be split between a missing vehicle (R02) and a missing driver (R03), so they are coded R02/R03, capacity with the cause not recorded. Leeds entries run from 5 May to 29 July 2026 and Warrington entries from 25 April to 19 June 2026; the Warrington log has no later entries.

Three Leeds entries are dated 2025 and one has no year; all four sit among May and June 2026 entries in a template first issued in April 2026, so they are treated as 2026. One Warrington volume is logged as '50m+' and is counted as 50 cubic metres, so price-related volume is a minimum. Revenue is recorded for only three entries, so lost revenue is not analysed. Customer names are withheld and sites are given by area; reasons are reproduced as logged, with one staff name removed. Three readings are the author's: W03 records rates of £145 and £119 by load size without saying whose they are; W11 is read as a loss to a competitor ('MCR') quoting £111 a cubic metre against Procon's £117; and W02 as an unresolved scheduling query.

By count, capacity accounts for 22 of the 27 declines. Those 22 involve 16 customers: three were refused more than once, one of them five times. None of the 21 customers in the two logs appears at both depots. By volume it accounts for 75 of at least 384 cubic metres, while two jobs lost on price account for at least 250 (Table A19.1; Figure A19.1). All twelve Warrington vehicle declines fall on three days: 26 May, 3 June (a failed six-weekly inspection) and 12 June (a breakdown). At Leeds, six of the nine capacity declines record only a morning shortage with no cause, and a seventh (L10) an afternoon one.

Table A19.1. Declined enquiries by coded reason

| Code | Category | Leeds | Warrington | Total | m³ |
| --- | --- | --- | --- | --- | --- |
| R02 | Capacity: vehicle unavailable | 0 | 12 | 12 | 37 |
| R03 | Capacity: driver unavailable | 2 | 1 | 3 | 13.5 |
| R02/R03 | Capacity: cause not recorded | 7 | 0 | 7 | 24.5 |
|  | Subtotal: capacity | 9 | 13 | 22 | 75 |
| R06 | Price not agreed (lost to competitor) | 0 | 2 | 2 | ≥250 |
| R01 | Beyond range / distance | 0 | 1 | 1 | 18 |
| R08 | Other (unclear) | 0 | 1 | 1 | 6 |
| — | No reason recorded | 1 | 0 | 1 | 35 |
|  | Total | 10 | 17 | 27 | ≥384 |

Figure A19.1. Declined enquiries by number and by volume, Leeds and Warrington, April to July 2026

Note. Data from the Leeds and Warrington declined-work logs, April to July 2026, coded by the author (Table A19.2). Price-related volume is a minimum, because one job was logged as '50m+'.

Table A19.2. Coded register of declined enquiries (L = Leeds, W = Warrington)

| ID | Date (as logged) | Area | m³ | Reason as logged | Code |
| --- | --- | --- | --- | --- | --- |
| L01 | 05/05/2026 | Cookridge | 3 | Offered 3.30pm no availbility before didnt book moved on | R02/R03 |
| L02 | 23/5/26 | Rotherham, out of hours | 2.5 | No driver availbility | R03 |
| L03 | 29/5/ (no year; treated as 2026) | Wakefield | 2.5 | No Availability until 4pm | R02/R03 |
| L04 | 3.6.25 (treated as 2026) | Wetherby | 3 | wanted am slot nothing available offerd pm did not book | R02/R03 |
| L05 | 4.6.25 (treated as 2026) | Leeds (Otley Road) | 2 | No Availability until 4pm | R02/R03 |
| L06 | 4.6.25 (treated as 2026) | Dewsbury | 2 | No Availability until 4pm | R02/R03 |
| L07 | 4.6.26 | Site noted as 'Castle' | 9 | No Availability until 4pm | R02/R03 |
| L08 | 18/07/2026 | Huddersfield (HD2), Saturday | 9 | No drivers to work the afternoons Saturday x2 OHH £750 & £450 | R03 |
| L09 | 20/07/2026 | Batley | 35 | (none recorded) | — |
| L10 | 29/07/2026 | Leeds | 3 | cant take afternoon slots | R02/R03 |
| W01 | 25/04/2026 | Carrington, out of hours | 2 | No Driver | R03 |
| W02 | 28/04/2026 | Atherton (M46) | 6 | Ask [staff member] was slots on clear after first job ? | R08 |
| W03 | 22/5/26 | Leigh | 200 | Chorley Concrete won this 1m3 deliveries £145.00 2m3 £119.00 on Gen3 | R06 |
| W04 | 26/5/26 | Golborne | 4 | Truck off the road | R02 |
| W05 | 26/5/26 | Manchester | 4 | Truck off the road | R02 |
| W06 | 26/5/26 | Westhoughton | 2 | Truck off the road | R02 |
| W07 | 26/5/26 | Stockport | 2 | Truck off the road | R02 |
| W08 | 3.6.26 | Stockport (two sites) | 4 | Didnt pass 6 weekly taken off the road | R02 |
| W09 | 3.6.26 | Golborne | 4 | Didnt pass 6 weekly taken off the road | R02 |
| W10 | 3.6.26 | Manchester | 3 | Didnt pass 6 weekly taken off the road | R02 |
| W11 | 8.6.26 | Culcheth | ≥50 | 4.5 miles from depot MCR £111.00 [rate recorded: £117/m³] | R06 |
| W12 | 12.6.26 | Stockport (am) | 2 | No truck broke down no commander unit | R02 |
| W13 | 12.6.26 | Chorley | 3 | No truck broke down no commander unit | R02 |
| W14 | 12.6.26 | Manchester | 2 | No truck broke down no commander unit | R02 |
| W15 | 12.6.26 | Great Sankey | 5 | No truck broke down no commander unit | R02 |
| W16 | 12.6.26 | Stockport (pm) | 2 | No truck broke down no commander unit | R02 |
| W17 | 19/06/2026 | Wirral | 18 | Too far to tarvel on return for a slab | R01 |